## Cover sheet
3GPP TSG-RAN WG5 Meeting #101 | [10 empty] | R5-236880
Chicago, United States, Nov. 13-17, 2023
Agenda Item: | 7.5.2
Source: | Huawei
Title: | WP UE Conformance - Further Multi-RAT Dual-Connectivity enhancement
Work item code: | LTE_NR_DC_enh2-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of UE Conformance - Further Multi-RAT Dual-Connectivity enhancement is to define the UE conformance requirements corresponding to WID on further enhancement on MR-DC, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for Rel-17. At the RAN#99 meeting in Mar. 2023 the Rel-17 RAN5 work item for UE Conformance - Further Multi-RAT Dual-Connectivity enhancement was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 94% (+49%) | 9 (+9) | 14
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 97.5% (+50.5%) | 5 (+5) | 6
FR1 |  | 100% (+54%) | 2 (+2) | 2
FR2 |  | 96.1% (+48.7%) | 3 (+3) | 4
NSA Option 3 (EN-DC) |  | 91.9% (+47.1%) | 4 (+4) | 8
FR1 |  | 93.4% (+50.5%) | 3 (+3) | 5
FR2 |  | 89.4% (+41.6%) | 1 (+1) | 3
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%) |  |  |  | 100% (+100%) |  |  | 100% (+100%)
Common ICS | 38.508-2 | 100% (+95%) |  |  | 100% (+95%) |  |  | 100% (+95%) |  |  |  | 100% (+95%) |  |  | 100% (+95%)
UE specific test functions | 38.509
NR RF/RRM
RRM test cases | 38.533 | 94.6% (+47.3%) | 9 (+9) | 14 | 100% (+50%) | 2 (+2) | 2 | 95.3% (+47.3%) | 3 (+3) | 4 |  | 92.3% (+50%) | 3 (+3) | 5 | 86.7% (+36.7%) | 1 (+1) | 3
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% (+80%) |  |  | 100% (+80%) |  |  | 100% (+80%) |  |  |  | 100% (+80%) |  |  | 100% (+80%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%) |  |  |  | 100% (+100%) |  |  | 100% (+100%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
5 References
[1] RP-230436 | New WID on UE Conformance - Further Multi-RAT Dual-Connectivity enhancement
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Further Multi-RAT Dual-Connectivity enhancement | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_NR_DC_enh2-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Further Multi-RAT Dual-Connectivity enhancement comprising the necessary new clauses/test cases and updates to existing clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [13 empty] | vs Area
WP Resp: |  | Yaping Zhang, Huawei |  |  | zhangyaping13@huawei.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR2
[15 empty] | 100% (+54%) | 96.1% (+48.7%) | 93.4% (+50.5%) | 89.4% (+41.6%)
[15 empty] | 6 (+2) | 11 (+3) | 11 (+2) | 7 (+2)
[15 empty] | 2.6 (+0.2) | 4.9 (+0.3) | 5.8 (+0.2) | 3.6 (+0.2)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | Adding the default message configuration for MR-DC enhancements | Huawei, Hisilicon |  | R5-237818 R5-236876 R5-237858 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100% | 100% | 100%
TS 38.508-2: Common ICS
20 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases | Nokia, Nokia Shanghai Bell | RAN5#102 (Feb-24) | R5-235614 R5-236874 |  | 0.1 | 100% (+95%) | 100% (+95%) | 100% (+95%) |  | 100% | 100% | 100% | 100%
NR RF/RRM
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
1 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533. | Nokia, Nokia Shanghai Bell, Sporton, Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-234348 R5-236875 R5-237772 |  | 0.1 | 100% (+80%) | 100% (+80%) | 100% (+80%) |  | 100% | 100% | 100% | 100%
TS 38.533: RRM test cases
|  | 38.533 | 4.5 | Signaling characteristics | [5 empty] | 0
|  | 38.533 | 4.5.2 | Interruption | [5 empty] | 0
2 | Y | 38.533 | 4.5.2.10 | EN-DC FR1 interruptions due to RRM and RLM/BFD measurements on deactivated NR PSCell | Verify E-UTRAN PCell interruptions due to RRM measurements and RLM/BFD measurements on the deactivated NR PSCell | Sporton | RAN5#101 (Nov-23) | R5-235709 R5-237805 | TS 38.133 cl A.4.5.2.10 | 1 | 100% (+50%) |  | 100% (+50%) |  |  |  | 100%
|  | 38.533 | 4.5.3 | SCell activation and deactivation delay | [5 empty] | 0
18 |  | 38.533 | 4.5.3.0 | Minimum conformance requirements | Adding minimum conformance requirements for Fast Scell Activation | Huawei, Hisilicon | RAN5#100 (Aug-23) | R5-234807 | TS 38.133 cl 8.3.16 | 0.1 | 100% |  | 100% |  |  |  | 100%
3 | Y | 38.533 | 4.5.3.6 | EN-DC FR1 Fast SCell Activation of known SCell in FR1 for 160ms SCell measurement cycle | Verify the fast SCell activation times for 160ms SCell measurement cycle | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-235909 R5-236227 | TS 38.133 cl A.4.5.3.6 | 1 | 100% (+50%) |  | 100% (+50%) |  |  |  | 100%
4 | Y | 38.533 | 4.5.3.7 | EN-DC FR1 Fast SCell Activation of known SCell in FR1 for 640 ms SCell measurement cycle | Verify the fast SCell activation times for 640ms SCell measurement cycle | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-236910 R5-236228 | TS 38.133 cl A.4.5.3.7 | 1 | 100% (+50%) |  | 100% (+50%) |  |  |  | 100%
|  | 38.533 | 4.5.10 | PSCell activation and deactivation delay | New sub-clause header |  |  |  |  | 0
5 | Y | 38.533 | 4.5.10.1 | EN-DC FR1 PSCell activation and deactivation delay | Verify that the NR PSCell activation and deactivation delay under EN-DC are within core requirements | Sporton | RAN5#101 (Nov-23) | R5-235710 R5-237806 | TS 38.133 cl A.4.5.10.1 | 1 | 80% (+80%) |  | 80% (+80%) |  |  |  | 80%
|  | 38.533 | 4.5.11 | Conditional PSCell addition and release delay | New sub-clause header |  |  |  |  | 0
19 |  | 38.533 | 4.5.11.0 | Minimum conformance requirements | Adding minimum conformance requirements for Conditional PSCell addition | Huawei, Hisilicon | RAN5#100 (Aug-23) | R5-234808 | TS 38.133 cl 8.9A | 0.1 | 100% |  | 100% |  |  |  | 100%
6 | Y | 38.533 | 4.5.11.1 | EN-DC FR1 Addition and Release Delay of PSCell | Verify that the NR conditional PSCell addition and release delays under EN-DC are within the requirements | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-235908 R5-237803 | TS 38.133 cl A.4.5.11.1 | 1 | 80% (+30%) |  | 80% (+30%) |  |  |  | 80%
|  | 38.533 | 5.5 | Signaling characteristics | [5 empty] | 0
|  | 38.533 | 5.5.3 | SCell activation and deactivation delay | [5 empty] | 0
7 | Y | 38.533 | 5.5.3.8 | EN-DC FR2 Fast SCell Activation of SCell in FR2 intra-band | Verify that the fast SCell activation and deactivation times are within the requirements | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-235911 R5-236230 | TS 38.133 cl A.5.5.3.8 | 1 | 100% (+50%) |  | 100% (+50%) |  |  |  |  | 100%
|  | 38.533 | 5.5.12 | PSCell activation and deactivation delay | New sub-clause header |  |  |  |  | 0
8 | Y | 38.533 | 5.5.12.1 | EN-DC FR2 PSCell activation and deactivation delay | Verify that the NR PSCell activation and deactivation delay under EN-DC are within the requirements | Sporton | RAN5#101 (Nov-23) | R5-235711 R5-237807 | TS 38.133 cl A.5.5.12.1 | 1 | 80% (+30%) |  | 80% (+30%) |  |  |  |  | 80%
|  | 38.533 | 5.5.13 | Conditional PSCell addition and release delay | New sub-clause header |  |  |  |  | 0
9 | Y | 38.533 | 5.5.13.1 | EN-DC FR2 Addition and Release Delay of NR PSCell | Verify that the conditional NR PSCell addition and release delays under EN-DC are within the requirements | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-235712 R5-237808 | TS 38.133 cl A.5.5.13.1 | 1 | 80% (+30%) |  | 80% (+30%) |  |  |  |  | 80%
|  | 38.533 | 6.5 | Signaling characteristics | [5 empty] | 0
|  | 38.533 | 6.5.3 | SCell activation and deactivation delay | [5 empty] | 0
10 | Y | 38.533 | 6.5.3.10 | NR SA FR1 Fast SCell Activation of known SCell in FR1 in non-DRX for 160ms SCell measurement cycle | Verify that the fast SCell activation and deactivation times are within the requirements | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-235912 R5-236231 | TS 38.133 cl A.6.5.3.10 | 1 | 100% (+50%) | 100% (+50%) |  |  | 100%
11 | Y | 38.533 | 6.5.3.11 | NR SA FR1 SCell Activation of known SCell in FR1 in non-DRX for 640 ms SCell measurement cycle | Verify that the fast SCell activation and deactivation times are within the requirements | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-235913 R5-236232 | TS 38.133 cl A.6.5.3.11 | 1 | 100% (+50%) | 100% (+50%) |  |  | 100%
|  | 38.533 | 7.5 | Signaling characteristics | [5 empty] | 0
|  | 38.533 | 7.5.3 | SCell activation and deactivation delay | [5 empty] | 0
12 | Y | 38.533 | 7.5.3.13 | NR SA FR2 SCell Activation for SCell in FR2 intra-band in non-DRX | Verify that the fast SCell activation and deactivation times are within the requirements | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-235914 R5-236233 | TS 38.133 cl A.7.5.3.13 | 1 | 100% (+50%) | 100% (+50%) |  |  |  | 100%
13 | Y | 38.533 | 7.5.3.14 | NR SA FR2 SCell Activation for known SCell in FR2 inter-band | Verify that the fast SCell activation and deactivation times are within the requirements | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-234810 R5-237954 | TS 38.133 cl A.7.5.3.14 | 1 | 100% (+50%) | 100% (+50%) |  |  |  | 100%
|  | 38.533 | 7.5.12 | Conditional PSCell addition and release delay | New sub-clause header |  |  |  |  | 0
14 | Y | 38.533 | 7.5.12.1 | Addition and Release Delay of PSCell | Verify that the conditional PSCell addition and release delays under SA are within the requirements | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-234811 R5-237809 | TS 38.133 cl A.7.5.12.1 | 1 | 100% (+50%) | 100% (+50%) |  |  |  | 100%
15 | Y | 38.533 | 7.5.14 | NR SA FR2 PSCell RACH-less based Activation and deactivation for FR1+FR2 inter-band with target PSCell in FR2 | Test the activation PSCell delay for a UE configured with one deactivated SCG in NR-DC and when PScell in one SCG is being activated | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-234812 R5-237953 | TS 38.133 cl A.7.5.14 Editor’s note: This test case is incomplete. The following aspects are either missing or TBD - General test parameters are TBD since it’s missing in TS 38.133 | 1 | 80% (+30%) | 80% (+30%) |  |  |  | 80%
17 |  | 38.533 | Annex A | RRM test configurations | RRM test configurations Adding CSI-RS, CSI-IM configurations | Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-234813 |  | 0.1 | 100% (+90%) | 100% (+90%) |  |  |  | 100%
21 |  | 38.533 | Annex E | Cell configuration mapping | Define cell configuration mapping | Nokia, Nokia Shanghai Bell,Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-234367 R5-237804 R5-237810 |  | 0.1 | 100% (+90%) | 100% (+90%) |  |  |  | 100%
22 |  | 38.533 | Annex F | Measurement uncertainties and test tolerances | Define measurement uncertainties and test tolerances | Nokia, Nokia Shanghai Bell,Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-237804 R5-237810 |  | 0.1 | 100% (+90%) | 100% (+90%) |  |  |  | 100%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
16 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | TT analysis for RRM Test cases | Nokia, Nokia Shanghai Bell, Sporton, Huawei, Hisilicon | RAN5#101 (Nov-23) | R5-236224 R5-236225 R5-236226 R5-236391 R5-236393 R5-236395 R5-237956 R5-236872 R5-236873 |  | 0.3 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  | 100% | 100% | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
TBD |  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  | TBD |  |  | 0.1
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.