3GPP TSG RAN meeting #102										RP-233763

Edinburgh, Scotland, December 11-15, 2023

## Status Report to TSG

Agenda item:			13.3.30

| WI / SI Name | UE Conformance - Further Multi-RAT Dual-Connectivity enhancement |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: No | Performance part: No |  | Testing part: Yes |
| Acronym | LTE_NR_DC_enh2-UEConTest |  |  |  |  |
| Unique ID | 991033 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-230436 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: N/A | Core part: N/A | Performance part: N/A | Testing part: Mar. 2024 |  |
| Overall Completion level | Study Item: N/A | Core part: N/A | Performance Part: N/A | Testing part: 94% |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | RAN 5 |
| --- | --- | --- |
| Rapporteur | Name | Yaping ZHANG |
|  | Company | Huawei |
|  | Email | zhangyaping13@huawei.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

Additional explanations/motivations for the time budget changes in the attached Excel table:

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

## 2.1	RAN1

#### 2.1.1	Agreements

#### 2.1.2	Remaining Open issues

## 2.2	RAN2

#### 2.2.1	Agreements

#### 2.2.2	Remaining Open issues

## 2.3	RAN3

#### 2.3.1	Agreements

#### 2.3.2	Remaining Open issues

## 2.4	RAN4

#### 2.4.1	Agreements

#### 2.4.2	Remaining Open issues

## 2.5	RAN5

#### 2.5.1	Agreements

WP is updated based on RAN5#101 output as [1].

31 CRs agreed during this meeting, and the WI completion reaches 94%.

All RRM test cases are completed with TT analysis included except for 7.5.14 SCG activation. And the remaining work is to define signaling test cases.

#### 2.5.2	Remaining Open issues

#### 2.5.3	Remaining Open issues with cross-WG dependencies

## 2.6	RAN6

#### 2.6.1	Agreements

#### 2.6.2	Remaining Open issues

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SAx/CTs

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention.

## 4.	References

NOTE:	This can be e.g. a list of all related Tdocs in the affected WGs since last TSG, references to LSs, produced TRs/TSs, the work/study item description or status reports of previous TSGs.

General documents

- R5-236880	WP UE Conformance - Further Multi-RAT Dual-Connectivity enhancement	Huawei, HiSilicon

TS 38.508-1 CRs

- R5-237818	Addition of SCG activation and deactivation configuration for NR-DC	Huawei, HiSilicon

- R5-236876	Addition of aperiodic TRS configuration for fast SCell activation	Huawei, HiSilicon

- R5-237858	Addition of conditional PSCell addition configuration for NR-DC	Huawei, HiSilicon

TS 38.508-2 CRs

- R5-236874	Addition of physical layer baseline capabilities for MR-DC enhancements	Huawei, HiSilicon

TS 38.533 CRs

- R5-236227	Completion of EN-DC FR1 fast SCell activation test case for 160 ms SCell measurement cycle	Nokia, Nokia Shanghai Bell

- R5-236228	Completion of EN-DC FR1 fast SCell activation test case for 640 ms SCell measurement cycle	Nokia, Nokia Shanghai Bell

- R5-237803	Completion of EN-DC FR1 test case for the conditional addition delay of PSCell	Nokia, Nokia Shanghai Bell

- R5-236230	Completion of EN-DC FR2 fast SCell in intra-band activation test case	Nokia Shanghai Bell

- R5-236231	Completion of NR SA FR1 fast SCell activation test case for 160 ms SCell measurement cycle	Nokia, Nokia Shanghai Bell

- R5-236232	Completion of NR SA FR1 fast SCell activation test case for 640 ms SCell measurement cycle	Nokia, Nokia Shanghai Bell

- R5-236233	Completion of NR SA FR2 fast SCell in intra-band activation test case	Nokia, Nokia Shanghai Bell

- R5-237804	Measurement uncertainty and test tolerance updation of fast SCell activation and CPAC test cases	Nokia, Nokia Shanghai Bell

- R5-237805	Update of RRM Test Case 4.5.2.10 EN-DC FR1 interruptions due to RRM and RLM/BFD measurements on deactivated NR PSCell	Sporton

- R5-237806	Update of RRM Test Case 4.5.10.1 EN-DC FR1 PSCell activation and deactivation delay	Sporton

- R5-237807	Update of RRM Test Case 5.5.12.1 EN-DC FR2 PSCell activation and deactivation delay	Sporton

- R5-237954	Update of 7.5.3.14 Fast SCell activation including test tolerance	Huawei, HiSilicon

- R5-237953	Update of 7.5.14 PSCell activation including test tolerance 	Huawei, HiSilicon

- R5-237808	Update of 5.5.13.1 Conditional PSCell Addition including test tolerance	Huawei, HiSilicon

- R5-237809	Update of 7.5.12.1 Conditional PSCell Addition including test tolerance	Huawei, HiSilicon

- R5-237810	Update of Annex F for MR-DC enhancement test cases including Test Tolerance	Huawei, HiSilicon

TR 38.903 CRs

- R5-236224	Addition of test tolerance analysis for fast SCell activation test cases of 4.5.3.6, 4.5.3.7, 6.5.3.10, 6.5.3.11	Nokia, Nokia Shanghai Bell

- R5-236225	Addition of test tolerance analysis for CPAC test cases of 4.5.11.1	Nokia, Nokia Shanghai Bell

- R5-236226	Addition of test tolerance analysis for fast SCell activation test cases of 5.5.3.8 and 7.5.3.13	Nokia, Nokia Shanghai Bell

- R5-236391	Addition of test tolerance analysis for 4.5.2.10 EN-DC FR1 interruptions due to RRM and RLM/BFD measurements on deactivated NR PSCell	Sporton

- R5-236393	Addition of test tolerance analysis for 4.5.10.1 EN-DC FR1 PSCell activation and deactivation delay	Sporton

- R5-236395	Addition of test tolerance analysis for 5.5.12.1 EN-DC FR2 PSCell activation and deactivation delay	Sporton

- R5-237956	Addition of test tolerance analysis for 7.5.3.14 Fast SCell activation 	Huawei, HiSilicon

- R5-236872	Addition of test tolerance analysis for Conditional PSCell Addition FR2 test cases	Huawei, HiSilicon

- R5-236973	Addition of test tolerance analysis for 7.5.14 PSCell activation	Huawei, HiSilicon

TS 38.522 CRs

- R5-236875	Addition of test applicability for MR-DC enhancement test cases	Huawei, HiSilicon

- R5-237772	Addition of test applicability and condition for RRM MR-DC Rel-17 Test Cases	Sporton

26.04.2023		minor adaptations for RAN #100

01.02.2023		minor adaptations for RAN #99

27.10.2022		minor adaptations for RAN #98e

01.08.2022		minor adaptations for RAN #97e

21.05.2022		minor adaptations for RAN #96

10.01.2022		minor adaptations for RAN #95e

04.10.2021		minor adaptations for RAN #94e

08.08.2021		minor adaptations for RAN #93e

17.05.2021		minor adaptations for RAN #92e

28.01.2021		minor adaptations for RAN #91e

09.11.2020		minor adaptations for RAN #90e

31.08.2020		minor adaptations for RAN #89e

20.04.2020		minor adaptations for RAN #88e

18.02.2020		minor adaptations for RAN #87e

14.11.2019		minor adaptations for RAN #86

18.08.2019		minor adaptations for RAN #85

12.05.2019		minor adaptations for RAN #84

27.02.2019		minor adaptations for RAN #83

21.11.2018		completion levels with colours added (for RAN #82)

v04.81	31.07.2018		simplification of template and addition of cross-TSG aspects (for RAN #81)

v04.80	21.05.2018		minor adaptations for RAN #80

v04.79	26.02.2018		minor adaptations for RAN #79

v04.78	18.11.2017		minor adaptations for RAN #78

v04.77	06.08.2017		minor adaptations for RAN #77

v04.76	15.05.2017		minor adaptations for RAN #76

v04.75	31.01.2017		minor adaptations for RAN #75

v04.74	28.10.2016		minor adaptations for RAN #74

v04.73	01.09.2016		adaptations for RAN #73 (time units in extra Excel table, RAN6 reporting included)

v04.72	26.05.2016		adaptations for RAN #72 (introduction of NR & GERAN TUs)

v04.71	10.02.2016		minor adaptations for RAN #71

v04.70	30.10.2015		minor adaptations for RAN #70

v04.69	12.08.2015		minor adaptations for RAN #69

v04.68	21.05.2015		minor adaptations for RAN #68

v04.67	01.02.2015		minor adaptations for RAN #67

v04.66	16.11.2014		minor adaptations for RAN #66

v04.65	16.08.2014		minor adaptations for RAN #65

v04.64	22.05.2014		minor adaptations for RAN #64

v04.63	24.01.2014		restructuring for RAN #63 to cover Core & Perf. in one doc file

v03.62	11.11.2013		section 1.2.3 adapted for RAN #62

v03	11.08.2013		section 1.2.3 added on time budget

v02	07.05.2010		history added, some spelling corrections

v01	13.11.2009		First version of the template