## Slide 1: Views on IMT-2030 submission timeline
Source: vivo
3GPP TSG RAN Meeting #103
Maastricht, Netherlands, March 18-21, 2024
RP-240139

## Slide 2: Background
In RP-233985, high level consideration for 6G timeline was endorsed in RAN #102 with following milestone
  TSG-wide 6G workshop: March 2025
  Stage 1 workshop: May 2024
  SA1 SID approval: Sep 2024
  SA2 SID approval: June 2025
  RAN WG SIDs approval: June 2025
  IMT2030 submission release: Release 21 as a single drop
  Detailed 6G timeline approval: March 2024 (RAN #103, this meeting)
In the following slides, vivo view on the detailed 6G timeline are provided for further decisions in RAN #103 meeting

## Slide 3: Consideration for RAN level study
Stage 1 workshop on IMT 2030 is planned to collect the input from different research global/regional research organizations and others on 6G use cases.
Based on these use cases, SA1 SI on 6G is supposed to conclude the 6G use cases and corresponding requirements from service perspective.
SA1 SI is supposed to be completed in June 2025.
RAN level study on radio requirements and KPI shall consider the SA1 conclusion on requirements from service perspective
Proposal 1: RAN level study is proposed to be started from March 2025 considering SA1 stage 1 SI and TSG-wide workshop outcome.

## Slide 4: Consideration for WG level study
Projects in R19 package has been well designed in reasonable scope to guarantee the Release 19 could be timely completed, i.e., June 2025. Delay the starting of R20 WG SI will not only impact to 6G timeline but also R19 package scope.
As endorsed in RP-232985, RAN R20 SID and SA2 R20 SID are expected to be approved in June 2025.
Also, as in RP-233985, both TSG-wide workshop and Stage 1 workshop are expected to be hold in March 2025 and May 2024 respectively
Proposal 2: The starting point of 6G WG level study is to be confirmed as June 2025

## Slide 5: Consideration for target completion of R21
As endorsed in RP-233985, R21 specifications will be the 1st set of 6G spec and will be the release for IMT-2030 submission. The quality of R21 specifications is the most important factor of designing 6G timeline.
Back to R15 timeframe, due to limited time and release pressure, more ad-hoc meetings than usual were added, e.g., 3 ad-hoc in 2017 for RAN1 and RAN4. Such situation shall be avoided in R21 timeframe.
Proposal 3: At least 21 months release duration with assumption that 6 WG meetings per year shall be designed to ensure the timely completion and specifications quality.

## Slide 6
2024
Q1
Q2
Q3
Q4
2025
Q1
Q2
Q3
Q4
2026
Q1
Q2
Q3
Q4
2027
Q1
Q2
Q3
Q4
2028
Q1
Q2
Q3
Q4
2029
Q1
Q2
Q3
Q4
Release 20 (18 M)
Release 21 (21M)
6G TSG-wide Workshop
RAN Requirements SI
RAN1/2/3/4 Tech SI
RAN1 WI
RAN1 SI on Channel model ( Inc. R19)
RAN2/3/4 WI
SA SI
SA WI
SA1 SI (Release-20 part2)
CT WI
Detailed 6G Timeline planning
R21 ASN.1 freeze
Architecture Decision?
R21 ASN.1 freeze
6G stage 1 workshop
IMT-2030 submission
CT SI