## Slide 1
Views on 6G timeline from CAICT
2024.03
3GPP TSG RAN#103 RP-240322
Maastricht, Netherlands, March 18-21, 2024
Agenda Item: 15

## Slide 2: Background
Some consensus have been achieved in last plenary for 6G timeline
  First TSG-wide 6G workshop is expected to be in March 2025
  Studies for 6G in 3GPP are expected to start from Release 20
    SA1 SID is expected to be approved in Sept’2024.
    RAN plenary SID (e.g., radio requirements and KPIs) is expected to be approved TBD (to be decided at RAN#103)
    SA2 SID is expected to be approved in June’2025. Other SA-WG SIDs (e.g., Security, etc.) are expected to be approved TBD
    RAN-WG SIDs are expected to be approved in June’2025
    CT-WG SIDs are expected to be approved TBD
  IMT-2030 submission and normative work for 6G in 3GPP are expected to start from Release 21
    Release 21 is expected to produce the 1st set of 3GPP 6G technical specifications, and will be the release for IMT-2030 submission before 2030
    Release 21 is expected to be delivered with a single drop (i.e., a single code freeze)
  Target TSG#103 (March’2024) for the remaining detailed 6G timeline decisions

## Slide 3: Overall 6G timeline proposal
R18
R19
R20/21
ITU
3GPP
RAN WG WI
RAN WG SI
SA1 SI + WI
RAN Req. SI
SA2 SI
SA2 WI
Proposed timeline
RAN plenary SID (e.g., radio requirements and KPIs) is proposed to be approved in June’2025 (no earlier than SA/RAN workshop)
21 month(R20)+21month(R21) is proposed to ensure the quality of 6G spec
SA1 6G workshop
SA+RAN 6G workshop
first 6G ASN.1 frozen

## Slide 4: Thanks