## Slide 1: Way forward on 6G timeline
NTT DOCOMO, CMCC, SK Telecom, LG Uplus, KT Corp.
3GPP TSG RAN meeting #103
Maastricht, Netherlands, March 18-21, 2024
RP-240786

## Slide 2: Background – TSG#102
RP-233985 - Endorsed​

## Slide 3: Discussion points
Rel-21
  ASN.1 freeze timing  Single drop with range between March-Sept’2029, to be decided later based on the progress
    Address both potential early mover of commercial 6G in 2030 and other operators seeking 6G value
    Meet the timeline for IMT-2030 self-evaluation to be submitted to ITU-R
Rel-20+21
  Duration  18 months at least for Rel-20 5G-A WIs, Rel-20 6G SI can be longer than 18 months, 21 months for Rel-21 5G-A/6G WIs as baseline
    Each release has WIs for 5G-A as well: longer duration leads to late deployment of 5G-A
    Sufficient study duration is necessary for 6G
RAN plenary SI
  Approval date  Dec’2024 or March 2025
  SI Start → from TSG#107 (March 2025, Just after 6G WS) based on the outcome from 6G WS
    Need high-level RAN requirement to start RAN-WG Rel-20 SI
Note: ITU-R interaction on IMT-2030 TPR can be done, e.g. via LS, even before 6G WS

## Slide 4: Proposed timeline
2023 |  |  |  | 2024 | 2023 | 2023 | 2023 | 2025 | 2023 | 2023 | 2023 | 2026 | 2023 | 2023 | 2023 | 2027 | 2023 | 2023 | 2023 | 2028 | 2023 | 2023 | 2023 | 2029 | 2023 | 2023 | 2023 | 2030 | 2023 | 2023 | 2023
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
3GPP RAN
6G WS (joint SA/CT/RAN)
ITU-R
Technical performance requirements
Evaluation criteria & methodology
Requirements, evaluation criteria and submission templates
Circular Letter
Workshop
Technology proposals for IMT-2030
Evaluation
Consensus building
Outcome & decision
IMT-2030 spec.
Timeline discussion
WS on 6G use cases
3GPP SA/CT
Stage 1 (SA1)
Stage 2 (SA2)
6G SI (Rel-20) + WI (Rel-21)
Stage 3 + ASN.1/Open API (CT)
6G SI (Rel-20) + WI (Rel-21)
6G SI (Rel-20) + WI (Rel-21)
6G RAN1 SI (Rel-20) + WI (Rel-21)
SID approval: Sep 24
SID approval: June 25
SID approval: June 25
*Endorsed in TSG#102
6G RAN2/3/4 SI (Rel-20) + WI (Rel-21)
ASN.1 freeze
Single drop
w/ range March-Sept’2029
6G RAN plenary SI