## Slide 1
3GPP Work Plan
Review at Plenary #103
Source: MCC / Work Plan Manager (A. Sultan)
Agenda item: Review of the Work Plan
Document for: Information
Review based on the latest available version of the Work Plan, available at: https://ftp.3gpp.org/Information/WORK_PLAN
Includes: - the progress on all WIDs, as indicated in the WG Chairs’ reports (CT & SA) and in the Status Report (RAN), - the new WIDs proposed by SA/CT WGs to TSG#103 (subject to removal if not TSG-approved)
Does not include: - the company-proposed WIDs approved at TSG#103
Warnings :
- This review is a high-level view of the 3GPP progress. It is based on the 3GPP Work Plan, a continuously updated document.
Some misalignments might temporarily appear on some individual items.
- Some WG cannot progress because of reasons beyond their control (e.g. dependencies with other groups).
These slides shall not be used to judge the “efficiency” of whatever WG.
© 3GPP 2024
RP-240824 (rev of CP-240012/RP-240017/SP-240418 )- 3GPP TSG#103, 18 -22 March 2024, Maastricht, The Netherlands

## Slide 2: Content of this Work Plan review
Snapshot of all ongoing Releases
Ongoing Releases
  Rel-18 Timeline and Progress
  Rel-19 Timeline and Progress
  Rel-20 Timeline and Progress
  Rel-21 Timeline and Progress
Background information

## Slide 3
Ongoing Releases timelines
#96
Release 19
Release 18
Note: All starting dates are indicative
#98e
#100
#102
#104
#106
#108
#110
#112
#114
2022
2023
2025
*: +3 months for RAN4
**: - 3 months for RAN1 & + 3 months for RAN4 perf
SA1 Stage 1
Stage 3 (CT & SA)
Stage 2 Normative
RAN Content def.*
RAN Completion**
Maint.*
ASN.1 & Open APIs
ASN.1
1st review
#99
#101
#103
#107
#109
#111
#113
2024
2026
SA1 Stage 1
RAN Completion**
Stage 3 (CT & SA)
ASN.1 & Open APIs
Stage 2 Normative
#105
#97-e
RAN Content Def*
SA St.2 Content Def
2021
#92-e
#94-e
#95-e
#93-e
Mar.
#91-e
TSGs
Mar.
Mar.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Dec.
Dec.
Dec.
Now

## Slide 4: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 5
Release 18 timeline
#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Release 18
Note: All starting dates are indicative
#94-e
#95-e
#96
#97-e
#98-e
#99
#100
#101
#102
#103
#104
#105
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2024
Now
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review
TSGs
2021
RAN Completion (RAN2/3/4core)

## Slide 6: Release 18 Progress: Stages 1 & 2
Stage 1 and TSG content definition:
  Completed since TSG#94
  SA1 has 25 normative items plus 14 studies.
Stage 2 at SA2 and SA6:
  Studies :
    Completed since TSG#99
    SA2 and SA6 have 43 studies
  Normative :
    Completed since TSG#100 (last remaining item was EDGEAPP_EXT (UID 960011, SA6, now “98%”)
    SA2 and SA6 have 57 normative items

## Slide 7: Release 18 Progress: Stage 3 (SA/CT)
Stage 3 (CT WGs) and SA3, SA4 and SA5*: reaching completion.
  Studies:
    71 studies for all these WGs
    All complete
  Normative:
    244 items for all these WGs
    OCI** (St.3 Norm) = 92% - against 78% at previous TSG
    Items below 50%:
*Note: For tools limitation reasons, SA3, SA4 and SA5 are reported here, even if they cover several Stages
**OCI = Overall Completion Index = average of all % completion
UID | Name | Acronym | WG | Target | %
990025 | Immersive Audio for Split Rendering Scenarios | ISAR | S4 | 06/06/2024 | 35%
1030026 | CT1/CT3/CT4 aspects of IVAS_Codec | IVAS_Codec |  | 06/06/2024 | 0%

## Slide 8: Release 18 Progress: Stage 3 (RAN)
Stage 3 in RAN: (reminder: new WIDs/SIDs approved at RAN#103 not considered here)
  RAN studies (21 items): All 100% complete (was 95%)
  RAN Core aspects : OCI: 93% - against 88% at previous RAN
    95 items in total
    67 items are 100% complete
    Items below 80%: see table
  RAN Perf aspects: OCI: 72% - against 55% at previous RAN
    73 item in total
    25 items are 100% complete
  RAN5 testing: OCI: 57% (12 items)
UID | Name | Acronym | WG | Target | %
981145 | Core Part: Introduction of 900 MHz NR band in the US | NR_900MHz_US-Core | R4 | 12/12/2023 | 25%
961113 | Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe | NR_RAIL_HPUE_n100_n101-Core | R4 | 12/12/2023 | 0%
961108 | Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) | NR_CADC_R18_yBDL_xBUL-Core | R4 | 06/06/2024 | 60%
1011053 | Core pat: Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC | R18_3Tx_NR_CA_ENDC-Core | R4 | 06/06/2024 | 70%
970188 | Core part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) | HPUE_FR1_DC_LTE_NR_R18-Core | R4 | 06/06/2024 | 75%
960199 | Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R18_xBDL_yBUL-Core | R4 | 06/06/2024 | 55%
991140 | Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW-Core | R4 | 12/12/2023 | 0%

## Slide 9: Release 18 recap – text version
Release 18 Freezes and other milestones, sorted by dates :
  Sept 2021 (TSG#93): Stage 1: 80% normative work; SA Workshop; joint SA/RAN/CT meeting
  Dec 2021 (TSG#94):
    Stage 1: 100% normative work
    RAN/SA/CT joint meeting on Rel-18 content; SA2 Work Items prioritization; RAN Content Definition
  Mar 2022 (TSG#95): RAN4-lead WIDs specified
  June 2022 (#96) till March 2023 (#99): no specific deadline
  June 2023 (TSG#100): Stage 2 Functional work (SA2 and SA6) Freeze
  Sep 2023 (TSG#101):
    RAN1 freeze (before maintenance)
    Freeze for SA3 (stages 2 & 3) – maintenance to continue
  Dec 2023 (TSG#102):
    RAN1 (after maintenance) declared frozen
    RAN2, RAN3, RAN4Core (before maintenance) declared frozen
  Mar 2024 (TSG#103):
    RAN2, RAN3, RAN4Core freeze maintenance
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze
    (also first review of ASN.1)
  June 2024 (TSG#104):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs
Now

## Slide 10: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 11
Release 19 timeline
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop

## Slide 12: Release 19 progress overview
Stage 1 (SA1):
  Studies :
    14 studies – stable for long
    All studies completed (including last exception: FS_ISN)
  Normative :
    24 tasks, including “miniWIDs” - one new WID at SA#103 (ISN, completed in one cycle)
    All normative work completed (including exception on ISN)
Stage 2 (SA2, SA6)
  SA & RAN Content defined at TSG#101 & 102 (considering SA1 outputs)
  Studies: 23 studies, OCI = 38% (against nearly 0% at previous TSG)
  Normative: 22 items, OCI = 17% (against nearly 0% at previous TSG)
All other groups (Stage 3, RAN):
  RAN studies: 3 Studies, just started
  RAN Core: 10 items (OCI=4%)
  RAN Perf: 9 items, not started
  Other RAN: 6 items (OCI=10%)
  SA3: 16 studies (OCI=7%); 7 normative WIDs (just starting)
  SA4: 7 studies, 2 normative; all just starting
  SA5: 17 studies, 2 normative; all just starting
  CT WG: not started (0 WID/SID so far)

## Slide 13: Release 19 timeline recap - text version
Release 19 Freezes and other milestones, sorted by dates :
  June 2023: RAN workshop on Rel-19 content, SA workshop on Rel-19 content
  Sept 2023 (TSG#101):
    Stage 1: 80% normative work
    Approve 1st part of SA Stage 2 package (SA/CT)
  Dec 2023 (TSG#102):
    Stage 1: 100% normative work
    RAN1/2/3 Content Definition
    Approve final package of SA Stage 2 with RAN/CT
  Mar 2024 (TSG#103): RAN4 Content Definition
  Dec 2024 (TSG#106): Stage 2 Functional work (SA2 and SA6) Freeze (working assumption)
  June 2025 (TSG#108): RAN1 freeze
  Sept 2025 (TSG#109):
    RAN2, RAN3, RAN4Core freeze
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze (working assumption)
  Dec 2025 (TSG#110):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs (working assumption)
Now

## Slide 14: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 15
Release 20 timeline
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
2024
2025
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Dec.
Dec.
Dec.
Now
TSGs
SA1 5GA SIDs selection
SA2 & RAN WG 6G SIDs sel.
Workshop 6G TSGs
No further timeline defined at this stage
100%
SA1 5GA St + Norm 80%
TSG RAN 6G SIDs selection
?
100%
SA2 5GA St + Norm 80%
SA2 6G St.
5GA ASN.1 & Open APIs
Stage 3 5GA St + Norm 100%
Stage 3 6G SIDs sel.
2026
#113
#114
Sep.
Dec.
#115
Mar.
2027
?
Jun
RP SI ITU
RP SI 6G
Rel-20 5GA
Rel-20 6G
SA1 6G SIDs selection
SA1 6G St.
Workshop IMT2030 use cases
RAN1 SI 6G
RAN2/3/4 SI 6G
St3. 6G St.
?
RAN4
content def.
RAN Content def.
RAN Rel-20 workshop
RAN1
RAN Completion (RAN2/3/4core)
RAN4_Perf

## Slide 16: More info on Release 20 (1/2)
SA1’s approach to split Rel-20 into “Rel-20_5GA” and “Rel-20_6G” is globally adopted
  Rel-20_5GA covers 5GA studies and normative; Rel-20_6G covers 6G studies only (6G normative in Rel-21)
Rel-20_5GA tentative deadlines:
  Stage 1 approval of SIDs: Jun 2024; Stage 1 normative freeze : Jun 2025
  Stage 2 approval of SIDs: not yet defined (NYD); Stage 2 normative freeze : Jun 2026 (80%); Sep 2026 (100%)
  Stage 3 (CT) approval of SIDs: Mar 2026 or earlier; Stage 3 CT normative freeze : Mar 2027
  Stage 3 RAN approval of SIDs:NYD; Stage 3 RAN normative freeze : NYD
  ASN.1/OpenAPI freeze: June 2027
  RAN : + 18 months compared to Rel-19 dates, i.e.
    Content def: June 2025
    Ran1: Dec 2026
    RAN2/3/4Core: March 2027
    RAN4 Perf: June 2027
Sources: SP-240192 (SA1 chair), CT-240307/SP-240458/RP-240823 (TSG Chairs)

## Slide 17: More info on Release 20 (2/2)
Rel-20_6G tentative deadlines: (only studies)
  Stage 1 approval of SIDs: Sep 2024 (TSG 105); Stage 1 (study) freeze: Mar 2026
  March 2025 (TSG#107): First TSG-wide 6G workshop
  SA2 and RAN-WG approval of SIDs: June 2025 (TSG 108); SA2 (study) freeze: Dec 2026 or Mar 2027
  SA1/SA2 6G SI may continue beyond Stage-1/Stage-2 freeze dates for 5G-Advanced
  Other SA WG (SA3, SA4, SA5, SA6) SI approval: TBD at future TSG meeting
  RAN1 starts in 3Q/25 until 1Q/27; RAN2/3/4 start in 4Q/25 until 2Q/27
  CT WG 6G SI will start 9 months after approval of SA2 SI.
Sources: SP-240192 (SA1 chair), SP-240432 from TSG Chairs

## Slide 18: Release 20 progress overview
Stage 1 (SA1):
  First 3 Rel-20 Studies submitted to TSG#103:
    Study on Satellite Access Phase 4
    Study on FRMCS Phase 6
    Study on Energy Efficiency as Service Criteria Phase 2
  Normative :
    Not started
Stage 2, Stage 3, RAN:
  Not started

## Slide 19: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 20: Release 21 initial talks
Release 21 is the release for submission to IMT-2030*, aka 6G
This implies that 3GPP (normative) work will be submitted to ITU before 2030
  However, ASN.1/OpenAPI freeze date is no earlier than March 2029
Release 21 Freezing dates and other milestones TBD
  Rel-21 timeline is to be decided no later than June 2026
Note that, as usual in 3GPP, previous Generations will also continue to be maintained & enhanced
* source: TSG#102-endorsed RP-240815

## Slide 21
All-Releases timelines
Release 19
Release 18
Note: starting dates are indicative
#100
#102
#104
#106
#108
#110
#112
#114
2024
2025
2027
* 3 months earlier for RAN1 & 3 months later for RAN4 perf
RAN completion with Maint
Stage 3 (CT & SA)
#99
#101
#103
#107
#109
#111
#113
2026
2028
#105
2023
Mar.
TSGs
Mar.
Mar.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Dec.
Dec.
Dec.
Now
Release 20
Release 21
Stage 1 SIDs (5GA & 6G)
Approval process
Rel-21 = 6G (study &) normative => Stage 3 & RAN completion before 2030
Workshop IMT2030 use cases
Workshop 6G TSGs
Rel-20 = 5GA (study & normative) & 6G Studies
St.3 + RAN compl*
Stage 1 + RAN content
Stage 2
#115
#117
#119
#116
#118
No further timeline defined at this stage
No further timeline defined at this stage
Stage 1 timeline not yet defined
?
Stage 2 & RAN WG
6G SIDs
Approval process
TO BE UPDATED

## Slide 22: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-18 Timeline and Progress
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 23: Background information (1/2): overall background information
Dedicated e-mail list for Work Plan aspects
Open to everyone interested (rapporteus, chairs, delegates, etc.) by sending the message “Subscribe 3GPP_WORKPLAN” to the address LISTSERV@LIST.ETSI.ORG
For comments/update to the Work Plan, please use the 3GPP_WORKPLAN list
3GPP Work Plan
http://www.3gpp.org/ftp/Information/WORK_PLAN
Contains Release 1999 to Release 20; Master version in MS Project; Working versions in Excel
Tutorials on content, maintenance and other info on the Work Plan in subfolder /info
3GPP Releases Descriptions – R99 to Rel-17
http://www.3gpp.org/ftp/Information/WORK_PLAN/Description_Releases/
“Releases Descriptions” for Releases 8 to 13: limited to copy-paste of the WIDs.
“Releases Descriptions” for Releases 14 to 17: TR 21.9xx: “Release xx Description; Summary of Rel-xx Work Items”, written in collaboration with all the Rel-xx Features Rapporteurs
3GPP Releases Descriptions – Rel-18
Started – v.0.2.0 in SP-240419 / RP-240037 / CP-240284

## Slide 24: Background information (2/2): Relationship between WGs, Stages and deadlines
Most 3GPP Working Groups handle only one Stage:
  SA1  Stage 1
  SA2  Stage 2; SA6  Stage 2
  CT WGs  Stage 3 (also Stage 2 for some specific items)
SA3, SA4 and SA5 handle several Stages for some or all their WIDs:
  SA3: handles Stages 2 and 3 for all its WIDs. Stage 2 at SA3 is one quarter after SA2/SA6’s deadline, but this date is an SA3-internal date since there is no dependency (i.e. SA3 is not expecting work from any other WGs)
  SA4: handles Stage 2 for some WIDs (for which SA4 might rely on CT WGs for Stage 3), and Stage 3 for a majority of its WIDs. Stage 2 WIDs in SA4 are clearly identified as such and have the same deadline as SA2/SA6’s date.
  SA5: handles Stages 1, 2 and 3 for all its WIDs. Stage 1 for SA5 is 4 quarters after SA1’s date. Stage 2 for SA5 is 2 quarters after SA2/SA6’s date. Stage 3 for SA5 is same date as CT WGs’ date.
  For SA3, SA4 and SA5, the completion date for all WIDs dealing with Stage 3 (fully or partially) is the same as for CT WGs.
  In this Work Plan review slides, SA3, SA4 and SA5 are reported in the “Stage 3” slides since their overall completion date is aligned with (CT’s) Stage 3. Except for SA4’s Stage 2-only WIDs but this cannot be handled by the present tools.
RAN has a slightly different process. RAN defines two dates:
  The “RAN Content Definition”, which is the same date as SA Stage 1 and SA content definition
  The “RAN Completion”, which is the same date as SA/CT’s Stage 3
  Note that there is no specific RAN-equivalent date for SA/CT’s Stage 2