## Cover sheet
3GPP TSG-RAN5 Meeting # 106 | [10 empty] | R5-250370
Athens, Greece, 17th Feb 2025 - 21st Feb 2025
Agenda Item: | 6.3.30
Source: | Qualcomm
Title: | Mobile Terminated-Small Data Transmission (MT-SDT)
Work item code: | NR_MT_SDT-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 65% (+25%) | 50% | 6 (+6)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 65% (+25%) | 50% | 6 (+6)
FR1 |  | 65% (+25%) | 0 | 6 (+6)
FR2 |  | 65% (+25%) | 0 | 6 (+6)
FR1 + FR2
NSA Option 3 (EN-DC)
FR1
FR2
FR1 + FR2
LTE
FDD
TDD
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 80% |  |  | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 80% |  |  | 0% |  |  | 0% |  |  | 0%
UE specific test functions | 38.509
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 80% | 1% | 6 (+6) | 0% | 1 | 6 (+6) | 0% | 1 | 6 (+6) | 0% | 0 | 6 (+6)
Applicability Protocol test cases | 38.523-2 | 100%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-241127 | Mobile Terminated-Small Data Transmission (MT-SDT) for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Mobile Terminated-Small Data Transmission (MT-SDT) | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_MT_SDT-UEConTest
WP Scope: |  | WP UE Conformance Test Aspects - Rel-18 NR small data transmissions in INACTIVE state | [14 empty] | vs Area
WP Resp: |  | Yogesh Tugnawat |  |  | Yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | LTE |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FDD | TDD | FDD + TDD
[14 empty] | Overall |  | 40% (+30%) | 40% (+30%)
[14 empty] | Number of WP items |  | 9 (+9) | 9 (+9) | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Sum weight of WP items |  | 8 (+8) | 8 (+8) | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Contribution by work plan analysis |  | 10%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4, 6 | Introduction of General and Signaling Test Environment for Rel-17 Small Data Transmission Tests | ASN.1 and other updates All RRC updates from 38.331 | Qualcomm | RAN5#104 (Aug-24) |  |  | 1 | 80% | 80% |  |  |  | 80% | 80%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4.4 | Introduction of common implementation conformance statements for Rel-17 Small Data Transmission Tests | Add ICS as needed for the test case applicability statements for the new test cases | Qualcomm | RAN5#104 (Aug-24) |  |  | 1 | 80% | 80% |  |  |  | 80% | 80%
RAN and CN protocol
TS 38.523-1: Protocol test cases
RRC
4 |  | 38.523-1 | 8.1 | NR RRC | Existing sub-clause header |  |  |  |  | 0
5 |  | 38.523-1 | 8.1.5 | RRC others | Existing sub-clause header |  |  |  |  | 0
6 |  | 38.523-1 | 8.1.5.13 | Small Data Trasmission | Existing sub-clause header |  |  |  |  | 0
7 | Y | 38.523-1 | 8.1.5.13.4 | RRC MT-SDT / CG based / Success | TS38.331, cl 5.3.2.3, cl. 5.3.13.1b, TS 38.321 cl.5.27.1 | Qualcomm | RAN5#105 (Nov-24) | R5-247634 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
8 |  | 38.523-1 | 8.1.5.1.1 | UE capability transfer / Success | TS38.331, cl 5.3.2.3, cl. 5.3.13.1b | Qualcomm | RAN5#104 (Aug-24) |  | Updates to UE capabilty test case | 1 | 100% | 100% |  |  |  | 100% | 100%
MAC
9 |  | 38.523-1 | 7.1 |  | Existing sub-clause header |  |  |  |  | 0
10 |  | 38.523-1 | 7.1.1 | RRC others | Existing sub-clause header |  |  |  |  | TBD
11 |  | 38.523-1 | 7.1.1.13 | Small Data Trasmission | Existing sub-clause header |  |  |  |  | 1
12 | Y | 38.523-1 | 7.1.1.13.6 | RA Based MT-SDT/2-step RACH/Success | TS 38.321 cl.5.27.1, cl.5.2, TS38.331, cl 5.3.2.3, cl. 5.3.13.1b | China telecom | RAN5#106 (Feb-25) | R5-251318 |  | 1 | 80% | 80% |  |  |  | 80% | 80%
13 | Y | 38.523-1 | 7.1.1.13.7 | RA Based MT-SDT/4-step RACH/Success | TS 38.321 cl.5.27.1, cl.5.2, TS38.331, cl 5.3.2.3, cl. 5.3.13.1b | Motorola Mobility/Lenovo | RAN5#105 (Nov-24) | R5-247636 |  | 1 | 100% | 100% |  |  |  | 100% | 100%
14 | Y | 38.523-1 | 7.1.1.13.8 | RA Based MT-SDT / 4-Step RACH /RACH resources instead of CG resources / Success | TS 38.321 cl.5.27.1, cl.5.2, TS38.331, cl 5.3.2.3, cl. 5.3.13.1b | Motorola Mobility/Lenovo | RAN5#106 (Feb-25) | R5-247637 | Test Purpose, Test Title Alignment migh tbe needed in next meeting i.e RAN5#106 | 1 | 80% | 80% |  |  |  | 80% | 80%
15 | Y | 38.523-1 | 7.1.1.13.9 | RA Based MT-SDT/ 4-step RACH / Time Alignment Timer | TS 38.321 cl.5.27.1, cl.5.2, TS38.331, cl 5.3.2.3, cl. 5.3.13.1b | ZTE | TBD |  | y | 1 | 0% | 0% |  |  |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
16 | Y | 38.523-2 | 4.1, 4.2 | Applicability for MT-SDT Test Case | Place holder |  | RAN5#105 (Nov-24) | R5-247635 R5-247638 |  |  | 100% | 100% |  |  |  | 100% | 100%
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.