## Cover sheet
3GPP TSG-RAN5 Meeting #106 | [10 empty] | R5-250868
Athens, Greece, 17th Feb 2025 – 21st Feb 2025
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon
Title: | WP of UE Conformance - IMS Data Channel test after RAN5 105
Work item code: | NG_RTC_IMS_dataCH-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 21% (+16%) | #VALUE! | #VALUE!
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 21.4% (+16.4%) | 1 (+1) | 6 (+4)
FR1 |  | 21.4% (+16.4%) | 1 (+1) | 6 (+4)
FR2 |  | 21.4% (+16.4%) | 1 (+1) | 6 (+4)
FR1 + FR2
NSA Option 3 (EN-DC)
FR1
FR2
FR1 + FR2
LTE |  | 20.8% (+15.8%) | 1 (+1) | 6 (+4)
FDD |  | 20.8% (+15.8%) | 1 (+1) | 6 (+4)
TDD |  | 20.8% (+15.8%) | 1 (+1) | 6 (+4)
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1 | 7.7% (+7.7%) |  |  | 0% | 0 | 4 (+4) | 0% | 0 | 4 (+4) | [12 empty] | 16.7% (+16.7%) | 1 (+1) | 6 (+4) | 16.7% (+16.7%) | 1 (+1) | 6 (+4)
IMS over 5GS protocol test cases | 34.229-5 | 50% (+50%) | 1 (+1) | 2 | 50% (+50%) | 1 (+1) | 2 | 50% (+50%) | 1 (+1) | 2
Applicability and ICS IMS test cases | 34.229-2 | 50% (+50%) |  |  | 50% (+50%) |  |  | 50% (+50%)
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - IMS Data Channel for NG RTC (Real Time Communication) | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | NG_RTC_IMS_dataCH-UEConTest
WP Scope: |  | <WP Scope description> | [14 empty] | vs Area
WP Resp: |  | Zhaobing Yang |  |  | yangzhaobing@huawei.com | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | LTE |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FDD | TDD | FDD + TDD
[14 empty] | Overall |  | 21.4% (+16.4%) | 21.4% (+16.4%) |  |  |  |  | 20.8% (+15.8%) | 20.8% (+15.8%)
[14 empty] | Number of WP items |  | 7 (+5) | 7 (+5) | 0 | 0 | 0 | 0 | 6 (+4) | 6 (+4) | 0
[14 empty] | Sum weight of WP items |  | 6.1 (+4.1) | 6.1 (+4.1) | 0 | 0 | 0 | 0 | 6 (+4) | 6 (+4) | 0
[14 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.508 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.508 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 36.509: UE specific testing functions
|  | 36.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | <Clause> | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | TBD |  |  | TBD
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
IMS
TS 34.229-1: IMS over LTE protocol test cases
|  | 34.229-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 34.229-1 | X | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 34.229-1 | X.X | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 34.229-1 | 8.17 | Initial Registration / IMS data channel | (1) with { UE supporting IMS data channel } ensure that { when { UE is made to register for IMS } then { UE sends a correctly composed initial REGISTER request including the sip.app-subtype media feature tag with a value "webrtc-datachannel" } } (2) with { UE having sent REGISTER request } ensure that { when { UE receiving a valid 200 OK response uncluding a Feature-Caps header field with the "+g.3gpp.datachannel" header field parameter } then { UE continues to proceed the register procedure } } | China Telecom | RAN5#107 (May-25) | R5-251382 | TS 24.186 cl 9.2.1.1 | 1 | 100% (+100%) |  |  | 100% (+100%) | [7 empty] | 100% | 100%
TBD | Y | 34.229-1 | 8.18 | Re-Registration / IMS data channel | (1) with { UE supporting IMS data channel and being registered to IMS } ensure that { when { UE needs to perform re-registration procedure } then { UE sends REGISTER message including the sip.app-subtype media feature tag with a value "webrtc-datachannel" } } (2) with { UE having sent REGISTER request } ensure that { when { UE receiving a valid 200 OK response without a Feature-Caps header field with the "+g.3gpp.datachannel" header field parameter } then { UE continues to proceed the register procedure and shall not determine that the Network supports the IMS data channel capability } } |  | RAN5#107 (May-25) |  | TS 24.186 cl 9.2.2.1 The UE shall continue to indicate its IMS data channel capability as specified in the above procedure when the UE has successfully done the IMS data channel capability negotiation during IMS initial registration or re-registration. | 1 | #VALUE! |  |  | 0% | [7 empty] | 0% | 0%
TBD | Y | 34.229-1 | X..X | IMS Data Channel / Originating side / Bootstrap Data Channel fail / Voice call / Without preconditions | (1) with { UE upporting IMS data channel and being registered to IMS } ensure that { when { UE is made to establish IMS Bootstrap Data Channel } then { UE shall include SDP media-level attributes "a=dcmap" in data channel media negotiation } } (2) with { UE having send INVITE without preconditions } ensure that { when { receiving SDP answer without media-level attributes "a=dcmap" } then { UE proceeds the voice call without preconditions} |  | RAN5#107 (May-25) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0% | 0%
TBD | Y | 34.229-1 | X..X | IMS Data Channel / Originating side / Bootstrap Data Channel fail / Voice call / With preconditions | (1) with { UE upporting IMS data channel and being registered to IMS } ensure that { when { UE is made to establish IMS Bootstrap Data Channel } then { UE shall include SDP media-level attributes "a=dcmap" in data channel media negotiation } } (2) with { UE having send INVITE without preconditions } ensure that { when { receiving SDP answer without media-level attributes "a=dcmap" } then { UE proceeds the voice call with preconditions } |  | RAN5#107 (May-25) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0% | 0%
TBD | Y | 34.229-1 | X..X | IMS Data Channel / Originating side / Bootstrap Data Channel fail / Video call / Without preconditions | (1) with { UE upporting IMS data channel and being registered to IMS } ensure that { when { UE is made to establish IMS Bootstrap Data Channel } then { UE shall include SDP media-level attributes "a=dcmap" in data channel media negotiation } } (2) with { UE having send INVITE without preconditions } ensure that { when { receiving SDP answer without media-level attributes "a=dcmap" } then { UE proceeds the Video call without preconditions} |  | RAN5#107 (May-25) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0% | 0%
TBD | Y | 34.229-1 | X..X | IMS Data Channel / Originating side / Bootstrap Data Channel fail / Video call / With preconditions | (1) with { UE upporting IMS data channel and being registered to IMS } ensure that { when { UE is made to establish IMS Bootstrap Data Channel } then { UE shall include SDP media-level attributes "a=dcmap" in data channel media negotiation } } (2) with { UE having send INVITE without preconditions } ensure that { when { receiving SDP answer without media-level attributes "a=dcmap" } then { UE proceeds the Video call with preconditions } |  | RAN5#107 (May-25) |  |  | 1 | 0% |  |  | 0% | [7 empty] | 0% | 0%
TS 34.229-5: IMS over 5GS protocol test cases
|  | 34.229-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 34.229-5 | Y | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 34.229-5 | Y.Y | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 34.229-5 | 6.10 | Initial Registration / IMS data channel | (1) with { UE supporting IMS data channel } ensure that { when { UE is made to register for IMS } then { UE sends a correctly composed initial REGISTER request including the sip.app-subtype media feature tag with a value "webrtc-datachannel" } } (2) with { UE having sent REGISTER request } ensure that { when { UE receiving a valid 200 OK response uncluding a Feature-Caps header field with the "+g.3gpp.datachannel" header field parameter } then { UE continues to proceed the register procedure } } | China Telecom | RAN5#107 (May-25) | R5-251383 | TS 24.186 cl 9.2.1.1 | 1 | 100% (+100%) | 100% (+100%) |  |  |  | 100% | 100%
TBD | Y | 34.229-5 | 6.11 | Re-Registration / IMS data channel | (1) with { UE supporting IMS data channel and being registered to IMS } ensure that { when { UE needs to perform re-registration procedure } then { UE sends REGISTER message including the sip.app-subtype media feature tag with a value "webrtc-datachannel" } } (2) with { UE having sent REGISTER request } ensure that { when { UE receiving a valid 200 OK response without a Feature-Caps header field with the "+g.3gpp.datachannel" header field parameter } then { UE continues to proceed the register procedure and shall not determine that the Network supports the IMS data channel capability } } |  | RAN5#107 (May-25) |  | TS 24.186 cl 9.2.2.1 The UE shall continue to indicate its IMS data channel capability as specified in the above procedure when the UE has successfully done the IMS data channel capability negotiation during IMS initial registration or re-registration. | 1 | 0% | 0% |  |  |  | 0% | 0%
TBD | Y | 34.229-1 | X..X | IMS Data Channel / Originating side / Bootstrap Data Channel fail / Voice call / Without preconditions | (1) with { UE upporting IMS data channel and being registered to IMS } ensure that { when { UE is made to establish IMS Bootstrap Data Channel } then { UE shall include SDP media-level attributes "a=dcmap" in data channel media negotiation } } (2) with { UE having send INVITE without preconditions } ensure that { when { receiving SDP answer without media-level attributes "a=dcmap" } then { UE proceeds the voice call without preconditions} |  | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
TBD | Y | 34.229-1 | X..X | IMS Data Channel / Originating side / Bootstrap Data Channel fail / Voice call / With preconditions | (1) with { UE upporting IMS data channel and being registered to IMS } ensure that { when { UE is made to establish IMS Bootstrap Data Channel } then { UE shall include SDP media-level attributes "a=dcmap" in data channel media negotiation } } (2) with { UE having send INVITE without preconditions } ensure that { when { receiving SDP answer without media-level attributes "a=dcmap" } then { UE proceeds the voice call with preconditions } |  | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
TBD | Y | 34.229-1 | X..X | IMS Data Channel / Originating side / Bootstrap Data Channel fail / Video call / Without preconditions | (1) with { UE upporting IMS data channel and being registered to IMS } ensure that { when { UE is made to establish IMS Bootstrap Data Channel } then { UE shall include SDP media-level attributes "a=dcmap" in data channel media negotiation } } (2) with { UE having send INVITE without preconditions } ensure that { when { receiving SDP answer without media-level attributes "a=dcmap" } then { UE proceeds the Video call without preconditions} |  | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
TBD | Y | 34.229-1 | X..X | IMS Data Channel / Originating side / Bootstrap Data Channel fail / Video call / With preconditions | (1) with { UE upporting IMS data channel and being registered to IMS } ensure that { when { UE is made to establish IMS Bootstrap Data Channel } then { UE shall include SDP media-level attributes "a=dcmap" in data channel media negotiation } } (2) with { UE having send INVITE without preconditions } ensure that { when { receiving SDP answer without media-level attributes "a=dcmap" } then { UE proceeds the Video call with preconditions } |  | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
TS 34.229-2: Applicability and ICS for IMS protocol test cases
TBD |  | 34.229-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 34.229-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 34.229-1 and/or 34.229-5. |  | TBD | R5-251397 |  | 0.1 | 50% (+50%) | 50% (+50%) |  |  |  | 50% | 50%
TS 34.229-3: IMS test suite (TTCN)
|  | 34.229-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 34.229-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.