## RAN WG1
NB-CIoT - Green indicates information anticipated to be stable from TR45.820.
| WG1#82bis [5 - 9 October 2015] | WG1#83 [16-20 November 2015] | RAN#70 | WG1 ad hoc [14 - 18 December 2015] | WG1 ad hoc[11 -15 January 2016] | WG1#84[15-19 February 2016] | RAN#71
| (Malmo, Sweden) | (Anaheim, California) | Sitges | (TBD) | ( TBD) | Malta | Goteborg
XY.201 - Physical layer General description
Note: An overview document.
Comment: Get specific details & updates from other RAN1 specs
| Task 1.1 Skeleton/Scope/ToC of Spec | Task 2.1 General description of Layer 1 |  | Task 3.1 General description of Layer 1 | Task 4.1 General description of Layer 1 | Task 5.1 - Finalise General Desc
| Present skeleton, scope and initial brief description | General description of layer 1 - Mod, coding, channels |  | Further updates to the description | Revision CRs | Revision CRs
| Task 1.2 Structure of PHY specs | Task 2.2 Services provided to higher layer |  | Revision CRs
| Provide overview of PHY specifications structure | List services provided to higher layers |  | Task 3.2 Services provided to higher layer |  | Task 5.2 Finalise Services provided
|  | Task 2.3 Physical channels and modulation |  | Revision CRs |  | Revision CRs
|  | List all the PHY channels |  | Task 3.3 Physical channels and modulation | Task 4.2 Physical channels and modulation | Task 5.3 Finalise PHY channels and modulation
|  |  |  | Further updates to the PHY channels and modulation description |  | Revision CRs
|  |  |  | Revision CRs | Revision CRs
XY.211 - Physical channels and modulation
Note:
Comment: Basic desricption available in TR (could be used). Still a complex one. Ideally, done before RRC.
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 Frame structure | Task 2.1: Details of Frame structure |  | Task 3.1: Details of Frame structure | Task 4.1 Details of Frame structure | Task 5.1 Finalise Frame Structure
| Use Frame Structure from TR | Details of Frame structure |  | Further updates to Frame structure + Revision CRs | Revision CRs | Revision CRs
| Task1.3: UL PHY channels overview | Task 2.2: Details of UL PHY channels |  | Task 3.2: Details of UL PHY channels | Task 4.2: Details of UL PHY channels | Task 5.2 Finalise details of UL PHY
| Provide overview of UL PHY Shared & Control ch | Detailed description of UL PHY channels |  | Further updates to channel descriptions + Revision CRs | Revision CRs | Revision CRs
| Task1.3: DL PHY channels overview | Task2.3: Details of DL PHY channels |  | Task3.3: Details of DL PHY channels | Task 4.3: Details of DL PHY channels | Task 5.3 Finalise details of DL PHY
| Provide overview of DL PHY Shared & Control ch | Detailed description of UL PHY channels |  | Further updates to channel descriptions | Revision CRs | Revision CRs
|  | Task2.4: Modulation overview |  | Task3.4: Modulation Details | Task 4.4: Modulation Details | Task 5.4 Finalise Modulation details
|  | Provide overview of modulation schemes |  | Detailed description of Modulation | Further details of Modulation + Revision CRs | Revision CRs
|  | Task 2.5: Precoding and mapping to RE |  | Task 3.5: Precoding and mapping to RE | Task 4.5: Precoding and mapping to RE | Task 5.5 Finalise Precoding and mapping
|  | Provide overview of precoding and mapping to resource elements |  | Detailed description of precoding | Further details of precoding + Revision CRs | Revision CRs
XY.212 - Multiplexing and Channel Coding
Note:
Comment: Basic description available in TR.
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 General Coding and multiplexing | Task 2.1: Details of Channel Coding, Multiplexing & CRCs |  | Task 3.1: Details of Channel Coding, Multiplexing & CRCs | Task 4.1 Details of Channel Coding, Multiplexing & CRCs | Task 5.1 Finalise details of channel coding
| Provide overview of coding schemes | Details for both UL and DL transport and signalling |  | Revision CRs | Revision CRs | Revision CRs
XY.213 - Physical layer procedures
Note: Detailed specification of PHY layer procedures.
Comment: Basic description of PHY layer procedures in TR. CHECK if L1 procedures (RACH etc) can be developed in parallel with RAN2. Need to be broadly complete before RRC encoding?
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 PHY Procedures (overview) | Task 2.1 Details of synchronisation and cell search |  | Task 3.1 Details of synchronisation and cell search | Task 4.1 Details of synchronisation and cell search
| Provide overview of PHY procedures | Provide synchronisation and cell search procedures |  | Further details | Revision CRs
| Provide UL shared channel procedures | Task 2.2 Details of random access procedures |  | Task 3.2 Details of random access procedures | Task 4.2 Details of random access procedures | Task 5.1 Finalise RACH
| Provide DL shared channel procedures | Provide details of RACH procedures |  | Further details of RACH procedures | Revision CRs | Revision CRs
| Provide control channel procedures | Task 2.3 Details of UE receiving shared channel proc |  | Task 3.3 Details of UE receiveing shared channel proc | Task 4.3 Details of UE receiveing shared channel proc | Task 5.2 Finalise UE share ch proc
| Provide Power control procedures | Provide details of DL PHY shared channel procedures |  | Further details of DL PHY shared channel procedures | Revision CRs | Revision CRs
| Coverage class overview | Task 2.4 Details of UE receving control channel proc |  | Task 3.4 Details of UE receving control channel proc | Task 4.4 Details of UE receving control channel proc | Task 5.3 Finalise UE control ch proc
|  | Provide details of DL PHY control channel procedures |  | Further details of DL PHY control channel procedures | Revision CRs | Revision CRs
|  | Task 2.5 Details of Coverage Class procedures |  | Task 3.5 Details of Coverage Class procedures | Task 4.5 Details of Coverage Class procedures | Task 5.4 Details of Coverage Class procedures
|  | UE reporting, RAN determination and commands |  | Further details of UL reporting procedures | Revision CRs | Revision CRs
|  | Task 2.6 Details of Power Control procedures |  | Task 3.6 Details of Power Control procedures | Task 4.6 Details of Power Control procedures
|  | Open loop uplink power control |  | Further details of power control procedures | Revision CRs
XY.214 - Measurements
Note: UE / RAN measurement abilities
Comment: Relatively small LTE spec. For CIoT, even smaller as no inter-RAT measurement and only UE autonomous cell reselection. Output of this work needed by RAN 4?
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 UE & RAN measurement capabilites |  |  |  |  | Task 5.1 Finalise UE measurement
| Overview of measurements for UE autonomous cell reselection |  |  |  |  | Revision CRs
|  | Task 2.1 UE measurement capabilities |  | Task 3.1 UE measurement |  | Task 5.2 Finalise CIoT measurement
|  | details of UE measurement of base station |  | Revision CRs |  | Revision CRs

## RAN WG2
Green indicates information anticipated to be stable from TR45.820. Both NB CIoT and NB LTE proposals are expected to reuse L2/L3 extensively - but with careful optimisation for small data.
| WG2#91bis [5 - 9 October 2015] | WG2#92 [16-20 November 2015] | RAN#70 | WG2 ad hoc [14 - 18 December 2015] | WG2 ad hoc[11 -15 January 2016] | WG2#93[15-19 February 2016] | RAN#71
| (Malmo, Sweden) | (Anaheim, California) | Sitges | (TBD) | ( TBD) | Malta | Goteborg
XY.300 - Overall description Stage 2
Note: Important and should aim for 80% complete by Oct-Nov meetings.
Comment: Dependency on architecture (Gb vs S1 vs "S1 with eNB caching UE context" vs "S1&small data over NAS") decision by RAN#69. This impacts the design of RRC; usage of SNDCP; and impacts on the needed CT1 NAS protocol enhancements).
| Task 1.1 Skeleton/Scope/ToC of Spec | Task 2.1 Overview of architecture |  | Task 3.1 Overview of architecture | Task 4.1 Overview of architecture | Task 5.1 Finalise Overview of arch
| Present skeleton, scope and initial brief description | Updates to architecture and functional splits |  | Finalise architectural design | Revision CRs | Revision CRs
| Task 1.2 Overview of architecture | Task 2.2 Overview of Layer 1 |  | Updates and Revision CRs | Task 4.2 Layer 1 | Task 5.2 Finalise Layer 1
| Provide overview of architecture | Updates and details to Layer 1 |  | Task 3.2 Layer 1 | Revision CRs | Revision CRs
| Provide functional split | [Sync with RAN1] |  | Updates to Layer 1 functions - finalise | Revision CRs
| Task 1.3 Overview of Layer 1 | Task 2.3 Layer 2 |  | Revision CRs | Task 4.3. Layer 2 | Task 5.3 Finalise Layer 2
| Provide overview of Layer 1 | Detailed functions of MAC, RLC, PDCP and RRC |  | Task 3.3. Layer 2 | Updates to Layer 2 functions | Revision CRs
| Task 1.4 Layer 2 | Task 2.4 Scheduling |  | Updates to Layer 2 functions (MAC, RLC, PDCP and RRC) | Revision CRs
| some text in TR Section 7.3.4.3 | Provide details of SI scheduling |  | Task 3.4 Scheduling | Task 4.4 Scheduling | Task 5.4 Finalise Scheduling
|  |  |  | Updates to SI scheduling | Revision CRs | Revision CRs
XY.302 - Services provided by the physical layer
Note: Fairly smaller specification
Comment:
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 Services | Task 2.1: Model of physical layer (downlink) |  | Task 3.1: Model of physical layer (downlink) | Task 4.1: Model of physical layer (downlink) | Task 5.1 Finalise model of PHY UL
| Services and functions of PHY layer | Downlink shared channel model |  | Update details of downlink shared channel model | Revision CRs
|  | Task 2.2: Model of physcial layer (uplink) |  | Task 3.2: Model of physcial layer (uplink) | Task 4.2: Model of physcial layer (uplink) | Task 5.2 Finalise model of PHY DL
|  | Uplink shared channel model |  | Update details of uplink shared channel model | Revision CRs
XY.304 - User equipment (UE) procedures in idle mode
Note: Fairly smaller specification. Removal of emergency state
Comment:
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
|  | Task 2.1: Cell selection and reselection |  | Task 3.1: Cell selection and reselection | Task 4.1 Cell selection and reselection | Task 5.1 Finalise
|  | Details of cell selection and reselection procedure |  | Finalise-cell selection and reselection | Revision CRs | Revision CRs
Task 2.2: PLMN selection
XY.306 - User equipment (UE) radio access capabilities
Note: Fairly smaller specification.
Comment: Should we think of 13dBm Tx power - is that a subscription parameter?
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
|  | Task 2.1 UE radio access capabilities |  | Task 3.1 UE radio access capabilities | Task 4.1 UE radio access capabilities | Task 5.1 Finalise UE capabilities
|  | Provide details of PHY parameters |  | Provide updated details of PHY parameters | Revision CRs | Revision CRs
|  | Provide details of MAC, PDCP, RRC parameters |  | Provide updated details of MAC, PDCP, RRC parameters
XY.321 - Medium Access Control (MAC) protocol specifications
Note:
Comment:
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 MAC architecture | Task 2.1 MAC architecture |  | Task 3.1 MAC architecture | Task 4.1 MAC architecture | Task 5.1 Finalise MAC architecture
| Provide overview of MAC services and functions | Details of MAC services and functions |  | Updated details of MAC services and functions | Revision CRs | Revision CRs
| Task 1.3 MAC procedures | Task 2.2 MAC procedures |  | Task 3.2 MAC procedures | Task 4.2 MAC procedures | Task 5.2 Finalise MAC procedures
| Overview of Random Access procedures | Details of random access procedures |  | Updated details of random access procedures | Revision CRs | Revision CRs
| Overview of DL data transfer procedure | Details of DL data transfer procedure |  | Updated details of DL data transfer procedure
| Overview of UL data transfer procedure | Details of UL data transfer procedure |  | updated details of UL data transfer procedure
| Task 1.4 MAC PDU and formats | Task 2.3 MAC PDU and formats |  | Task 3.3 MAC PDU and formats | Task 4.3 MAC PDU and formats | Task 5.3 MAC PDU and formats
| Overview of MAC PDU formats/parameters | Details of MAC PDU formats/parameters |  | Updated details of MAC PDU formats/parameters | Revision CRs | Revision CRs
XY.322 - Radio Link Control (RLC) protocol specifications
Note:
Comment: Scope of RLC specification is being worked out
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 RLC architecture | Task 2.1 RLC architecture |  | Task 3.1 RLC architecture | Task 4.1 RLC architecture | Task 5.1 Finalise RLC architecture
| Provide overview of RLC services and functions | Details of RLC services and functions |  | Updated details of RLC services and functions | Revision CRs | Revision CRs
|  | Task 2.2 RLC procedures |  | Task 3.2 RLC procedures | Task 4.2 RLC procedure | Task 5.2 Finalise RLC procedure
|  | Segmentation and reassembly |  | Updated details of segmentation and reassembly | Revision CRs | Revision CRs
|  | Task 2.3 RLC PDU and formats |  | Task 3.3 RLC PDU and formats | Task 4.3 RLC PDU and formats | Task 5.3 Finalise RLC PDU and formats
|  | Details of RLC PDU formats/parameters |  | Updated details of RLC PDU formats/parameters | Revision CRs | Revision CRs
XY.323 - Packet Data Convergence Protocol (PDCP) specification
Note:
Comment: If S1-based, PDCP
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 PDCP architecture | Task 2.1 PDCP architecture |  | Task 3.1 PDCP architecture | Task 4.1 PDCP architecture | Task 5.1 Finalise PDCP architecture
| ProvidePDCP services and functions | Details of PDCP services and functions |  | Updated details of PDCP services and functions | Revision CRs | Revision CRs
| Task 1.3 PDCP procedures | Task 2.2 PDCP procedures |  | Task 3.2 PDCP procedures | Task 4.2 PDCP procedures | Task 5.2 Finalise PDCP procedures
|  | Details of UL data transfer procedure |  | Updated details of UL data transfer procedure | Revision CRs | Revision CRs
|  | Details of DL data transfer procedure |  | Updated details of DL data transfer procedure
|  | Task 2.3 PDCP PDU and formats |  | Task 3.3 PDCP PDU and formats | Task 4.3 PDCP PDU and formats | Task 5.3 Finalise PDCP PDU and formats
|  | Details of PDCP PDU formats/parameters |  | Updated details of PDCP PDU formats/parameters | Revision CRs | Revision CRs
XY.331 - Radio Resource Control (RRC); protocol specification
Note:
Comment: Aim to provide simplified RRC (with minimal message sequences). Depends on SA2 architecture design outcome.
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 System Information | Task 2.1 System Information |  | Task 3.1 System Information | Task 4.1 System information | Task 5.1 Finalise RRC spec
| Overview of system information (necessary changes) | Details of Service Information |  | Updated details of Service Information | Revision CRs | Revision CRs
| Task 1.3 RRC services | Task 2.2 RRC Procedures |  | Task 3.2 RRC Procedures | Task 4.2 RRC procedures | Task 5.2 Finalise RRC procedures
| Overview of RRC services - messages | Details of RRC procedures/messages |  | Updated details of RRC procedures/messages | Revision CRs | Revision CRs
[5 empty] | Task 4.3 ASN.1 freezing | Task 5.3 Freeze ASN.1
[5 empty] | Initiate offline ASN.1 freezing task | conclude freezing task

## RAN WG3
| WG3#89bis [5 - 9 October 2015] | WG3#90 [16-20 November 2015] | RAN#70 | WG3#91[15-19 February 2016] | RAN#71
| (Sophia Antipolis, France) | (Anaheim, California) | Sitges | Malta | Goteborg
TS 36.413 - S1 Application Protocol (S1AP)
Note:
Comment:
| Task 1.1 CRs on S1AP functions | Task 2.1 CRs on S1AP procedures |  | Task 3.1 CRs on S1AP procedures
| List changes to functions | Updates to S1AP procedures |  | Fruther updates to S1AP procedures
| Task 1.2 CRs on S1AP procedures | Task 2.2 CRs on S1AP procedures |  | Task 3.2 CRs on S1AP procedures
| Present overview of S1AP procedures | Updates and details to Layer 1 |  | Further updates and details to Layer 1

## RAN WG4
| WG4#76bis [12- 16 October 2015] | WG4#77 [16-20 November 2015] | RAN#70 | WG4 ad hoc [11 -15 January 2016] | WG4#78 [15-19 February 2016] | RAN#71
| (Sophia Antipolis, France) | (Anaheim, California) | Sitges | ( TBD) | Malta | Goteborg
37.104 - E-UTRA, UTRA and GSM/EDGE; Multi-Standard Radio (MSR) Base Station (BS) radio transmission and reception
Note:
Comment:
| Task 1.1 Min Requirements: BS power classes | Task 2.1: Min Requirements / power classes |  | Task 3.1 Min requirements | Task 4.1 Finalise min requirements
| CRs on min requirements, BS classes/ power classes | CRs on details of requirements, BS classes, UE power classes |  | Further details + Revision CRs | Revision CRs
| Task 1.2 Operating Bands | Task 2.2: Operating Bands |  | Task 3.2 Operating Bands | Task 4.2 Finalise operating bands
| Bands, channel bandwidth, channel spacing | Details of Bands, channel BW, channel spacing |  | Further details of bands, channel BW, channel spacing | Revision CRs
| Task 1.3 Transmitter Characteristics | Task 2.3 Transmitter Characteristics |  | Revision CRs.
| Max/min BS transmit power, power control | Details of BS transmit power, power control |  | Task 3.3 Transmitter characteristics | Task 4.3 Finalise transmitter characteristics
| ACLR , spectrum emission masks | Details of ACLR and spectrum emission masks |  | Further details of BS Tx power, power control | Revision CRs
| Task 1.4 Receiver Characteristics | Task 2.4 Receiver Characteristics |  | Further details of ACLR and masks + Revision CRs
| Max input level, ACS, blocking characteristics, Reference sensitivity | Details of max input level, ACS, blocking characteristics, , Reference sensitivity |  | Task 3.4 Receiver characterisitics | Task 4.4 Receiver characteristics
| Spurious responses, intermodulation characteristics | Details of spurious responses, intermodulation |  | Further details of ACS, blocking, spurious, IM | Revision CRs
|  | Task 2.5 Performance Requirements |  | Task 3.5 Performance Requirements | Task 4.5 Performance requirements
|  | Performance requirement for BS |  | Details of performance requirement | Revision CRs
TS 37.141 - E-UTRA, UTRA and GSM/EDGE; Multi-Standard Radio (MSR) Base Station (BS) conformance testing
Note:
Comment: Testing methods and conformance requirements (for the items listed in 37.104)
| Task 1.1 Test methods and conformance requirements | Task 2.1 Test methods and conformance requirements |  | Task 3.1 Test methods and conformance requirements | Task 4.1 Finalise test methods and conformance
| Define testing methods and conformance requirements | CRs |  | CRs | Revision CRs
| Task 1.2 Operating Bands | Task 2.2 Operating Bands |  | Task 3.2 Operating Bands | Task 4.2 Finalise Operating bands
| BS testing requirements | BS testing requirements |  | Further CRs on BS testing requirements | Revision CRs
| Task 1.3 Transmitter characteristics | Task 2.3 Transmitter characteristics |  | Task 3.3 Transmitter characteristics | Task 4.3 Finalise tranmitter characteristics
| Test requirements for Tx char | CRs on test requirements for Tx char |  | Further CRs on test requirements for Tx char | Revision CRs
| Task 1.4 Receiver characterisitics | Task 2.4 Receiver characterisitics |  | Task 3.4 Receiver characterisitics | Task 4.4 Finalise receiver characteristics
| Test requirements for Rx char | CRs on test requirements for Rx char |  | Further CRs on test requirements for Rx char | Revision CRs
XY.101 - User Equipment (UE) radio transmission and reception
Note:
Comment:
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 Min Requirements: power classes | Task 2.1: Min Requirements / power classes |  | Task 3.1 Min requirements | Task 4.1 Finalise min requirements
| Define min requirements, BS classes/ power classes | Details of requirements, BS classes, UE power classes |  | Further details + Revision CRs | Revision CRs
| Task 1.3 Operating Bands | Task 2.2: Operating Bands |  | Task 3.2 Operating Bands | Task 4.2 Finalise operating bands
| Bands, channel bandwidth, channel spacing | Details of Bands, channel BW, channel spacing |  | Further details of bands, channel BW, channel spacing | Revision CRs
| Task 1.4 Transmitter Characteristics | Task 2.3 Transmitter Characteristics |  | Revision CRs.
| Max/min transmit power, power control | Details of transmit power, power control |  | Task 3.3 Transmitter characteristics | Task 4.3 Finalise transmitter characteristics
| Output RF (OOB emissions) , spectrum emission masks | Details of output RF and spectrum emission masks |  | Further details of Tx power, power control | Revision CRs
| Task 1.5 Receiver Characteristics | Task 2.4 Receiver Characteristics |  | Further details of o/p RF and masks + Revision CRs
| Max input level, ACS, blocking characteristics, Reference sensitivity | Details of max input level, ACS, blocking characteristics, Reference sensitivity |  | Task 3.4 Receiver characterisitics | Task 4.4 Receiver characteristics
| Spurious responses, intermodulation characteristics | Details of spurious responses, intermodulation |  | Further details of ACS, blocking, spurious, IM | Revision CRs
|  | Task 2.5 Performance Requirements |  | Task 3.5 Performance Requirements | Task 4.5 Performance requirements
|  | Performance requirement for CIoT device |  | Details of performance requirement | Revision CRs
XY.104 - Base Station (BS) radio transmission and reception
Note:
Comment:
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 Min Requirements: BS power classes | Task 2.1: Min Requirements / power classes |  | Task 3.1 Min requirements | Task 4.1 Finalise min requirements
| Define min requirements, BS classes/ power classes | Details of requirements, BS classes, UE power classes |  | Further details + Revision CRs | Revision CRs
| Task 1.3 Operating Bands | Task 2.2: Operating Bands |  | Task 3.2 Operating Bands | Task 4.2 Finalise operating bands
| Bands, channel bandwidth, channel spacing | Details of Bands, channel BW, channel spacing |  | Further details of bands, channel BW, channel spacing | Revision CRs
| Task 1.4 Transmitter Characteristics | Task 2.3 Transmitter Characteristics |  | Revision CRs.
| Max/min BS transmit power, power control | Details of BS transmit power, power control |  | Task 3.3 Transmitter characteristics | Task 4.3 Finalise transmitter characteristics
| ACLR , spectrum emission masks | Details of ACLR and spectrum emission masks |  | Further details of BS Tx power, power control | Revision CRs
| Task 1.5 Receiver Characteristics | Task 2.4 Receiver Characteristics |  | Further details of ACLR and masks + Revision CRs
| Max input level, ACS, blocking characteristics, Reference sensitivity | Details of max input level, ACS, blocking characteristics, Reference sensitivity |  | Task 3.4 Receiver characterisitics | Task 4.4 Receiver characteristics
| Spurious responses, intermodulation characteristics | Details of spurious responses, intermodulation |  | Further details of ACS, blocking, spurious, IM | Revision CRs
|  | Task 2.5 Performance Requirements |  | Task 3.5 Performance Requirements | Task 4.5 Performance requirements
|  | Performance requirement for BS |  | Details of performance requirement | Revision CRs
XY.133 - Requirements for support of radio resource management
Note:
Comment:
Task 1.1 Skeleton/Scope/ToC of Spec
Present skeleton, scope and initial brief description
| Task 1.2 RRC Idle mode | Task 2.1 RRC Idle mode |  | Task 3.1 RRC Idle mode | Task 4.1 Finalise RRC Idle mode
| Cell selection, reselection | Details of measurement for cell selection, reselection |  | Further details of measurements for cell selection/reselection | Revision CRs
| Task 1.3 Timing and signalling | Task 2.2 Timing and signalling |  | Task 3.2 Timing and signalling | Task 4.2 Finalise timing and signalling
| Time synchronization and timing advance | Details of timing sync and TA. |  | Further details of sync and TA | Revision CRs
| Task 1.4 Measurements peformance requirement | Task 2.3 Measurements performance requirement |  | Task 3.3 Measurements performance requirement | Task 4.3 Finalise measurement performance requirement
| Any measurements pref requirement in RAN and CIoT | Details of measurements perf requirement (CIoT) |  | Further details of measurements perf requirement (CIoT)
|  | Details of measurements perf requirement (RAN) |  | Details of measurements perf requirement (RAN)