## Slide 1: WF on the scope and timeline of shortened TTI and processing time for LTE
Huawei, HiSilicon, Vodafone, China Unicom, LG Uplus, SK telecom, KT, Telecom Italia, BT, T-Mobile USA, Deutsche Telekom, Orange, Telefónica, Telstra, KPN, CATT, CATR, OPPO, InterDigital, Samsung
3GPP TSG RAN Meeting #73
New Orleans, USA, September 19 - 22, 2016
RP-161920
AI: 10.11.1

## Slide 2: Background
Current scope of shortened TTI and processing time for LTE
  Processing time reduction for legacy 1ms TTI, for FS1/2/3
  For FS1, sPDCCH/sPDSCH/sPUSCH/sPUCCH design based on
    2-symbol and 7-symbol for sPDCCH/sPDSCH
    2-symbol, 4-symbol , and 7-symbol for sPUSCH/sPUCCH with possible down selection on supported sTTI duration
  For FS2, sPDCCH/sPDSCH/sPUSCH/sPUCCH design based on 7-symbol
  Both CRS based and DMRS based sPDCCH/sPDSCH included
  Both CA and non-CA included
 | 2016.10 | 2016.11 | 2017.2 | 2017.4 | 2017.5 | 2017.8 | 2017.10 | 2017.11 | 2018.2
RAN1 | 2 | 2 | 3 | 3 | 2 | 2 |  |  | 
RAN2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 
RAN4 RF core |  | 0.5 | 1 | 1 | 1 | 1 |  |  | 
RAN4 RD core |  | 0.5 | 1 | 1 | 1 | 1 |  |  | 
RAN4 RF perf |  |  |  |  |  |  | 0.5 | 0.5 | 0.5
RAN4 RD perf |  |  |  |  |  |  | 1.5 | 1.5 | 1.5

## Slide 3: Proposals
Complete the following objectives (including striving to complete the corresponding ASN.1) by RAN#76, with further discussions on which release to include the following objectives in future RAN meetings
  Processing time reduction for legacy 1ms TTI, for FS1/2/3
  For FS1, sPDCCH/sPDSCH/sPUSCH/sPUCCH design based on
    2-symbol for sPDCCH/sPDSCH
    2-symbol for sPUSCH/sPUCCH
  CRS based and DMRS based sPDCCH/sPDSCH for FS1
  DL CA and UL non-CA for FS1
The other objectives will be completed by RAN#77 as currently planned, and will be discussed in WG meetings before RAN#76
 | 2016.10 | 2016.11 | 2017.2 | 2017.4 | 2017.5 | 2017.8 | 2017.10 | 2017.11 | 2018.2
RAN1 | 2 | 2 | 3 4 | 3 4 | 2 4 | 2 |  |  | 
RAN2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 
RAN4 RF core |  | 0.5 | 1 | 1 | 1 | 1 |  |  | 
RAN4 RD core |  | 0.5 | 1 | 1 | 1 | 1 |  |  | 
RAN4 RF perf |  |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
RAN4 RD perf |  |  |  |  |  | 1.5 | 1.5 | 1.5 | 1.5