## Slide 1
Way Forward
on the overall 5G-NR workplan
RP-170666
3GPP RAN #75
Dubrovnik, March 2017
Alcatel-Lucent Shanghai-Bell, Alibaba, Apple, AT&T, British Telecom, Broadcom, Cisco, Convida Wireless, Deutsche Telekom, DOCOMO, Ericsson, Etisalat, Huawei, Intel, KDDI, KT, LG Electronics, LGU+, NEC, Nokia, Ooredoo, Qualcomm, Samsung, Sierra Wireless, SK Telecom, Sony, Sprint, Swisscom, Telecom Italia, TeliaSonera, Telstra, Verizon, vivo, Vodafone, ZTE

## Slide 2: Increase in global momentum for the nascent 5G ecosystem
Increased interest for early deployments of 5G-NR mobile broadband
  Interest for early deployments in 2019 in several regions in the world
We propose the 3GPP workplan to be adjusted to respond to market interest
Introduce an intermediate milestone in Rel-15 RAN working group activities
  Structure 3GPP work so to ensure work swift and solid progress for both Non-Standalone and Standalone NR, including forward compatibility and commonality between the two
  Overall system performance shall not be compromised by an early release
Centered around the 3GPP global standard

## Slide 3: Proposal
By December 2017: complete Stage 3 for Non-Standalone 5G-NR eMBB with Option 3
  Ensure commonality with Standalone, as well as forward compatibility
    L1 and L2-User-Plane completion date is common for both Non-Standalone and Standalone, i.e., complete stage-3 of all L1 and L2-User-Plane by December 2017
  Prioritization of NR band definition (and related band combinations with LTE) will be discussed separately
By March 2018: intermediate freeze of ASN.1 for Non-Standalone 5G NR eMBB accordingly
Maintain current schedule for Standalone 5G-NR in Rel-15
  Stage 3 completion June 2018; ASN.1 freeze September 2018
Ensure alignment of core network aspects
  Ask TSGs SA and CT to ensure completion of stage-3 for the so-called “Option 3” family by December 2017 in case modifications to the current specifications are needed
  Overall 5G Core Network already agreed to be completed by June 2018
Adjust 3GPP schedule to enable 3GPP-compliant 2019 5G-NR launches

## Slide 4: Proposal (cont.)
2016 | 2017 |  |  |  | 2018 |  |  | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
NSA = Non StandAlone = EPC core (“Option 3”) & LTE anchor
SA = StandAlone
5G study
5G NR Work Item
5G NR NSA Completion
Stage 3 completion for Non-Standalone 5G-NR eMBB
(+ASN.1 freeze in the following quarter)
RAN #74
RAN #75
RAN #78
RAN #80 (Rel-15 completion)
Further evolution
5G NR SA Completion
Stage 3 completion for Standalone 5G-NR
(+ASN.1 freeze in the following quarter)