## Slide 1
WF on Work plan of
Self Evaluation SI
Huawei, Ericsson, Telecom Italia
RP-172101
3GPP TSG RAN#77, Sapporo, Japan, September 11 – 14, 2017
Agenda Item: 9.3.2

## Slide 2: Background
It is agreed in RP-172098 that 3GPP should after RAN#81 submit to ITU-R
  Preliminary self evaluation results
  Complete templates (including description template and compliance template)
3GPP needs to provide self evaluation against eMBB, mMTC and URLLC test environments and KPIs at that time.
Considering the workload of preparing submission templates and self evaluation report, It would be good to start the activity from Sep 2017.
  No online time in RAN WG needed at least in 2017Q4
  For 2017Q4, focusing on calibration and preparing of preliminary information for description template.

## Slide 3: Proposal
The following work plan is proposed according to the agreed IMT-2020 submission timeplan
  Step 1: From Sep 2017 to Dec 2017, discussions in RAN ITU-R Ad-Hoc
    Calibration for self evaluation
    Prepare and finalize initial description template information that is to be submitted to ITU-R WP 5D#29.
  Step 2: From early 2018 to Sep 2018, targeting “update & self eval” submission in Sep 2018
    Performance evaluation against eMBB, mMTC and URLLC requirements and test environments for NR and LTE features.
    Update description template and prepare compliance template according to self evaluation results.
    Provide description template, compliance template, and self evaluation results based on Rel-15 in Sep 2018.
  Step 3: From Sep 2018 to June 2019, targeting “Final” submission in June 2019
    Performance evaluation update by taking into account Rel-16 updates in addition to Rel-15
    Update description template and compliance template to take into account Rel-16 updates in addition to Rel-15
    Provide description template, compliance template, and self evaluation results based on Rel-15 and Rel-16 in June 2019.

## Slide 4: Proposal
The following email discussions are proposed for Step 1 after RAN#77
  Plan an email discussion in RAN ITU-R Ad-Hoc on calibration for self evaluation – Lead by Huawei (Rapporteur)
    Including calibration detailed plan, calibration metrics, baseline parameter for calibration, test environments and evaluation configurations for calibration as defined in Report ITU-R M.[IMT-2020. EVAL], etc.
  Plan an email discussion in RAN ITU-R Ad-Hoc on preparing initial description template – Lead by Huawei, Ericsson (Co-Rapporteurs)
  ITU-R Ad-Hoc contact person will kick off the scope and timing of the E-mail discussion in the ITU-R Ad-Hoc mailing list

## Slide 5: For Reference: Submission Timeplan (From RP-172098)

## Slide 6: Submission timeplan
WP 5D Meeting | Deadline for Contributions to WP 5D
#29 | 24 January 2018 before 16:00 hours UTC
#31 | 2 October 2018 before 16:00 hours UTC
#32 | 2 July 2019 before 16:00 hours UTC

## Slide 7: Submission timeplan
Submission Milestone Name | 3GPP Meeting | ITU-R Meeting | General Submission Content | Submission Templates (Release Basis) | Self- Evaluation (Release Basis)
Workshop | RAN # 77 Sept 2017 | WP 5D #28 Oct 2018 | Overview | - | -
Initial Templates Only | RAN # 78 Dec 2017 | WP 5D # 29 Feb 2018 | Description Templates | Description Templates 5.2.3 (R15) | -
Update & Self-Eval | RAN # 81 Sept 2018 | WP 5D # 31 Oct 2018 | Description Templates Compliance Templates Self-Evaluation | Description Templates 5.2.3 (R15) Compliance Templates 5.2.4 (R15) | Self-Evaluation (R15)
Final | RAN # 84 June 2019 | WP 5D # 32 July 2019 | Description Templates Compliance Templates Self-Evaluation | Description Templates 5.2.3 (R15+R16) Compliance Templates 5.2.4 (R15+R16) | Self-Evaluation (R15+R16)