## Slide 1
Status Report of RAN WG2 to TSG-RAN #83
3GPP TSG RAN#83 Shenzhen, China, March 2019
RAN2 Chair: Richard Burbidge (Intel)

## Slide 2: LTE – Release 15
CR to mandate setting FGI 103 and 104 was agreed as per RAN#82 decisions (R2-1902453)

## Slide 3: NR – Release 15 EN-DC and SA corrections
NR SA and NSA specifications are stabilising
  Reduced time spent discussing corrections – approximately 3 days in the main session and 1 days in parallel sessions at RAN2#105
  Number of CRs and the size/impact of the CRs is coming down
  Threshold for accepting CRs is going up - essential corrections only
  No CRs with non backwards compatible (NBC) changes to ASN.1 were agreed
Focus on high quality coversheets including an impact analysis with the following information:
  The impacted 5G architecture options (e.g. EN-DC, SA)
  The impacted functionality
  The (system level) consequences if only the UE or only the network is implemented according to the CR
  The (system level) consequences if the CR is not agreed at all
  Aim to provide information to enable RAN2 to make the correct decision on the CR and to enable operators/vendors to judge criticality of the CR

## Slide 4: NR - Release 15 Feature lists
RAN2 agreed to capture the RAN1/2/4 feature lists within a 3GPP Internal TR (38.8xx series) at the end of Rel-15
  Intension is to not loose the information which has been critical is creating the UE capability signalling structure
  To be captured in at end of Rel-15 when late drop is completed (including ASN.1 freeze) to avoid need for maintenance

## Slide 5: NR – Release 15 late drop
NR late drop is functionally complete within RAN2
Following CRs to introduce the NR later drop were endorsed by RAN2:
  38.331 CR (R2-1902800)
  36.331 CR (R2-1902675)
  38.306 CR (R2-1902679)
  36.306 CR (R2-1901556)
These CRs are not provided to RAN#83 for approval to avoid destabilising existing frozen ASN.1 in 36.331 and 38.331.
Following the ASN.1 review during Q2 2019, the CRs will be updated and provided to RAN#84 in June 2019 for approval and ASN.1 freeze.
Same process as in June 2018 when NR standalone was completed
Functional completion and scheduled ASN.1 freeze are as per the schedule endorsed by RAN#82 in RP-182790.

## Slide 6: NR – Release 16 (1)
I-IoT Study Item (RAN2 led)
  38.825 v 1.0.0 is provided to RAN for a 1 step approval (RP-190189)
  The conclusions of the TR include several recommendations for the scope of an I-IoT WI.
  Study item is complete from RAN2 perspective
UE capability signalling Study Item (RAN2 led)
  37.873v1.0.0 is provided to RAN for a 1 step approval (RP-190296)
  Recommendation that UE capability Identity mechanism and RRC level segmentation is pursued within a follow on WI.
  Study item is complete from RAN2 perspective

## Slide 7: NR – Release 16 (2)
V2X Study Item (RAN1 led)
  Study Item complete from RAN2 perspective
Positioning Study Item (RAN1 led)
  Study Item complete from RAN2 perspective
Non Public Networks (NPN)
  Relating to SA2 SI FS_Vertical_LAN
  RAN2 conducted initial analysis to understand the RAN2 spec impacts of this work. LS to RAN provided in RP-190052

## Slide 8: RAN2 TUs from RAN#82 (RP-182904)
NR TUs
LTE TUs and overall NR+LTE situation
Notes: Present

## Slide 9: RAN2 time planning at RAN#83
TU allocation for Q1 2020
  RAN2#82 agreed that the Rel-16 completion in RAN2 is March 2020
  Next slide shows a proposed TU update to reflect revised completion date
  In general, WIs/SIs already plan are allocated same TUs in Q1 2020 as in last meeting of 2019
  In few cases, adjustments to 2019 TUs are also made
TU allocation for work not already covered by current time budget:
  RIM-CLI – WI with RAN2 objectives agreed at RAN#82 but no TUs agreed
  NPN /CAG- Relating to SA2 SI FS_Vertical_LAN
  IDC – WI and TUs discussed at RAN#82 but finally postponed to RAN#83
  LTE based 5G terrestrial broadcast – RAN1 SI completed and WI proposed
    (TUs allocated for the above WIs are not shown in the following slide)
Details to be discussed during an offline session this week

## Slide 10: RAN2 time planning at RAN#83 Proposed NR TUs for Q1 2020
Notes: Present

## Slide 11: RAN2 time planning at RAN#83 Proposed LTE TUs for Q1 2020
Notes: Present

## Slide 12: Summary and concluding remarks
Another extremely busy quarter with focus and priority on NR Rel-15 corrections and late drop.
NR SA and NSA specifications are stabilising
  Number and size of CRs coming down
  Threshold for accepting CRs going up
NR late drop is functionally complete within RAN2, ASN.1 review planned and on schedule for ASN.1 freeze in June 2019
Following TU adjustments related the shift in Rel-16 completion to March 2020, RAN2 is lightly over time budget
  But several items requesting RAN2 time to be discussed this week (e.g. RIM-CLI, NPN, IDC, LTE broadcast)
  No space for new items

## Slide 13: Special Thanks
Hu Nan (RAN2 VC)
Johan Johansson (RAN2 VC)
Kyeongin Jeong (V2X session chair)
Brian Martin (NB-IoT session chair)
Emre Yavuz (MTC session chair)
Nathan Tenny (Positioning session chair)
Diana Pani (LTE legacy, NTN, NR power saving, NR DC/CA session chair)
Tero Henttonen (LTE, NR mobility session chair)
Juha Korhonen (MCC support)
Meeting hosts: European Friends