## Slide 1: Release-17 schedule Source: TSG RAN and SA Chairmen
RP-190718
3GPP TSG RAN #83
Shenzhen, China, 18th – 21st March, 2019

## Slide 2
Glimpse at history
Chart: Release length
| Rel-4 | Rel-5 | Rel-6 | Rel-7 | Rel-8 | Rel-9 | Rel-10 | Rel-11 | Rel-12 | Rel-13 | Rel-14 | Rel-15 early drop | Rel-15 base | Rel-15 late drop | Rel-16
 | 18 | 15 | 36 | 30 | 12 | 12 | 15 | 21 | 24 | 12 | 15 | 6 | 6 | 9 | 12

## Slide 3
Release 17 schedule
 | TSG SA – CT* | TSG RAN | Key points
Stage 1 freeze | September/2019 for 80% December/2019 completion | N.A. | Stage-1 freeze already decided at TSG#82
Package approval | N.A. | December/2019 | 
Stage 2 freeze | Stage-3 freeze - 3Q | N.A. | 9 month overlap of SA2/RAN2/RAN3 phase allows for coordination
RAN1 freeze | N.A. | Stage-3 freeze - 1Q | Early freeze of RAN1 to help RAN2 work finalize on time
Stage 3 freeze | June or September/2021 | June or September/2021 | June/2021 corresponds to a 15-month Release September/2021 corresponds to an 18-month Release
ASN.1 freeze | N.A. | Stage-3 freeze + 1Q | 
RAN4 performance completion | N.A. | Stage-3 freeze + 2Q | Allow additional 3 months for RAN4 performance work completion

## Slide 4: Proposal
Majority of company proposals fluctuate between 15 and 18 month long Release-17
The SA-RAN joint session to identify if there is a decisive reason one way or another (15 vs 18)
If such a decisive reasons does not exist, it is proposed to conduct a show of hands between 15 and 18, and adopt majority view