## Slide 1
Steven Chen
RAN4 Chairman (FUTUREWEI)
Status Report RAN WG4 to TSG-RAN #87-E
3GPP TSG RAN #87-e RP-200009
E-meeting, 16 – 19, March 2020

## Slide 2: Executive Summary (1/2)
Observations on the RAN4 e-meeting
  Email discussions were organized in 96 email threads, each with a moderator. Moderators generated summaries that allows traceability of discussions and decisions. No telephone conferences
  About 5000 emails in total
  Some delegates didn’t strictly follow the meeting guidelines, perhaps because this was the first such e-meeting
  Overall, the progress was reasonably good. By the nature of email discussion, progress of contentious topics was hard to achieve
    Rel-16 NR
  Good progress achieved for Rel-16 NR spectrum WIs
  Mixed progress for Rel-16 NR non-spectrum WIs.
  Typically the last two quarters before stage 3 freeze are critical for completion. Now with all meetings in Q1 and Q2 being conducted as e-meetings, it will be very challenging to achieve full completion of Core part in Q2

## Slide 3: Executive Summary (2/2)
Rel-15 NR
  A substantial amount of effort was put into Rel-15 NR maintenance and good progress was made
  This effort is expected to continue into Q2
LTE maintenance for Rel-15
  Because of focused scope, only two critical CRs were treated and agreed
Rel-16 LTE
  Good progress

## Slide 4: Statistics
Chart: 
| #90 | #90bis | #91 | #92 | #92bis | #93 | #94-e
Delegates | 372 | 324 | 387 | 266 | 298 | 382 | 226
Chart: 
| #90 | #90bis | #91 | #92 | #92bis | #93 | #94-e
Contributions | 2584 | 2774 | 2337 | 2576 | 2230 | 2886 | 2883
Meeting | Date | Location | Host | Delegates registered/attendees | Documents requested/uploaded
RAN4 #94-e | Feb. 24 – Mar. 6, 2020 | Electronic meeting |  | 226/226 | 2883/2840

## Slide 5: NR

## Slide 6: Completion of ongoing WI/SI
SI/WI to be completed
Title | SR
Addition of channel bandwidths in Band n77 and n78 | RP-200274
Introduction of Band n53 | RP-200104
Addition of wider channel bandwidths in NR band n28 | RP-200127
adding wider channel bandwidth support to band n1 | RP-200301
Introduction of NR band n26 | RP-200329
Adding wider channel bandwidth to NR band n38 | RP-200302

## Slide 7: NR – RAN4 led items

## Slide 8: FR1 UE RF
Clarification CR agreed for almost contiguous allocation for CP-OFDM.
WFs/CRs agreed for
  Intra-band contiguous DL CA for FR1
  Intra-band contiguous UL CA for FR1 power class 3
  Intra-band non-contiguous UL CA for FR1 power class 3
WF for RF and RRM requirements agreed for switching period between case 1 and case 2. An LS was sent to RAN1 and RAN2
Initial discussion on time masks for ULSUP-TDM
SR completion level: 70% for core part, 30% for perf. part.; Extend core part to June 2020.

## Slide 9: FR2 UE RF
MPE: a WF on MPE agreed in which further agreements on P-MPR reporting were made. It was also agreed that “fast emergency signal” is not needed. In addition, two LSs were sent to RAN2.
Some agreements made for:
  Intra-band contiguous DL CA for aggregated BW larger than 1400 MHz. The objective of defining UE RF requirements for intra-band contiguous DL CA for aggregated channel bandwidth wider than 1200 MHz will be removed from the WI.
  Contiguous intra-band UL CA
A WF on Spherical coverage enhancements was agreed.
A WF on Multiband relaxation framework enhancement was agreed
RRM requirements for FR2 inter-band DL CA: Initial discussion took place with limited progress.
SR completion level: 35% for core part, 35% for perf. Part; Extend Core/Perf part to June 2020.

## Slide 10: RRM Requirements Enhancements
RRM
  Good progress for multiple objectives including SRS carrier switching, multiple SCell activation, CGI reading, BWP switching on multiple CCs, inter-frequency measurement without MG, mandatory MG patterns, and FR2 Inter-band CA with respective WFs approved.
  FR2 Non-simultaneous UL carrier operation: No progress. Discussion postponed due to dependency on RF part conclusions.
  UL spatial relation info switching: Initial discussion in Q1’20 with limited progress.
WI status report
  Completion level: 70% for core part, 0% for perf. part.
  Extend Core part to June 2020, and Perf. part to Dec 2020.

## Slide 11: CSI-RS based L3 Measurement
RRM
  WFs on CSI-RS based RRM measurements requirements were approved in R4-2002257 and R4-2002258.
  Very limited progress reached on “intra/inter-frequency measurement definition” topic which has a big impact on the overall WI progress.
WI status report
  Completion level: 40% for core part, 0% for perf. part.
  Extend Core part to June 2020.

## Slide 12: High Speed Train Scenarios
RRM
  Good progress achieved on RRM Core requirements
  WF on RRM requirements for NR HST was approved in R4-2002253.
Demodulation
  Good progress on BS Demodulation, CRs agreed to introduce PUSCH, PRACH and UL timing adjust test cases
  Good progress on UE Demodulation with detailed test parameters agreed
    The maximum Doppler shift values need to be addressed in future RAN4 meetings
    The applicable rules need to be further studied in future RAN4 meetings, FFS for release independent
  FFS whether to introduce test cases for transmission scheme 1 and 2, transmission scheme 3 not supported in Rel-16 and no requirements in Rel-16
SR completion level: 65% for core part, 55% for perf. Part; Extend core part to June 20, perf. part plan to complete in Sep 20

## Slide 13: Performance requirement enhancement
Demodulation
  Overall good progress achieved on BS and UE demodulation and CSI, CR agreed to introduce UE TDD LTE-NR co-existence and BS PUSCH FR2 2T2R MCS 12 Test cases
  General aspect: Release independent approach WF agreed for UE demodulation and CSI requirements (R4-2002390)
  PMI test cases: WF agreed with some detailed parameters need to be addressed in future RAN4 meetings
  UE CA normal demodulation: WF agreed with applicability rules need to be further addressed in future RAN4 meetings
  UE CA CQI requirements: work planned to start in Q2’20 in accordance to WID
  UE CA power imbalance: whether start to discuss power imbalance FR1 intra-band EN-DC test(s) in Q2’ 20 pending on RAN#87-e decision on the revise of WID objectives
SR completion level: 50% for perf. Part, target completion date Sep.20

## Slide 14: FR2 DL 256QAM
CR endorsed for introducing FR2 DL 256QAM into BS specification (38.104, 38.141-1)
BS and UE CRs will be agreed as a package once all core requirements completion
FFS how to define the UE maximum input level for 256QAM
SR completion level: 90% for core part and 20% for perf. part; Extend core part to June 20, and perf. part to Dec 20

## Slide 15: NR – Other WG led items

## Slide 16: Rel-16 NR – eMIMO
RF
  WF for uplink full power transmission was approved
  There were divergent views on MPR reduction for pi/2 BPSK DMRS, which needs to be further discussed
RRM
  Good progress achieved
  WF on NR eMIMO RRM requirements approved in R4-2002242
Demodulation
  Demodulation and CSI requirements scope agreed in WF R4-2002419
  PDSCH demodulation requirement for multi-TRP/panel transmission agreed in R4-2002420
  PMI requirement for Type II advanced codebook agreed in R4-2002421
    SR completion level: RAN4-75% core part, 15% for perf. part, Extend core part to June 20 and per. part to Dec. 20

## Slide 17: Rel-16 NR – CLI and RIM
RRM
  Reply LS to RAN2 to inform RAN4 agreement for UE behavior in case of FDMed DL signal/channel and CLI measurement was approved.
  Perf. part: two CRs for measurement accuracy and minimum SRS_RP level. The WF on CLI performance requirement was approved.
WI status report
  Completion level: RAN4 - 100% for core part, 30% for perf. part.
  No extension requested

## Slide 18: Rel-16 NR – NR-U
RF
  WF agreed on wideband operation, Intra-band contiguous bandwidth classes, UE RF requirements mainly for PC5 (20 dBm maximum output power)
  WF agreed on NR-U FRCs for BS RX requirements
  TBD how to capture the TPs for NR-U band combinations.
RRM
  Good progress achieved but WI still has a big amount of open issues
  RRM agreements captured in R4-2002336, R4-2002335, R4-2002278
Total completion level: 90% for core part, 30% for perf. part. Extension: core part extension to June 2020, perf. part extension to Dec 2020

## Slide 19: Rel-16 NR – eURLLC
Demodulation
  URLLC ultra-low BLER test: Detailed test parameters and test methodology agreed in WF R4-2002422
  UE and BS demodulation requirements agreed in WF R4-2002428/R4-2002429
  FFS whether to introduce FR2 BS and UE requirements including high reliability and low latency related
  FFS Performance requirements for DFT-s-OFSM
  FFS whether introduce CQI test with ultra-low BLER
    SR completion level: 100% for core part, 40% for perf. part, target completion date Sep 20

## Slide 20: Rel-16 NR – Power Saving
    RF
  Agreement reached on switching time for MIMO layer adaptation
    RRM
  WF on RRM measurement relaxation for Power Saving was agreed (R4-2002338)
  Issue on 4Rx demodulation requirement impact due to MIMO layer postponed to the WI Perf. part
    SR completion level: Total 85% for core part, 0% for perf. part. Extend core part to June 2020, and perf. part to Dec 2020.

## Slide 21: Rel-16 NR – Positioning
    RRM
  Good progress on multiple aspects but WI still has a big amount of open issues
  WFs on NR Positioning UE requirements approved (R4-2002328)
  WFs on NR Positioning gNB requirements approved (R4-2002328)
  WF on NR Positioning impact on RRM requirements approved (R4-2002276)
  LS to RAN2/3 on gNB measurements report mapping for NR Positioning was approved (R4-2002280)
WI status report
  Completion level: Total - 90% for core part, 0% for perf. part.
  Extend Core part to June 2020, and Perf. part to Dec 2020.

## Slide 22: Rel-16 NR – 5G V2X and NR sidelink
    RF
  Good progress. 6 approved WFs and 7 endorsed CRs in UE TX/RX requirements for single carrier, additional On/OFF Switching Time Mask for TDM operation between LTE SL and NR SL at n47, UL MIMO for NR-V2X, Rx requirements for NR V2X concurrent operation
  5 TPs for TR38.886
    RRM
  Good progress achieved
  Way forward on NR V2X RRM requirements was approved (R4-2002230)
  4 CRs on RRM requirements agreed
    SR completion level: Total 90% for core part, 0% for perf. part. Extend Core part to June 2020, and Perf. part to Dec 2020.

## Slide 23: Rel-16 NR – NR Mobility Enhancement
RRM
  Good progress achieved and agreements on NR Mobility Enhancements RRM requirements captured in WF R4-2002224
  2 CRs on RRM requirements agreed
SR completion level: Total - 90% for core part, 0% for perf. part. Extend Core part to June 2020.

## Slide 24: Rel-16 NR – MR-DC
RRM
  Good progress achieved.
  Three WFs on RRM Requirements for MR-DC, NR Inter-RAT EMR requirements and UE RRM requirements for dormancy Scell were approved
  2 CRs on RRM requirements agreed
    SR completion level: Total - 90% for core part, 0% for perf. part. Extend Core part to June 2020, and Perf. part to Dec 2020.

## Slide 25: Rel-16 NR – IAB
    General
  WF on TS drafting reference rules and WF on IAB definition agreed; WF on CA and multi-carrier agreed
    RF
  Good progress achieved for Tx and Rx RF core requirements with sets of WFs agreed
  There are remaining open issues on RF requirements including IAB-MT ACLR/ACS, dynamic power range, Beam correspondence etc.
    RRM
  Limited set of agreements achieved on the remaining open issues
  Initial Draft CRs/TPs on RRM requirements agreed
    SR completion level: RAN4 - 65% for core part, 0% for perf. part, Extend core part to June 20, and perf. part to Dec 20

## Slide 26: Rel-16 NR – OTA BS Testing
    Several TPs agreed for the new TR 37.941
    TR 37.941 V1.0.0 with implemented all agreed TPs agreed in R4-2002430
    SR completion level: 70% for perf. part

## Slide 27: Rel-16 NR – 2-step RACH for NR
    RRM
  RAN4 RRM requirements objectives not included in the WID
  Potential 2-step RACH RRM impacts identified
  Actual work not triggered and rapporteurs recommended to revise WID to include RRM objectives if any formal work needs to be done in RAN4
Demodulation
  Potential impact on performance requirements agreed
SR completion level: 99% for core part, 10% for perf. part; Extend core part to June 20 and performance part to Sep. 20

## Slide 28: Rel-16 NR – SRVCC from 5G to 3G
WF on SRVCC RRM test cases agreed
Initial CR on RRM performance requirements agreed
SR Completion level: 50% for perf. part.

## Slide 29: Rel-16 NR – SON/MDT
    SON/MDT
  WF on MDT RRM requirements
  2 CRs on RRM requirements agreed
  RAN4 related WID objectives completed

## Slide 30: Rel-16 NR –Spectrum WI(1/2)
29 dBm UE Power Class for LTE band 41 and NR Band n41
  Several WFs were agreed such as UE behavior when P-Max is not present, A-MPR for PC1.5 intra-band EN-DC, etc.
  Further discussion on CR for allocation aware MPR and PC1.5 A-MPR .
High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)
  First meeting. Agreements made on LTE duty cycle configuration, NR duty cycle, etc.
Band n259
  Agreement made on BS RF and UE RRM requirements
  FFS UE Multiband Relaxation
  Addition of asymmetric channel bandwidth for NR band n66
  RAN4 work done. LS sent to RAN2 on UE capability signaling
Addition of channel BW in NR band n1 (NR_n1_BW & NR_n1_BW2)
  Adding 25MHz and 30MHz channel bandwidth is done.

## Slide 31: Rel-16 NR –Spectrum WI(2/2)
LTE/NR spectrum sharing in band 48/n48 frequency range
  Initial discussion on channel raster, UL shift, and sync raster pattern. Some options provided
Adding 40 MHz channel bandwidth (15, 30 and 60kHz SCS) in NR band n3
  No need for A-MPR. UE refsense TBD
  Adding 50 MHz channel bandwidth (15, 30 and 60kHz SCS) in NR band n65
  REFSENS values and RB allocations agreed.
  A-MPR simulations assumptions agreed

## Slide 32: Rel-16 Basket WI Status
Rel-16 NR Basket WI Status Report
Above revised WIDs have been endorsed by RAN4
WI Title | Status Report | Revised WID
NR intra-band CA | RP-200097 | RP-200101
NR Inter-band CA for 3 bands DL with 1 band UL | RP-200239 | RP-200238
NR Inter-band CA for 4 bands DL with 1 band UL | RP-200099 | RP-200103
EN-DC for 2 bands DL with 2 bands UL (1 LTE band + 1 NR band) | RP-200222 | RP-200221
EN-DC for 3 bands DL with 2 bands UL (2 LTE bands + 1 NR band) | RP-200272 | RP-200271
EN-DC for 4 bands DL with 2 bands UL (3 LTE bands + 1 NR band) | RP-200098 | RP-200102
EN-DC for 5 bands DL with 2 bands UL (4 LTE bands + 1 NR band) | RP-200133 | RP-200134
EN-DC of x bands (xDL/1UL x=1, 2,3,4) LTE and 2 NR bands (2DL/1UL); | RP-200081 | R4-200080
EN-DC for 3 bands DL with 3 bands UL | RP-200111 | RP-200110
NR Inter-band CA/DC for 2 bands DL with up to 2 bands UL | RP-200169 | RP-200168
NR Inter-band CA/DC for 3 bands DL with 2 bands UL | RP-200172 | RP-200171
Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | RP-200272 | RP-200273
Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | RP-200229 | RP-200228

## Slide 33: Rel-16 NR – SI
7-24 GHz
  Several TPs for frequency bands, BS RF and BS classes were approved.
  TR 38.820 v2.0.0 is available.
  95% completed.
MIMO OTA
  Good progress on FR2 test methodology with some remaining open issues
  TR38.827 v1.2.0 NR MIMO OTA agreed R4-2002482
  Further extension (1 quarter) is needed to complete remaining issues on the FR2 test methods
FR2 Test enhancement
  No discussion

## Slide 34: LTE

## Slide 35: Rel-16 LTE
eMTC5
  RF: WF on remaining issues were agreed in R4-2002741. Several TPs on coexistence study and specific aspects of TDD were approved.
  RRM: Good progress on RRM Core requirements finalization and initial discussion on performance requirements. WF R4-2002268 agreed.
  Demodulation: WF with initial test scope agreed in R4-2002426
  SR completion level: 95% for core part, 15% for perf. part. Extend core part to June 20, and perf. part to Dec 20
NB-IOTenh3
  RF: TP on summary of co-existence study and TDD configuration were approved. CRs on conformance testing were agreed for TS 38.141
  Conformance testing: WF for test cases for NR in-band operation was approved
  RRM: Good progress on RRM requirements finalization. WF R4-2002337 agreed.
  Demodulation: WF with initial test scope agreed in R4-2002425
  SR completion level: 95% for core part, 15% for perf. part. Extend core part to June 20, and perf. part to Dec 20

## Slide 36: Rel-16 LTE
LTE MIMO
  CR agreed for TS 36.101-1 Introduction of new SRS requirements for LTE eMIMO
LTE even further mobility enhancement
  RRM: WF on RRM requirements agreed in R4-2002272
  SR completion level: 85% for core part, 0% for perf. Part; Extend core part to June 20
LTE high speed
  RRM: All requirements finalized, CRs agreed
  Demodulation: requirements finalized, CRs agreed
  SR completion level: 100% for core part, 100% for perf. Part, the WI finalized
LTE-based 5G terrestrial broadcast
  WF in R4-2002423 on demodulation requirements was agreed.
  SR completion level: 50% for perf. Part
Support for NavIC Navigation Satellite System for LTE
  CR of TS 36.171 for introducing NavIC in LTE – performance part agreed

## Slide 37: Rel-16 LTE Spectrum related WI
Rel-16 LTE Basket WI Status Report
  Above revised LTE CA WIDs have been endorsed by RAN4
WI Title | Status Report | Revised WID
LTE intra-band CA | RP-200096 | RP-200100
LTE inter-band CA for 2 bands DL with 1 band UL | RP-200230 | RP-200231
LTE inter-band CA for 3 bands DL with 1 band UL | RP-200266 | RP-200267
LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL | RP-200158 | RP-200157
LTE inter-band CA for 2 bands DL with 2 band UL | RP-200268 | RP-200269
LTE inter-band Carrier Aggregation for x bands DL with 2 bands UL | RP-200079 | RP-200078
Additional LTE bands for UE category M1 and/or NB1 | RP-200155 | RP-200153
Additional LTE bands for UE category M2 and/or NB2 | RP-200156 | RP-200154

## Slide 38: Views on new WI/SI proposals
  Q2 focus is to complete R16 core part
  The current guidance is only critical spectrum related R16/17 proposals will be discussed/approved.

## Slide 39: Thank You!
  Vice chairs Haijie Qiu and Andrey Chervyakov for helping structure the e-meeting and chairing sessions
  Kai-Erik Sunell and Young Ik Jo for efficient secretary support
  Email moderators for leading the email discussions and providing summaries
  Delegates for contributions and discussion