## Slide 1: 3GPP Release timelines
Source: RAN Chairman,
RAN1 Chairman,
RAN2 Chairman,
RAN3 Chairman,
RAN4 Chairman
RAN5 Chairman
RP-200493

## Slide 2: Introduction
These slides present a proposal to adjust the 3GPP RAN milestones in light of the recent cancellation of WG and TSG face-to-face meetings
Note that the proposal has been coordinated across all TSGs

## Slide 3: Overall timeline
Q2
Q3
Q4
2021
Q2
Q3
Q4
Q1
2022
Q1
2020
Q1
2019
Q4
Rel-16 RAN1 freeze
Rel-16 stage-3 freeze*
Rel-16 ASN.1 freeze
Rel-16 RAN4
performance completion*
Rel-17 RAN1,2,3 package approval
Rel-17 RAN4 package approval for spectrum related items*
Rel-17 RAN1 freeze*
Rel-17 stage-3 freeze*
Rel-17 ASN.1 freeze*
Rel-17 RAN4
performance completion*
Release 17 timeline
Release 16 completion
Rel-17 RAN4 RF/RRM/Demod package approval*
* These milestones show a 3-month shift compared to previously approved timelines

## Slide 4: Key points – Release 16
Release-16 stage-3 freeze moved to June/2020
Release-16 ASN.1 freeze remains in June/2020
UE capabilities work is to be addressed with high priority in Q2 in order to ensure necessary signaling can be in place for the ASN.1 freeze in June
  RAN2 needs the feature list from both RAN1 and RAN4 in order to design the signaling
Release-16 RAN4 performance completion moved to Dec/2020
  Proper start time for the Performance work in RAN4 can be determined case-by-case for each Work Item. If Performance work can be started for a given Item in Q2 that can be determined by the RAN4 leadership. Normal RAN4 TU planning will commence from June onwards along with other WGs

## Slide 5: Key points – Release 17
Start of Release-17 work
  RAN1 will start in May WG E-meeting addressing Study Items first.
  RAN 2-3-4 will start in August meeting. Exact scope TBD.
Release-17 package approved for RAN1-2-3 at RAN#86 is unchanged
  Overall number of TUs allocated for the different items assumed to be unchanged, but the exact distribution across meetings and quarters will be re-evaluated at RAN#88
Release-17 RAN4 package approval will be done in 2 phases: in June and September 2020
  RAN4 package approval for spectrum proposals will be done in June/2020
  RAN4 package approval for all other RF, RRM and Demod proposals in September/2020
Release-17 RAN1 freeze moved to June/2021
Release-17 stage-3 freeze moved to September/2021
Release-17 ASN.1 freeze moved to December/2021
Release-17 RAN4 performance completion moved to March/2022
Adding a meeting for RAN1-2-3-4 in January/2021 is the preferred option to ensure the new Rel-17 can be kept. Formal decision on this will be made at RAN#88 in September. There is no additional WG meeting planned for July/2020.

## Slide 6: Proposal
It is proposed to endorse the milestones and Key Points shown in these slides

## Slide 7: Thank You !