3GPP TSG RAN Meeting #89-e									RP-201521

Electronic Meeting, September 14 - 18, 2020

Status Report to TSG

Agenda item:			9.7.9

| WI / SI Name | Study on NR QoE management and optimizations for diverse services |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: Yes | Core part: No | Performance part: No |  | Testing part: No |
| Acronym | FS_NR_QoE |  |  |  |  |
| Unique ID | 860061 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-193256 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: 03/2021 (changed from 12/2020) | Core part: mm/yyyy | Performance part: mm/yyyy | Testing part: mm/yyyy |  |
| Overall Completion level | Study Item: 10 % | Core part: xx% | Performance Part: xx% | Testing part: xx% |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | RAN3 |
| --- | --- | --- |
| Rapporteur | Name | Xiang Pan |
|  | Company | China Unicom |
|  | Email | panx14@chinaunicom.cn |

1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | Yes |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table:

2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

2.1	RAN1

2.1.1	Agreements

2.1.2	Remaining Open issues

2.2	RAN2

2.2.1	Agreements

RAN2#111-e (Aug.2020)

4 contributions ([1]~[4]) were submitted in this meeting. Since no TU was allocated in RAN2#111-e for this SID, no agreement was reached and related discussions should be continued in the next meeting.

2.2.2	Remaining Open issues

2.3	RAN3

2.3.1	Agreements

RAN3#109-e (Aug.2020)

21 contributions ([5]~[25]) were submitted in this meeting. The time plan and potential solutions have been discussed and the following agreements were made:

Workplan and TR Skeleton

-	TR Skeleton[26] was agreed.

Service types

-	The supported service types of NR QoE management include Streaming services, MTSI services, VR, MBMS and URLLC related services in addition to VR.[27] The details of URLLC related services in addition to VR are FFS.

-	In addition to the QoE metrics, the radio related measurements and information to assist the NR QoE management functionality are considered. Whether the radio related measurements and information are collected from the RAN node and/or from the UE is FFS.

-	An LS[28] to SA4 to info RAN3’s agreement on supported services of NR QOE and inform SA4 to feedback the progress on QoE metrics of other URLLC related services when available. And also cc to SA5, RAN2 and SA2.

Solutions

-	Both the management-based and signalling-based solutions for NR QoE management are supported.

-	The UE Application layer measurement capability is indicated in the UE Radio Capability Info Indication message.

-	RAN3 agree to study the following solutions, the details are FFS.

- The mechanisms for RAN releasing QoE measurements.

- The mechanisms for handling QoE report delivery at RAN overload.

- QoE measurement configuration and reporting in SA, NSA and MR-DC.

- The mechanisms to maintaine NR QoE measurement configuration in the RRC INACTIVE state.

- Mobility support for both signaling- and management-based NR QoE management.

- The requirements for QoE report visibility at the RAN.

- Event- and time-based measurement triggering and stopping, as well as measurement triggering by RAN.

-	An LS[29] to RAN2 to inform them that UP solution is precluded and the NR QoE reports are carried over CP from RAN3 point of view.

2.3.2	Remaining Open issues

-	Enhanced mechanism for RAN part delay measurement.

-	The mechanisms for slice-level QoE measurement.

-	The mechanisms for segmentation of QoE reports.

-	Potential interface impacts.

2.4	RAN4

2.4.1	Agreements

2.4.2	Remaining Open issues

2.5	RAN5

2.5.1	Agreements

2.5.2	Remaining Open issues

2.5.3	Remaining Open issues with cross-WG dependencies

2.6	RAN6

2.6.1	Agreements

2.6.2	Remaining Open issues

3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

3.1	SA4

3.1.1	Agreements with cross-TSG impacts

3.1.2	Remaining Open issues with cross-TSG impacts

-	Feedback the progress on QoE metrics of URLLC related services in addition to VR when available.

NOTE: This section should also flag any critical dependencies that need TSG attention.

4.	References

NOTE:	This can be e.g. a list of all related Tdocs in the affected WGs since last TSG, references to LSs, produced TRs/TSs, the work/study item description or status reports of previous TSGs.

TSG RAN WG3

RAN3#109e

- R2-2007081	NR QoE management	Samsung Electronics	discussion

- R2-2007600	NR QoE Measurement Triggering, Configuration, Collection and Reporting	Ericsson	discussion

- R2-2007768	Discussion for NR QoE	Huawei, HiSilicon	discussion

- R2-2007940	Discussion on QoE in NR	ZTE Corporation, Sanechips	discussion

- R3-204643	Time plan for NR QoE Management and Optimizations for Diverse Services	China Unicom	Work Plan

- R3-204644	TR Skeleton for NR QoE Management and Optimizations for Diverse Services	China Unicom	other

- R3-204706	QoE Configuration and reporting	Qualcomm Incorporated	discussion

- R3-204707	QoE handling in handover	Qualcomm Incorporated	discussion

- R3-204708	Interworking with LTE QoE	Qualcomm Incorporated	discussion

- R3-204851	Framework for QoE measurement collection	Nokia, Nokia Shanghai Bell	discussion

- R3-205181	Initial Consideration On Study of NR QoE	ZTE	discussion

- R3-205182	TP for FS_NR_QoE	ZTE	other

- R3-205183	Consideration on slice QoE measurement	ZTE	discussion

- R3-205200	pCR for TR 38.8xx: NR QoE Management Framework	Ericsson	other

- R3-205201	pCR for TR 38.8xx: NR QoE Measurement Triggering, Configuration, Collection and Reporting	Ericsson	other

- R3-205202	pCR for TR 38.8xx: Use Cases for NR QoE Management	Ericsson	other

- R3-205281	NR QoE measurement overview	Huawei	discussion

- R3-205282	Initial discussion on latency measurement	Huawei	discussion

- R3-205283	Potential RAN3 impacts about QoE measurement	Huawei	other

- R3-205359	Discussion on NR QoE solution for various service	CATT	discussion

- R3-205360	Discussion on NR QoE solution architecture and interface impact	CATT	discussion

- R3-205370	Some Considerations on QOE Collection in NR	China Telecommunications	discussion

- R3-205402	Discussion on NR QoE requirements and potential solutions	Samsung	discussion

- R3-205403	Discussion on NR QoE interface impact and solutions	Samsung	discussion

- R3-205439	NR QoE management	CMCC	discussion

- R3-205816	TR Skeleton for NR QoE Management and Optimizations for Diverse Services	China Unicom	other

- R3-205725	TP for TR38.890 on 5G services	ZTE	pCR

- R3-205724	New service type of NR QoE	ZTE	LS out

- R3-205785	LS on Transport of NR QoE Reports in the RAN	Ericsson	LS out