## Slide 1: Discussion on Rel-17 timeline
LG Electronics Inc.

## Slide 2: Backgrounds
Q2
Q3
Q4
2021
Q2
Q3
Q4
Q1
2022
Q1
2020
Q1
2019
Q4
Rel-17
RAN1 starts
Rel-17
RAN1 freeze
Rel-17
RAN2/3 starts
Rel-17
Stage-3 freeze
Rel-17
ASN-1 freeze
Rel-17 RAN4 performance completion
Schedule
@ RAN#86
Rel-17
RAN1 freeze
Rel-17
Stage-3 freeze
Rel-17
ASN-1 freeze
Rel-17 RAN4 performance completion
Schedule
@ RAN#87
Rel-17
RAN1 starts
Rel-17
RAN2/3 starts
Due to changes on meeting environment from COVID-19 situation, original Rel-17 time schedule made in RAN#86 is shifted by 3 months in RAN#87

## Slide 3: Discussion
Further Delay of Rel-17 time schedule is inevitable because:
  Actual start of Rel-17 works has been delayed due to extension of Rel-16 maintenance works
  Progress of Rel-17 SI/WIs in each WG via e-meetings is not as efficient as f2f meetings
  It is still unclear when 3GPP can start ordinary f2f meetings.
Therefore, shifting Rel-17 time line by at least 3 months (or more) is necessary
  It seems to be already a common assumption that Rel-17 RAN1 SI/WI freezing will be shifted to at least September 2021 or later (with a corresponding timeline shift for the RAN2/3/4 works)
  FFS if whole time schedule updates for Rel-17 should be announced officially in RAN#89

## Slide 4: Discussion
To expedite the progress of Rel-17 works, additional WG meeting in January can be considered
  However, current e-meeting schedules in each WG already tight since each e-meeting requires 3 weeks (1 week for preparation phase + 2 weeks for main discussion) and more (e.g. additional 1 week for a few remaining discussion)
  Moreover, Asian New Year’s holiday season in February should be respected
Therefore, additional meeting (if considered) in January should be compact than ordinary e-meetings. For example, shortened period with selected topics (e.g., only for a few selected SI/WIs)

## Slide 5: Discussion
There are two RAN1-leading Rel-17 SIs which are not yet started, i.e., NR XR study and IOT over NTN.
  Since progress of ongoing Rel-17 RAN1 WIs/Sis is very slow and only one meeting (in October) remains in 2020, it is not desirable to add more Rel-17 works for Rel-17 items in this year
Therefore, NR XR study and IOT over NTN may be started at an appropriate point of time in 2021

## Slide 6: Conclusions
Rel-17 time line should be shifted by at least 3 months (or more) on top of the updated schedule in RAN#87
  FFS if whole time schedule updates for Rel-17 should be announced officially in RAN#89
Additional WG meeting in January can be considered
  with shortened period than ordinary e-meetings with selected topics
Start of the two SIs on NR XR and IOT over NTN is delayed to 2021