## Slide 1: Discussions on R17 Timeline
RP-201786
3GPP TSG RAN WG Meeting #89e
E-MEETING, Sept 14-18th 2020
Document for: Discussion
Agenda Item: 9
China Academy of Telecommunications Technology (CATT)

## Slide 2
In RP#88-e, the following was endorsed in RP-201361 on R17 timeline
  Even though it is understood that further delay to the Release 17 timeline will be necessary, there are no changes to the above timeline at this point
    Timeline changes will be addressed once firm detailed planning will be possible. This planning is not expected to happen before December 2020.
In this RP meeting, it is expected that RAN should at least discuss the TU arrangements for the SIs/WIs in Q4 WG meetings.
  This requires assumption on SI completion time
Furthermore, even though the potential updates of R17 timeline may be discussed in the next RP, it is meaningful to first establish a general understanding of the discussion scope already in this RP meeting.
Background

## Slide 3: Study Item Extension
Based on current progress in the Rel-17 SIs, the completion date of Dec. 2020 is very changeling, if not impossible. Situations include
  Still many aspects to clarify in terms of scenarios, use cases and scope of discussions. Some SIs proposed 45% completion or even lower than 40%.
  LSs btw WGs require more time to conclude.
  Interaction with SA WGs take time.
Planning of Q4 WG TU should base on realistic completion date, e.g., one more quarter delay.
Proposal 1 RP discuss Q4 WG TU based on the assumption that the R17 SIs completion date is extended to at least 2021Q1.

## Slide 4: Scope of R17 Timeline Discussions
In RP#86, some WIDs were not included in last minute due to concerns on work load.
The following has been endorsed in RP-193243
  After the initial Rel-17 package approval in RAN#86, additional Rel-17 SI(s)/WI(s) can be considered in RAN#89 (for RAN1-led items) and RAN#90 (for RAN2/3-led items), taking into account of the progress of the items in the initial Rel-17 package
R17 timeline should take into account both time budget and market requirements, to ensure a real successful release in both standardization and business worlds.
Proposal 2 RP should consider potential additional items in future discussions of R17 timeline.

## Slide 5: Summary
On TU planning for Q4 WG meeting
Proposal 1 RP discuss Q4 WG TU based on the assumption that the R17 SIs completion date is extended to at least 2021Q1.
On future discussions of R17 timeline
Proposal 2 RP should consider potential additional items in future discussions of R17 timeline.