## RAN 90
Rel | leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | RAN4 impact | SI/WI status in RAN4 | 90 Dec.20 | 98 (RF) | 98 (RD) | 91 Mar.21 | 98b (RF) | 98b (RD) | 99 (RF) | 99 (RD) | 92 Jun.21 | 100 (RF) | 100 (RD) | 93 Sep.21 | 100b (RF) | 100b (RD) | 101 (RF) | 101 (RD) | 94 Dec.21 | 102 (RF) | 102 (RD) | 95 Mar.22
RAN1-led items
R15 | R4 | NR | R15 NR Maintenance |  |  |  |  | Yes | Completed |  | 0.5 | 0.5
R16 | R1 | NR | NR_unlic-Core | WI | Core part: NR-based Access to Unlicensed Spectrum | RP-191575 | Qualcomm | Yes | Completed
R16 | R4 | NR | NR_unlic-Perf | WI | Perf part: NR-based Access to Unlicensed Spectrum | RP-191575 | Qualcomm | Yes | Ongoing |  | 0.5 | 1.5 |  | 0.5 | 1.5 | 0.5 | 1.5
R16 | R1 | NR, LTE | 5G_V2X_NRSL-Core | WI | Core part: 5G V2X with NR sidelink | RP-191723 | LG Electronics | Yes | Completed
R16 | R4 | NR | 5G_V2X_NRSL-Perf | WI | Perf part: 5G V2X with NR sidelink | RP-191723 | LG Electronics | Yes | Ongoing |  |  | 1.5 |  |  | 1 |  | 1
R16 | R1 | NR | NR_eMIMO-Core | WI | Core part: Enhancements on MIMO for NR | RP-192271 | Samsung | Yes | Completed
R16 | R4 | NR | NR_eMIMO-Perf | WI | Perf. part: Enhancements on MIMO for NR | RP-192271 | Samsung | Yes | Ongoing |  |  | 1
R16 | R1 | NR | NR_UE_pow_sav-Core | WI | Core part: UE Power Saving in NR | RP-191607 | CATT | Yes | Completed
R16 | R4 | NR | NR_PoserSaving-Perf | WI | Perf part: UE power saving in NR performance | RP-191607 | CATT | Yes | Ongoing |  |  | 0.25
R16 | R1 | NR | NR_POS-Core | WI | Core part: NR Positioning Support | RP-191156 | Intel | Yes | Completed
R16 | R4 | NR | NR_POS-Perf | WI | Perf part：NR Positioning Support | RP-191156 | Intel | Yes | Ongoing |  |  | 1 |  |  | 1 |  | 1
R16 | R1 | NR | NR_L1enh_URLLC-Core | WI | Core part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-191584 | Huawei | Yes | Completed
R16 | R4 | NR | NR_L1enh_URLLC-Perf | WI | Perf Part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-191584 | Huawei | Yes | Ongoing |  |  | 0.5
R17 | R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-193235 | MediaTek | No | NA
R17 | R1 | NR | FS_NR_pos_enh | SI | Study on NR positioning enhancements | RP-193237 | CATT | No | NA
R17 | R1 | NR | NR_pos_enh (planned) | WI | NR positioning enhancements | RP-xxxxxx |  | Yes | Not started | [7 empty] | 0.25 |  |  | 1 |  |  | 1 |  | 1 |  |  | 1
R17 | R4 | NR | NR_pos_enh-Perf (planned) | WI | NR positioning enhancements | RP-xxxxxx |  | Yes | Not started
R17 | R1 | NR | FS_NR_redcap | SI | Study on support of reduced capability NR devices | RP-193238 | Ericsson | No | NA
R17 | R1 | NR | NR_redcap-Core (planned) | WI | Support of reduced capability NR devices | RP-xxxxxx |  | Yes | Not started | [6 empty] | 0.25 | 0.25 |  | 0.5 | 1 |  | 0.5 | 1 | 0.5 | 1 |  | 0.5 | 1
R17 | R4 | NR | NR_redcap-Perf (planned) | WI | Support of reduced capability NR devices | RP-xxxxxx |  | Yes | Not started | [15 empty] | 0.25 |  |  | 0.5
R17 | R1 | NR | FS_NR_cov_enh | SI | Study on NR coverage enhancements | RP-193240 | China Telecom | No | NA
R17 | R1 | NR | NR_cov_en-Core (planned) | WI | NR coverage enhancements | RP-xxxxxx |  | Yes | NA | [6 empty] | 0.25 |  |  | 0.5 |  |  | 0.5 |  | 0.5 |  |  | 0.5
R17 | R4 | NR | NR_cov_enh-Perf (planned) | WI | NR coverage enhancements | RP-xxxxxx |  | Yes | Not started | [15 empty] | 0.25 |  |  | 0.5
R17 | R1 | NR | FS_NR_52_to_71GHz | SI | Study on supporting NR from 52.6 GHz to 71 GHz | RP-193259 | Intel | Yes | Ongoing |  | 1
R17 | R1 | NR | FS_NR_XR_eval | SI | Study on XR (Extended Reality) evaluations for NR | RP-193241 | Qualcomm | No | NA
R17 | R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-193133 | Samsung | Yes | Not started | [6 empty] | 0.25 | 0.25 |  | 0.25 | 1 |  | 0.25 | 1 | 0.25 | 1 |  | 0.25 | 1
R17 | R4 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-193133 | Samsung | Yes | Not started | [15 empty] | 0.25 |  |  | 0.5
R17 | R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Yes | Not started |  |  |  |  | 2 |  | 2 | 0.25 |  | 2 | 1 |  | 2 | 1 | 2 | 1 |  | 2 | 1
R17 | R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Yes | Not started | [18 empty] | 0.5
R17 | R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-193257 | LG Electronics | Yes | Ongoing |  | 1 |  |  | 1 | 0 | 1 | 0.25 |  | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 1
R17 | R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-193257 | LG Electronics | Yes | Not started | [18 empty] | 0.25
R17 | R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-193260 | Ericsson | No | NA
R17 | R1 | NR | NR_DSS-Perf | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-193260 | Ericsson | Yes | Not started
R17 | R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei, Ericsson | Yes | Not started |  |  |  |  | 0.5 |  | 0.5 | 0.25 |  | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5
R17 | R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf. part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei, Ericsson | Yes | Not started | [15 empty] | 0.25 |  |  | 0.5
RAN2-led items
R16 | R2 | NR | NR_IAB-Core | WI | Core part: Integrated Access and Backhaul for NR | RP-192188 | Qualcomm | Yes | Completed
R16 | R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-192188 | Qualcomm | Yes | Ongoing |  | 1 | 1 |  | 1 | 1 | 1 | 1
R16 | R2 | NR | LTE_NR_DC_CA_enh-Core | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-192336 | Ericsson | Yes | Completed
R16 | R4 | NR | LTE_NR_DC_CA_enh-Perf | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-192336 | Ericsson | Yes | Ongoing |  |  | 1 |  |  | 0.5 |  | 0.5
R16 | R2 | LTE | LTE_feMob-Core | WI | Core Part: Even further Mobility enhancement in E-UTRAN | RP-181544 | China Telecom | Yes | Completed
R16 | R4 | LTE | LTE_feMob-Perf | WI | Per Part: Even further Mobility enhancement in E-UTRAN | RP-181475 | China Telecom | Yes | Ongoing |  |  | 0.25
R17 | R2 | NR | FS_NR_SL_relay | SI | Study on NR Sidelink relay | RP-193253 | OPPO | No | NA
R17 | R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-193254 | CMCC | No | NA
R17 | R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-193233 | Nokia | Yes | Not started | [7 empty] | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5 |  |  | 0.5
R17 | R4 | NR | NR_IIOT_URLLC_enh-Perf | WI | Perf part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-193233 | Nokia | Yes | Not started
R17 | R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | Yes | Ongoing |  | 2 | 0.5 |  | 2 | 0.5 | 2 | 0.5 |  | 2 | 0.5 |  | 2 | 0.5 | 2 | 0.5 |  | 2 | 0.5
R17 | R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | Yes | Not started | [15 empty] | 0.25 |  |  | 0.5
R17 | R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-193239 | MediaTek | Yes | Ongoing |  |  | 0.25 |  |  | 0.25 |  | 0.25 |  |  | 0.25 |  |  | 0.25 |  | 0.25 |  |  | 0.25
R17 | R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-193239 | MediaTek | Yes | Not started | [18 empty] | 0.25
R17 | R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-193248 | Huawei | No | NA
R17 | R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | Yes | Not started | [7 empty] | 0.25 |  |  | 0.5 |  |  | 0.5 |  | 0.5 |  |  | 0.5
R17 | R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | Yes | Not started
R17 | R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | Yes | Not started |  |  |  |  | 0.25 |  | 0.5 | 0.25 |  | 1 | 0.5 |  | 1 | 0.5 | 1 | 0.5 |  | 1 | 0.5
R17 | R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | Yes | Not started | [18 empty] | 0.25
R17 | R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-201305 | ZTE | Yes | Not started | [13 empty] | 0.5 |  | 0.5 |  |  | 0.5
R17 | R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-201305 | ZTE | Yes | Not started
R17 | R2 | NR, LTE | LTE_NR_MUSIM | WI | Support for Multi-SIM devices in Rel-17 | RP-193263 | vivo | No | NA
RAN4-led items
R16 | R4 | NR | NR_DL256QAM_FR2-Core | WI | Core part: Add support of NR DL 256QAM for FR2 | RP-191891 | China Telecom | Yes | Completed
R16 | R4 | NR | NR_DL256QAM_FR2-Perf | WI | Perf. Part: Add support of NR DL 256QAM for FR2 | RP-191891 | China Telecom | Yes | Ongoing |  |  | 0.25
R16 | R4 | NR | NR_RRM_Enh_Core | WI | WI on NR RRM enhancement in R16 | RP-193211 | Intel, ZTE, Apple | Yes | Completed
R16 | R4 | NR | NR_RRM_Enh_Perf | WI | WI on NR RRM enhancement in R16 | RP-193211 | Intel, ZTE, Apple | Yes | Ongoing |  |  | 1
R16 | R4 | NR | NR_CSIRS_L3meas | WI | Core part: CSI-RS based L3 measurement requirements for NR | RP-191992 | CATT | Yes | Completed
R16 | R4 | NR | NR_CSIRS_L3meas | WI | Perf. part: CSI-RS based L3 measurement requirements for NR | RP-191992 | CATT | Yes | Ongoing |  |  | 1 |  |  | 0.5 |  | 0.5
R16 | R4 | NR | NR_enh-Perf | WI | NR performance requirement enhancement | RP-192532 | China Telecom | Yes | Ongoing |  |  | 0.75
R16 | R4 | NR | R16 NR Maintenance and TEI |  |  |  |  | Yes | Ongoing |  | 2 | 2.5 |  | 2 | 1.5 | 2 | 1.5 |  | 1.5 | 1 |  | 1.5 | 1 | 1.5 | 1 |  | 1.5 | 1
R17 | R4 | NR | FS_FR2_enhTestMethods | SI | Study on enhanced test methods for FR2 in NR | RP-192430 | Apple，CAICT | Yes | Ongoing |  | 0.5 |  |  | 0.5 |  | 0.5
R17 | R4 | NR | FS_6425_10500MHz _NR | WI |  | RP-200513 | Huawei | Yes | Ongoing |  | 1
R17 | R4 | NR | NR_FR2_FWA_Bn257_Bn258-Core | WI | Introduction of FR2 FWA UE with maximum TRP of 23dBm for band n257 and n258 | RP-200503 | Softbank | Yes | Ongoing |  | 0.1 | 0.25
R17 | R4 | NR | NR_FR2_FWA_Bn257_Bn258-Perf | WI | Introduction of FR2 FWA UE with maximum TRP of 23dBm for band n257 and n258 | RP-200503 | Softbank | Yes | Ongoing
R17 | R4 | NR | NR_RF_FR1_enh-Core | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-202088 | Huawei | Yes | Ongoing |  | 1.5 |  |  | 1.5 |  | 1.5 | 0.5 |  | 1.5 | 0.5 |  | 1.5 | 0.5 | 1.5 |  |  | 1.5
R17 | R4 | NR | NR_RF_FR1_enh-Perf | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-202088 | Huawei | Yes | Not started
R17 | R4 | NR | NR_demod_enh2-Perf | WI | Further enhancement on NR demodulation performance | RP-202000 | China Telecom | Yes | Not started | [5 empty] | 1.5 |  | 1.5 |  |  | 1.5 |  |  | 1.5 |  | 1.5 |  |  | 1
R17 | R4 | NR | NR_DL1024QAM_FR1-Core | WI | Introduction of DL 1024QAM for NR FR1 | RP-202044 | Ericsson | Yes | Not started |  |  |  |  | 0.25 |  | 0.25 |  |  | 0.25
R17 | R4 | NR | NR_DL1024QAM_FR1-Perf | WI | Introduction of DL 1024QAM for NR FR1 | RP-202044 | Ericsson | Yes | Not started | [12 empty] | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 | 0.25
R17 | R4 | NR | NR_HST_FR1_enh-Core | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-202106 | CMCC | Yes | Ongoing |  |  | 0.5 |  |  | 0.5 |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5 |  |  | 0.5
R17 | R4 | NR | NR_HST_FR1_enh-Perf | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-202106 | CMCC | Yes | Ongoing |  |  | 0.5 |  |  | 0.5 |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5 |  |  | 0.5
R17 | R4 | NR | NR_MIMO_OTA-Core | WI | MIMO OTA requirements for NR UEs | RP-201800 | CAICT | Yes | Ongoing |  | 0.5
R17 | R4 | NR | NR_MIMO_OTA-Perf | WI | MIMO OTA requirements for NR UEs | RP-201800 | CAICT | Yes | Ongoing |  | 0.5 |  |  | 1 |  | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  | 1
R17 | R4 | NR | FS_NR_eff_BW_util | SI | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | RP-202103 | Ericsson | Yes | Ongoing |  | 0.5 |  |  | 0.5 |  | 0.5
R17 | R4 | NR | NR_RF_FR2_req_enh2-Core | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-202107 | Nokia | Yes | Ongoing |  | 2 | 1 |  | 2 | 1 | 2 | 1 |  | 2 | 1 |  | 2 | 1 | 2 | 1 |  | 2 | 1
R17 | R4 | NR | NR_RF_FR2_req_enh2-Perf | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-202107 | Nokia | Yes | Not started
R17 | R4 | NR | NR_MG_enh-Core | WI | NR and MR-DC measurement gap enhancements | RP-202119 | MediaTek | Yes | Ongoing |  |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  | 1
R17 | R4 | NR | NR_MG_enh-Perf | WI | NR and MR-DC measurement gap enhancements | RP-202119 | MediaTek | Yes | Not started
R17 | R4 | NR | NR_HST_FR2-Core | WI | NR support for high speed train scenario in FR2 | RP-202118 | Samsung | Yes | Ongoing |  | 0.5 | 0.25 |  | 0.25 | 1 | 0.25 | 1 |  | 0.25 | 1 |  | 0.25 | 1 | 0.25 | 1 |  | 0.25 | 0.75
R17 | R4 | NR | NR_HST_FR2-Perf | WI | NR support for high speed train scenario in FR2 | RP-202118 | Samsung | Yes | Not started | [5 empty] | 0.5 |  | 0.5 |  |  | 1 |  |  | 1 |  | 1 |  |  | 0.75
R17 | R4 | NR | NR_RRM_enh2-Core | WI | Further RRM enhancement for NR and MR-DC | RP-202053 | Apple | Yes | Ongoing |  |  | 1.5 |  |  | 1.5 |  | 1.5 |  |  | 1.5 |  |  | 1.5 |  | 1.5 |  |  | 1
R17 | R4 | NR | NR_RRM_enh2-Perf | WI | Further RRM enhancement for NR and MR-DC | RP-202053 | Apple | Yes | Not started
R17 | R4 | NR | R17 Basket WIs |  |  |  |  | Yes | Ongoing |  | 3 |  |  | 3 |  | 3 |  |  | 3 |  |  | 3 |  | 3 |  |  | 3
R17 | R4 | NR | R17 NR spectrum related WI/SI |  |  |  |  | Yes | Ongoing |  | 2 |  |  | 2 |  | 2 |  |  | 2 |  |  | 2 |  | 2 |  |  | 2
R17 | R4 | NR | R17 LS activities |  |  |  |  | Yes | Ongoing |  | 1 | 1 |  | 1 | 1 | 1 | 1
RAN5-led items
R17 | R5 | NR | FS_UE_5GNR_App_Data_Perf | SI | Study on 5G NR UE Application Layer Data Throughput Performance |  | Qualcomm, AT&T | Yes | Not started | [5 empty] | 0.5 |  | 0.5 |  |  | 0.25
Last row in NR totals. Insert new NR items above this line. Do not remove
First row in LTE totals. Insert new LTE items below this line. Do not remove
RAN4-led items
R17 | R4 | LTE | LTE CA basket WIs |  |  |  |  | Yes | Ongoing |  | 1 |  |  | 1 |  | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  | 1
R17 | R4 | LTE | R17 LTE spectrum related WI/SI |  |  |  |  | Yes | Ongoing |  | 0.5 |  |  | 0.5 |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5 |  |  | 0.5
R16 | R4 | LTE | LTE Maintenance |  |  |  |  | Yes | Ongoing |  | 0.5 | 0.25 |  | 0.5 | 0.25 | 0.5 | 0.25 |  | 0.5 | 0.25 |  | 0.5 | 0.25 | 0.5 | 0.25 |  | 0.5 | 0.25
Last row in LTE totals. Insert new LTE items above this line. Do not remove
NR |  | NR |  |  | allocated above | [5 empty] | 21.1 | 20 |  | 21.25 | 16.75 | 22.25 | 19.75 |  | 19.25 | 17.5 |  | 19.25 | 18 | 19.25 | 18.75 |  | 19.25 | 19.75
NR |  | NR |  |  | Legacy
NR |  | NR |  |  | TEI and other not planned issues
NR |  | NR |  |  | Reserve
NR |  | NR |  |  | total used capacity | [5 empty] | 21.1 | 20 |  | 21.25 | 16.75 | 22.25 | 19.75 |  | 19.25 | 17.5 |  | 19.25 | 18 | 19.25 | 18.75 |  | 19.25 | 19.75
NR |  | NR |  |  | available capacity | [5 empty] | 22.5 | 20 |  | 22.5 | 20 | 22.5 | 20 |  | 22.5 | 20 |  | 22.5 | 20 | 22.5 | 20 |  | 22.5 | 20
NR |  | NR |  |  | remaining/exceeded capacity | [5 empty] | 1.4 | 0 |  | 1.25 | 3.25 | 0.25 | 0.25 |  | 3.25 | 2.5 |  | 3.25 | 2 | 3.25 | 1.25 |  | 3.25 | 0.25
LTE |  | LTE |  |  | allocated above | [5 empty] | 2 | 0.25 |  | 2 | 0.25 | 2 | 0.25 |  | 2 | 0.25 |  | 2 | 0.25 | 2 | 0.25 |  | 2 | 0.25
LTE |  | LTE |  |  | Legacy
LTE |  | LTE |  |  | TEI and other not planned issues
LTE |  | LTE |  |  | Reserve
LTE |  | LTE |  |  | total used capcaity | [5 empty] | 2 | 0.25 |  | 2 | 0.25 | 2 | 0.25 |  | 2 | 0.25 |  | 2 | 0.25 | 2 | 0.25 |  | 2 | 0.25
LTE |  | LTE |  |  | available capacity | [5 empty] | 2 | 0.5 |  | 2 | 0.5 | 2 | 0.5 |  | 2 | 0.5 |  | 2 | 0.5 | 2 | 0.5 |  | 2 | 0.5
LTE |  | LTE |  |  | remaining/exceeded capacity | [5 empty] | 0 | 0.25 |  | 0 | 0.25 | 0 | 0.25 |  | 0 | 0.25 |  | 0 | 0.25 | 0 | 0.25 |  | 0 | 0.25