## Slide 1: RAN Timeline and Meeting Planning
Source: RAN Chair, RAN1 Chair, RAN2 Chair, RAN3 Chair, RAN4 Chair, RAN5 Chair
RP-210978

## Slide 2: Background: RAN#91-e Endorsed RAN meeting plan & Rel-18 planning
TSG
June
2021
WG
TSG
RAN1-E
T
S
G
#
9
3 E
RAN5-E
RAN4-E
RAN3-E
RAN2-E
Planned as E-meetings
21-25
28-2
5-9
12-16
19-23
26-30
2-6
9-13
16-20
23-27
30-3
6-10
13-17
20-24
27-1
4-8
11-15
18-22
25-29
1-5
8-12
15-19
22-26
29-3
6-10
13-17
20-24
14-18
T
S
G
#
9
2
E
I
N
A
C
T
I
V
E
P
E
R
I
O
D
July
2021
August
2021
September
2021
October
2021
November
2021
December
2021
R
E
L
1
8
W
S
G
T W
s
TBD (f2f or E-meeting)
WG
WG
TSG
RAN5-E
Rel18
Email
Discussion
Q&A
Rel18
Email
Prep
January
2022
February
2022
17-21
24-28
31-04
07-11
14-18
21-25
March
2022
28-04
07-11
14-18
T
S
G
#
9
5
Rel-17 stage-3 freeze
Rel-18 RAN4 package approval
RAN1
RAN4
RAN3
RAN2
RAN5
10-14
03-07
WG
WG
TSG
Rel18
Email
Prep
Rel18
RAN4 Email
Prep
I
N
A
C
T
I
V
E
P
E
R
I
O
D
I
N
A
C
T
I
V
E
P
E
R
I
O
D
I
N
A
C
T
I
V
E
P
E
R
I
O
D
Rel18
consolidation
RAN1E
(5+2)
RAN2-E
RAN3-E
RAN4-E
T
S
G
#
9
4
E
Rel-17 RAN1 freeze
Rel-18 RAN1/2/3/4 package approval
I
N
A
C
T
I
V
E
P
E
R
I
O
D
21-25
I
N
A
C
T
I
V
E
P
E
R
I
O
D
RAN1E
(2+5)
RAN2
(5+2)
RAN3 (5+3)
RAN4 (5+2)
RAN1
(5+2)
INACTIVE
Planned as E-meeting,
but TBC in June

## Slide 3: RAN timeline
Rel-17 Timeline & start of Rel-18
  No timeline change for Rel-17 & the start of Rel-18
  Potential prioritization/down-scoping for Rel-17 items
    To be discussed in RAN#92-e (June) and in RAN#93-e (September)
Timeline for Rel-18
  To be discussed during RAN Rel-18 workshop

## Slide 4: RAN meeting planning
Regarding the inactive period during July 26th to July 30th
  RAN2 may use this period for email discussion at RAN2’s Chair discretion
Regarding WG meetings in 4Q’2021
  Confirm the previously endorsed arrangement as shown on slide 2
Regarding TBC for RAN#94 (f2f vs. electronic)
  Confirm to be electronic
For Q1/2022 WG meetings and RAN#95  To be discussed/confirmed in RAN#93-e (September)
Additional planning for Q2/2022 and afterwards is to be discussed in RAN#93-e

## Slide 5: Proposal
It is proposed to endorse the RAN timeline and meeting planning on slides 3 to 4.