## RAN4_TU_review_RAN#92-e
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [6 empty] | RAN | R1 | R2 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R4RF | R4RD | RAN | R4RF | R4RD | RAN | R4RF | R4RD | R4RF | R4RD | RAN | Final column of TU total. Insert new quarters before this column. Do not remove this column
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | latest SR | rapporteur | target | sum TUs | comment | 91 Mar.21 | 104bis | 113bis | 98bis | 98bis | 105 | 114 | 112 | 99 | 99 | 20 | 92 Jun.21 | 100 | 100 | 93 Sep.21 | 101 | 101 | 94 Dec.21 | 101bis | 101bis | 102 | 102 | 95 Mar.22
RAN1-led items
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-202024 | RP-211185 | Samsung | Mar 22 | 14 | REL-17 |  | 6 |  |  |  | 2 | 0.5 |  | 0.25 | 0.25 |  |  | 0.25 | 1 |  | 0.25 | 1 |  | 0.25 | 1 | 0.25 | 1
R4 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-202024 | RP-211185 | Samsung | Sept 22 | 0.75 | REL-17 | [19 empty] | 0.25 |  | 0.5
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-193229 | RP‑211267 | Qualcomm | Jun 21 | 20.25 | REL-17 |  | 3 |  | 2 |  | 1 |  |  | 2 | 0.25 |  |  | 2 | 1 |  | 2 | 1 |  | 2 | 1 | 2 | 1
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-193229 | RP-211267 | Qualcomm | Sep.21 | 0.5 | REL-17 | [21 empty] | 0.5
R1 | NR | NR_pos_enh-Core | WI | Core Part: NR positioning enhancements | RP-210903 | RP-211313 | CATT | Mar 22 | 11.75 | REL-17 |  | 1 | 1.5 |  |  | 3 | 2 |  |  | 0.25 |  |  |  | 1 |  |  | 1 |  |  | 1 |  | 1
R1 | NR | NR_pos_enh-Perf | WI | Perf Part: NR positioning enhancements | RP-210903 | RP-211313 | CATT | Sept 22 | 1 | REL-17 | [7 empty] | 1
R1 | NR | NR_redcap-Core | WI | Core Part: support of reduced capability NR devices | RP‑211038 | RP‑210982 | Ericsson | Mar 22 | 12 | REL-17 |  | 1 | 0.5 |  |  | 3 | 1 |  | 0.25 | 0.25 |  |  | 0.5 | 1 |  | 0.5 | 1 |  | 0.5 | 1 | 0.5 | 1
R1 | NR | NR_redcap-Perf | WI | Perf Part: support of reduced capability NR devices | RP‑211038 | RP-210982 | Ericsson | Sept 22 | 0.75 | REL-17 | [19 empty] | 0.25 |  | 0.5
R1 | NR | NR_cov_enh-Core | WI | Core Part: NR coverage enhancements | RP-210855 | RP-211126 | China Telecom | Mar 22 | 6.5 | REL-17 |  | 1 |  | 0.25 |  | 3 |  |  | 0.25 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_cov_enh-Perf | WI | NR coverage enhancements | RP-210855 | RP-211126 | China Telecom | Sept 22 | 0.75 | REL-17 | [19 empty] | 0.25 |  | 0.5
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-201306 | RP-211339 | Huawei, Ericsson | Mar 22 | 9.75 | REL-17 |  | 0.5 | 1 | 0.5 |  | 1.5 | 1 | 0.5 | 0.5 | 0.25 |  |  | 0.5 | 0.5 |  | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf part: Additional enhancements for NB-IoT and LTE-MTC | RP-201306 | RP-211339 | Huawei, Ericsson | Sept 22 | 0.75 | REL-17 | [19 empty] | 0.25 |  | 0.5
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-202846 | RP‑211271 | LG Electronics | Mar 22 | 16.25 | REL-17 |  | 3 | 1 | 1 |  | 1 | 1 |  | 1 | 0.25 |  |  | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-202846 | RP‑211271 | LG Electronics | Sept 22 | 0.25 | REL-17 | [21 empty] | 0.25
R1 | NR | FS_NR_XR_eval | SI | Study on XR (Extended Reality) evaluations for NR | RP-201145 | RP‑211266 | Qualcomm | Dec 21 | 2 | REL-17 |  | 1 |  |  |  | 1
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-202689 |  | MediaTek | Dec 21 | 3 | REL-17 |  | 1 | 0.5 |  |  | 1 | 0.5
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP‑211345 | RP‑211343 | Ericsson | Mar 22 | 2 | REL-17 |  | 0.5 |  |  |  | 1.5
R4 | NR | NR_DSS-Perf | WI | Perf part: NR Dynamic spectrum sharing (DSS) | RP‑211345 | RP‑211343 | Ericsson | Sept 22 | 0 | REL-17
R4 | NR | NR_unlic-Perf | WI | Perf part: NR-based Access to Unlicensed Spectrum | RP-191575 | RP-211265 | Qualcomm | Closed | 4 | REL-16 |  |  |  | 0.5 | 1.5 |  |  |  | 0.5 | 1.5
R4 | NR | 5G_V2X_NRSL-Perf | WI | Perf part: 5G V2X with NR sidelink | RP-200129 | RP‑211270 | LG Electronics | Closed | 2 | REL-16 |  |  |  |  | 1 |  |  |  |  | 1
R4 | NR | NR_POS-Perf | WI | Perf part：NR Positioning Support | RP-200218 | RP-211412 | Intel | Closed | 2 | REL-16 |  |  |  |  | 1 |  |  |  |  | 1
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  |  | Dec 19 | 3 | REL-17 |  | 1 |  |  |  | 2
RAN2-led items
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-211113 | RP-211111 | Nokia | Mar 22 | 8 | REL-17 |  | 3 |  |  |  | 1 | 1 | 0.5 |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_IIOT_URLLC_enh-Perf | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-211113 | RP-211111 | Nokia | Sept 22 | 0 | REL-17 | [16 empty] | 0 |  |  | 0 |  | 0
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-210988 | RP-210986 | Thales | Mar 22 | 21 | REL-17 |  | 0.5 | 1.5 | 2 | 0.5 | 1.5 | 1.5 | 1 | 2 | 0.5 |  |  | 2 | 0.5 |  | 2 | 0.5 |  | 2 | 0.5 | 2 | 0.5
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-210988 | RP-210986 | Thales | Sept 22 | 0.75 | REL-17 | [19 empty] | 0.25 |  | 0.5
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-210938 | RP-211452 | MediaTek | Mar 22 | 5.5 | REL-17 |  | 0.5 | 1 |  | 0.25 | 1.5 | 0 |  |  | 0.25 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-210938 | RP-211452 | MediaTek | Sept 22 | 0.25 | REL-17 | [21 empty] | 0.25
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-211200 | RP-211199 | Qualcomm | Mar.22 | 12 | REL-17 |  | 0.5 | 1 | 0.25 |  | 1.5 | 1 | 1 | 0.5 | 0.25 |  |  | 1 | 0.5 |  | 1 | 0.5 |  | 1 | 0.5 | 1 | 0.5
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-211200 | RP-211199 | Qualcomm | Sept 22 | 0.75 | REL-17 | [20 empty] | 0.5 | 0.25
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-201038 | RP‑211361 | Huawei | Mar.22 | 6 | REL-17 |  | 0.5 | 1.5 |  |  | 1.5 | 1.5 | 1
R4 | NR | NR_MBS_Perf | WI | Perf. part: NR multicast and broadcast services | RP-201038 | RP‑211361 | Huawei | Sept 22 | 0 | REL-17
R2 | NR | NR_SL_relay | WI | NR Sidelink Relay | RP‑211050 | RP‑211049 | OPPO | Mar.22 | 4.5 | REL-17 |  |  | 1.5 |  |  |  | 1 | [6 empty] | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R2 | NR | NR_Slice | WI | Enhancement of RAN Slicing for NR WID | RP‑211289 | RP‑211287 | CMCC | Mar.22 | 1 | REL-17 |  |  | 0.5 |  |  |  | 0.5
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-201612 |  | CMCC | Jun.21 | 0.5 | REL-17 | [7 empty] | 0.5
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | RP-211362 | Huawei | Mar.22 | 5 | REL-17 |  |  | 0.5 |  | 0.5 |  | 0.5 | 1 |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | RP-211362 | Huawei | Dec.21 | 0 | REL-17
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-201305 | RP‑211347 | ZTE | Mar.22 | 3 | REL-17 |  |  | 1 |  |  |  | 0.5 | [9 empty] | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-193252 | RP‑211347 | ZTE | Dec.21 | 0 | REL-17
R2 | NR, LTE | LTE_NR_MUSIM | WI | Support for Multi-SIM devices in Rel-17 | RP‑211156 | RP‑211157 | vivo | Jun 21 | 1.5 | REL-17 |  |  | 1 |  |  |  | 0.5
R2 | NR | NR_UDC-Core | WI | NR UDC | RP‑211203 | RP‑211204 | CATT
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-192188 | RP‑211198 | Qualcomm | Closed | 4 | REL-16 |  |  |  | 1 | 1 |  |  |  | 1 | 1
R4 | NR | LTE_NR_DC_CA_enh-Perf | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-192336 | RP‑211148 | Ericsson | Closed | 1 | REL-16 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R2 | NR |  |  | Misc R1 items, Cov Enh, DSS sched enh etc |  |  |  |  | 0.5 | REL-17 | [6 empty] | 0.5
R2 | NR, LTE |  |  | R17 Other, 5G Bcast etc (including reserve) |  |  |  |  | 2 | REL-17 |  |  | 1 |  |  |  | 1
RAN3-led items
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-201281 | RP‑211291 | CMCC | Mar 22 | 3 | REL-17 |  |  | 1 |  |  |  | 0.5 | 1.5
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP‑211409 | RP‑211410 | China Unicom | Sep 21 | 1 | REL-17 | [7 empty] | 1
R3 | NR | FS_NR_ENDC_data_collect | SI | Further Enhancments to Data Collection SI | RP-201620 | RP‑211288 | CMCC | Mar 22 | 1 | REL-17 | [7 empty] | 1
R3 | NR | NR_QoE | WI | NR QoE WI | RP‑211406 | RP‑211408 | China Unicom | Mar 22 | 2 | REL-17 |  |  | 0.5 |  |  |  | 0.5 | 1
R3 | NR | NG_RAN_PRN_enh | WI | NR Private Networks Enhancement WI | RP-202363 | RP‑211128 | China Telecom | Mar 22 | 1.5 | REL-17 |  |  | 0.5 |  |  |  | 0.5 | 0.5
R3 | NR | FS_NR_QoE | SI | Study on NR QoE (Quality of Experience) management and optimizations for diverse services | RP-193256 |  | China Unicom | Mar 21 | 0 | REL-17
RAN4-led items
R4 | NR | NR_CSIRS_L3meas | WI | Perf. part: CSI-RS based L3 measurement requirements for NR | RP-210590 | RP‑211212 | CATT | Closed | 1 | REL-16 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_FR2_enhTestMethods | SI | Study on enhanced test methods for FR2 in NR | RP‑211449 | RP‑211504/RP-211447 | Apple，CAICT |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | LTE | FS_HPUE_B12_B5_FWVM | SI | High power UE operation in Band 12 and Band 5 for fixed-wireless and vehicle-mounted use cases | RP-201261 | RP‑210984 | Nokia | Closed |  | REL-17 |  |  |  | 0.25 |  |  |  |  | 0.25
R4 | NR | FS_NR_eff_BW_util | SI | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | RP‑211468 | RP‑211403 | Ericsson |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.5 |  |  | 0.5
R4 | NR | FS_NR_PC2_UE_FDD | SI | Study on high power UE (power class 2) for one NR FDD band | RP-202870 | RP‑211074 | China Unicom |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.5
R4 | NR | FS_NR_600MHz_ext | SI | Study on extended 600MHz NR band | RP-202924 | RP‑211047 | Spark NZ Ltd | Sep 21 |  | REL-17 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1
R4 | NR | NR_MIMO_OTA-Core | WI | MIMO OTA requirements for NR UEs | RP-201800 | RP‑211303 | CAICT |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_MIMO_OTA-Perf | WI | MIMO OTA requirements for NR UEs | RP-201800 | RP‑211303 | CAICT |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_demod_enh2-Perf | WI | Further enhancement on NR demodulation performance | RP‑211135 | RP‑211134 | China Telecom |  |  | REL-17 |  |  |  |  | 1.5 |  |  |  |  | 1.5 |  |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 |  | 1
R4 | NR | NR_DL1024QAM_FR1-Core | WI | Introduction of DL 1024QAM for NR FR1 | RP-202886 | RP‑211301 | Ericsson |  |  | REL-17 |  |  |  | 0.25 |  |  |  |  | 0.25 |  |  |  | 0.25
R4 | NR | NR_DL1024QAM_FR1-Perf | WI | Introduction of DL 1024QAM for NR FR1 | RP-202044 | RP‑211301 | Ericsson |  |  | REL-17 | [15 empty] | 0.25 | 0.25 |  | 0.25 | 0.25 | 0.25 | 0.25
R4 | NR | NR_RRM_enh2-Core | WI | Further RRM enhancement for NR and MR-DC | RP-202874 | RP‑211428 | Apple |  |  | REL-17 |  |  |  |  | 1.5 |  |  |  |  | 1.5 |  |  |  | 1.5 |  |  | 1.5 |  |  | 1.5 |  | 1
R4 | NR | NR_RRM_enh2-Perf | WI | Further RRM enhancement for NR and MR-DC | RP-202874 | RP‑211428 | Apple |  |  | REL-17
R4 | NR | NR_HST_FR1_enh-Core | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | RP‑211292 | CMCC |  |  | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_HST_FR1_enh-Perf | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | RP‑211292 | CMCC |  |  | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_RF_FR2_req_enh2-Core | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP‑211174 | RP‑211499 | Nokia |  |  | REL-17 |  |  |  | 2 | 1 |  |  |  | 2 | 1 |  |  | 2 | 1 |  | 2 | 1 |  | 2 | 1 | 2 | 1
R4 | NR | NR_RF_FR2_req_enh2-Perf | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP‑211174 | RP‑211499/ RP‑211173 | Nokia |  |  | REL-17
R4 | NR | NR_HST_FR2-Core | WI | NR support for high speed train scenario in FR2 | RP-210800 | RP‑211196 | Samsung |  |  | REL-17 |  |  |  | 0.25 | 1 |  |  |  | 0.25 | 1 |  |  | 0.25 | 1 |  | 0.25 | 1 |  | 0.25 | 1 | 0.25 | 0.75
R4 | NR | NR_HST_FR2-Perf | WI | NR support for high speed train scenario in FR2 | RP-210800 | RP‑211196 | Samsung |  |  | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.5 |  |  | 1 |  |  | 1 |  | 0.75
R4 | NR | NR_MG_enh-Core | WI | NR and MR-DC measurement gap enhancements | RP-210679 | RP‑211453 | MediaTek |  |  | REL-17 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  | 1
R4 | NR | NR_MG_enh-Perf | WI | NR and MR-DC measurement gap enhancements | RP-210679 | RP‑211453 | MediaTek |  |  | REL-17
R4 | NR | NR_RF_FR1_enh-Core | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP‑211368 | RP‑211367 | Huawei |  |  | REL-17 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.5 |  |  | 1.5 | 0.5 |  | 1.5 | 1 |  | 1.5 | 1 | 1.5 | 1
R4 | NR | NR_RF_FR1_enh-Perf | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP‑211368 | RP‑211367 | Huawei |  |  | REL-17
RAN4 | NR | NR_repeaters-Core | WI | NR Repeaters | RP-210818 | RP‑211503/RP‑211304 | Qualcomm, Commscope | March 22 |  | REL-17 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  | 1
R4 | NR | NR_BCS4-Core | WI | Core part: Introduction of bandwidth combination set 4 (BCS4) for NR | RP-202832 | RP‑211167 | Ericsson | Mar. 2022 |  | REL-17 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  | 1
R4 | NR | NR_FR1_TRP_TRS-Core | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP‑211158 | RP‑211160 | vivo, OPPO, CMCC |  |  | REL-17 | [8 empty] | 0.25 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_FR1_TRP_TRS-Perf | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP‑211158 | RP‑211160 | vivo, OPPO, CMCC |  |  | REL-17 | [15 empty] | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | FS_NR_Opt_pi2BPSK | SI | New study on optimizations of pi/2 BPSK uplink power in NR | RP-210910 | RP‑211075 | Qualcomm |  |  | REL-17 | [8 empty] | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | LTE_terr_bcast_bands-Core | WI | Core part: WID on new bands and bandwidth allocation for LTE based 5G terrestrial broadcast | RP-210907 |  | EBU | Dec 21 | 0 | REL-17
R4 | NR | R17 NR Basket Wis | [7 empty] | REL-17 |  |  |  | 3 |  |  |  |  | 3 |  |  |  | 3 |  |  | 3 |  |  | 3 |  | 3
R4 | NR | R17 NR spectrum related WI/SI | [7 empty] | REL-17 |  |  |  | 2 |  |  |  |  | 2 |  |  |  | 2 |  |  | 2 |  |  | 2 |  | 2
R4 | LTE | R17 LTE basket WIs | [7 empty] | REL-17 |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  | 1 |  |  | 1 |  | 1
R4 | LTE | R17 LTE spectrum related WI/SI | [7 empty] | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | LTE,NR | R17 LTE/NR spectrum Perf part |  | All potential performance part for WIs in R17 NR Basket Wis, R17 NR spectrum related WI/SI, R17 LTE basket Wis,R17 LTE/NR spectrum Perf part | [5 empty] | REL-17 | [13 empty] | 0.25 |  |  | 0.25 |  |  | 0.25 |  | 0.25
R4 | NR | R17 LS activities | [7 empty] | REL-17 |  |  |  | 1 | 1 |  |  |  | 0.25 | 0.25
R4 | NR | R16 LTE and NR Maintenance and TEI | [7 empty] | REL-16 |  |  |  | 2 | 1.5 |  |  |  | 2 | 1.5 |  |  | 1.5 | 2 |  | 1.5 | 1 |  | 1.5 | 1 | 1.5 | 1
R4 | NR | R15 LTE and NR Maintenance | [11 empty] | 0.5 | 0.25 |  |  |  | 0.5 | 0.25 |  |  | 0.5 | 0.5 |  | 0.25 | 0.25
R4 | LTE | LTE maintenance | [20 empty] | 0.5 | 0.25 |  | 0.5 | 0.25 |  | 0.5 | 0.25 | 0.5 | 0.25
RAN5-led items
R5 | NR | FS_UE_5GNR_App_Data_Perf | SI | Study on 5G NR UE Application Layer Data Throughput Performance |  | RP‑211258 | Qualcomm, AT&T |  |  | Rel-17 | [13 empty] | 0.25
0
| LTE,NR |  |  | allocated above | [7 empty] | 24 | 17 | 27.25 | 17 | 27 | 17 | 11.5 | 28 | 19 | 0 | 0 | 27.25 | 19.75 | 0 | 26 | 20 | 0 | 25.25 | 21 | 25.75 | 22 | 0
| LTE,NR |  |  | Legacy | [7 empty] | 6 | 11 |  |  | 3 | 11
| LTE,NR |  |  | TEI and other not planned issues | [7 empty] | 1 | 0 |  |  | 1 | 0 | 1
| LTE,NR |  |  | Reserve
| LTE,NR |  |  | total used capacity | [7 empty] | 31 | 28 | 27.25 | 17 | 31 | 28 | 12.5 | 28 | 19 | 0 | 0 | 27.25 | 19.75 | 0 | 26 | 20 | 0 | 25.25 | 21 | 25.75 | 22 | 0
| LTE,NR |  |  | available capacity | [7 empty] | 31 | 28 | 24 | 15 | 31 | 28 | 12 | 24 | 15 |  |  | 24.5 | 20.5 |  | 24.5 | 20.5 |  | 24.5 | 20.5 | 24.5 | 20.5
| LTE,NR |  |  | remaining/exceeded capacity | [7 empty] | 0 | 0 | -3.25 | -2 | 0 | 0 | -0.5 | -4 | -4 |  |  | -2.75 | 0.75 |  | -1.5 | 0.5 |  | -0.75 | -0.5 | -1.25 | -1.5