## Cover sheet
3GPP TSG-RAN5 Meeting #92-e | [7 empty] | R5-214235
Electronic Meeting, 16 - 27 August 2021
Agenda Item: | 7.4.2
Source: | Rapporteur (Ericsson)
Title: | UE Conformance Test Aspects – UE Conformance Test Aspects – Rel-16 CA configurations Work Plan
Work item code: | LTE_CA_R16-UEConTest
Document for: Information
1. Introduction
At the RAN#80 meeting in August 2018 the Rel-16 RAN5 work item for UE Conformance Test Aspects of Rel-16 LTE CA configurations was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items for Rel-16 CA configurations. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. The work sheet 'Summary Work Plan' shows the status for each Rel-16 CA configuration. For each company assigned CA configurations that is ongoing and not yet completed a specific work sheet with the detailed work plan is provided.
2. Work item status
Estimation of WI overall completeness:
Area |  | Current Completeness | Number of Test cases/CA configs. | Number of company assigned Test cases(CA configs. | Number of ongoing Test cases/CA configs. | Number of completed Test cases/CA configs. | History
New Rel-16 LTE CA test cases |  | 7% | 39 (+39) | 0 | 0 | 0
New Rel-16 LTE CA configurations |  | 1% | 607 | 15 | 6 | 0
Estimation of completeness per type of CA configurations:
Type of CA configuration |  | Current Completeness | Number of CA configs. | Number of company assigned CA configs. | Number of ongoing CA configs. | Number of completed CA configs. | History
2DL/1UL |  | 8.1% | 12 | 1 | 1 | 0 | RAN5#81: WI created RAN5#82: 1.4%, +3 configs RAN5#83: 19.4% RAN5#84: 16.2% RAN5#88-e: 8.1%, +6 configs
2DL/2UL |  | 0% | 17 | 1 | 0 | 0 | RAN5#81: WI created RAN5#82: 0% +3 configs RAN5#83: 0% RAN5#84: +10 configs
3DL/1UL |  | 2.2% | 45 | 2 | 1 | 0 | RAN5#81: WI created RAN5#82: 0.4%, +10 configs RAN5#84: 3.7%, +5 configs RAN5#88-e: 2.3%, +11 configs
3DL/2UL |  | 0% | 67 | 0 | 0 | 0 | RAN5#81: WI created RAN5#82: 0%, +16 configs RAN5#83: 0%, +1 config RAN5#84: 3.7%, +19 configs RAN5#88-e:: 0%, -6 configs
3DL/3UL |  | 0% | 1 | 0 | 0 | 0 | RAN5#81: WI created
4DL/1UL |  | 0.8% | 87 | 5 | 1 | 0 | RAN5#81: WI created RAN5#82: 0%, +27 configs RAN5#83: 1.1%, +16 configs RAN5#88-e: 0.8%, + 7configs
4DL/2UL |  | 0% | 90 | 0 | 0 | 0 | RAN5#81: WI created RAN5#82: 0%, +25 configs RAN5#83: 0%, +32 configs RAN5#84: 3.7%, -19 configs RAN5#88-e: 0%, +5 configs
4DL/3UL |  | 0% | 4 | 0 | 0 | 0 | RAN5#81: WI created RAN5#83: 0%, +2 configs RAN5#88-e: 0%, -1 configs
4DL/4UL |  | 0% | 0 | 0 | 0 | 0
5DL/1UL |  | 1.7% | 81 | 4 | 2 | 0 | RAN5#81: WI created RAN5#82: 0%, +33 configs RAN5#83: 2.2%, +10 ocnfigs RAN5#84: 2.4%, -4 configs RAN5#88-e: 1.9%, +4 configs
5DL/2UL |  | 0% | 79 | 1 | 0 | 0 | RAN5#81: WI created RAN5#82: 0%, +31 configs RAN5#83: 0%, +24 configs RAN5#84: -21 configs RAN5#88-e: + 8 configs
5DL/3UL |  | 0% | 3 | 0 | 0 | 0 | RAN5#81: WI created RAN5#83: 0%, +2 configs RAN5#84: 0%, -1 configs
6DL/1UL |  | 1.2% | 54 | 1 | 1 | 0 | RAN5#81: WI created RAN5#82: 6%, +21 configs RAN5#83: 1.7%, + 6 configs RAN5#88-e: 1.4%, +4 configs
6DL/2UL |  | 0% | 36 | 0 | 0 | 0 | RAN5#81: WI created RAN5#82: 0%, +10 configs RAN5#83: 0%, + 4 configs RAN5#84: 0%, -5 configs RAN5#88-e: 0%, +6 configs
6DL/2UL |  | 0% | 1 | 0 | 0 | 0 | RAN5#85: CA config type introduced
7DL/1UL |  | 0% | 18 | 0 | 0 | 0 | RAN5#81: WI created RAN5#82: 0%, +7 configs RAN5#83: 0%, +2 configs RAN5#88-e: 0%, +2 configs
7DL/2UL |  | 0% | 10 | 0 | 0 | 0 | RAN5#81: WI created RAN5#82: 0%, +2 configs RAN5#83: 0%, +1 config RAN5#84: 0%, -1 configs
8DL/1UL |  | 0% | 1 | 0 | 0 | 0 | RAN5#88-e: CA config type introduced
3 References
[1] RP-181605 | New Work Item Proposal: UE Conformance Test Aspects – Rel-16 LTE CA configurations; Supporting companies: Bureau Veritas, CAICT, China Unicom, CMCC, Ericsson, Huawei, Korea Testing Laboratory, NTT DOCOMO, INC., Sprint, SRTC, Tejet, Telecom Italia, Verizon

## Summary Work Plan
RAN5 work plan summary for Rel-16 CA configurations
Note! CA configurations where the impact is limited to addition of new bandwidth combination set(s) to already existing CA configurations the CA configuration legend has a suffix "BW set #", where # indicate the new bandwidth combination set.
Sub-WI ID# | Sub-WI Name | Sub-WI Rapporteur | CA Type | Sub-WI scope |  |  |  | Sub-WI status
|  |  |  | Sub-WI Group Work Plan (Including the CA configuration(s) and CA fallbacks of the CA Sub-WI) | New CA configuration(s) | New DL Fallback CA config(s) | Other Fallback CA config(s) | Target / Completed | Completion | Progress since previous meeting | Comments
2DL-1UL CA Configurations
21145 | CA_2A-13A BW set 2 (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
21146 | CA_2A-26A (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
21148 | CA_7A-13A (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
21141 | CA_7A-29A (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
21154 | CA_18A-41A (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
21138 | CA_18A-42A (2DL-1UL) | KDDI | 2DL/1UL | 21138: CA_18A-42A (2DL-1UL) | 2DL/1UL: DL-CA_18A-42A (Rel-16: 21138) |  |  | RAN5#94 (Feb-22) | 97.06% |  | Contact: Tomoya Michihata(to-michihata@kddi.com)
21156 | CA_20A-41A (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
21144 | CA_26A-66A (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
21139 | CA_28A-32A (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
21142 | CA_28A-66A (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
21140 | CA_42A-42A BW set 1 (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
21150 | CA_48B (2DL-1UL) |  | 2DL/1UL | [5 empty] | 0%
2DL-2UL CA Configurations
22080 | CA_2A-13A BCS2 (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22070 | CA_2A-14A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22030 | CA_2A-48A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22061 | CA_3A-11A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22071 | CA_4A-28A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22027 | CA_13A-66A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22065 | CA_14A-30A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22066 | CA_14A-66A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22100 | CA_18A-41A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22068 | CA_25A-26A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22101 | CA_25A-26A BCS1 (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22102 | CA_25A-26A BCS2 (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22069 | CA_25A-41A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22057 | CA_26A-48A (2DL-2UL) | Southern Linc | 2DL/2UL | 22057: CA_26A-48A (2DL-2UL) | 2DL/2UL: DL-CA_26A-48A / UL-CA_26A-48A (Rel-16: 22057) |  | 2DL/1UL: DL-CA_26A-48A (Rel-15: 21114) - | RAN5#94 (Feb-22) | 0% |  | Contact: rdesai@southernco.com
22063 | CA_26A-48A-48A (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22074 | CA_48B (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
22062 | CA_48C (2DL-2UL) |  | 2DL/2UL | [5 empty] | 0%
3DL-1UL CA Configurations
31372 | CA_1A-3A-46A BW set 1 (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31358 | CA_1A-3A-46A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31375 | CA_1A-5A-28A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31373 | CA_1A-7A-38A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31374 | CA_1A-7A-46A BW set 1 (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31380 | CA_1A-8A-42A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31385 | CA_1A-11A-42A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31403 | CA_1A-18A-41A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31356 | CA_1A-18A-42A (3DL-1UL) | KDDI | 3DL/1UL | 51254: CA_1A-3A-18A-42C (5DL-1UL) |  |  |  |  | 0%
31404 | CA_1A-20A-38A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31357 | CA_1A-28A-40A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31405 | CA_2A-5A-48A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31381 | CA_2A-7A-13A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31367 | CA_2A-7A-29A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31387 | CA_2A-26A-66A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31376 | CA_2A-28A-66A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31377 | CA_3A-3A-5A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31378 | CA_3A-5A-7A BW set 1 (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31361 | CA_3A-5A-28A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31382 | CA_3A-8A-42A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31359 | CA_3A-18A-42A (3DL-1UL) | KDDI | 3DL/1UL | 31359: CA_3A-18A-42A (3DL-1UL) | 3DL/1UL: DL-CA_3A-18A-42A (Rel-16: 31359) |  | 2DL/1UL: DL-CA_3A-18A (Rel-15: 21119) 2DL/1UL: DL-CA_3A-42A (Rel-12) 2DL/1UL: DL-CA_18A-42A (Rel-16: 21138) | RAN5#94 (Feb-22) | 96.97% |  | Contact: Tomoya Michihata(to-michihata@kddi.com)
31360 | CA_3A-32A-46A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31379 | CA_5A-7A-66A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31203 | CA_5A-48A-66A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31324 | CA_5B-46A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31392 | CA_7A-7A-13A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31383 | CA_7A-7A-20A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31364 | CA_7A-7A-28A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31370 | CA_7A-7A-29A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31389 | CA_7A-13A-66A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31390 | CA_7A-26A-66A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31363 | CA_7A-28A-40A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31369 | CA_7A-29A-66A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31365 | CA_7A-32A-46A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31393 | CA_7C-13A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31371 | CA_7C-29A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31394 | CA_8A-11A-42A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31384 | CA_13A-46A-46A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31398 | CA_18A-41C (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31355 | CA_18A-42C (3DL-1UL) | KDDI | 3DL/1UL | 51254: CA_1A-3A-18A-42C (5DL-1UL) |  |  |  |  | 0%
31399 | CA_20A-41C (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31366 | CA_28A-42A-42A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31362 | CA_41A-42A-42A (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31368 | CA_42A-42C BW set 1 (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
31400 | CA_46A-48B (3DL-1UL) |  | 3DL/1UL | [5 empty] | 0%
3DL-2UL CA Configurations
32183 | CA_1A-1A-7A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32111 | CA_1A-3A-38A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32140 | CA_1A-7A-7A BW set 1 (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32148 | CA_1A-7A-8A BW set 1 (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32147 | CA_1A-7A-8A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32200 | CA_1A-7A-20A BCS2 (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32199 | CA_1A-7A-20A BCS1 (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32144 | CA_1A-7A-20A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32145 | CA_1A-7A-20A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32146 | CA_1A-7A-20A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32204 | CA_1A-18A-41A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32184 | CA_1A-41C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32101 | CA_2A-2A-13A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32126 | CA_2A-2A-14A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32102 | CA_2A-4A-13A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32205 | CA_2A-5A-48A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32130 | CA_2A-5A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32132 | CA_2A-5B (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32206 | CA_2A-12A-66A BCS1 (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32112 | CA_2A-12A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32149 | CA_2A-13A-46A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32207 | CA_2A-13A-48A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32208 | CA_2A-13A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32151 | CA_2A-14A-30A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32150 | CA_2A-14A-30A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32152 | CA_2A-14A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32153 | CA_2A-14A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32157 | CA_2A-46A-48A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32158 | CA_2A-46A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32127 | CA_2A-48A-48A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32159 | CA_2A-48A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32129 | CA_2A-48C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32160 | CA_2A-48C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32161 | CA_2A-48C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32165 | CA_2A-66B (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32164 | CA_2A-66B (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32167 | CA_2A-66C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32133 | CA_3A-8A-38A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32097 | CA_3C-28A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32109 | CA_4A-5B (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32139 | CA_4A-7C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32134 | CA_5A-5A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32212 | CA_5A-48A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32135 | CA_5A-66A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32110 | CA_5A-66B (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32169 | CA_5B-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32168 | CA_5B-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32171 | CA_13A-48A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32172 | CA_13A-48A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32173 | CA_13A-48A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32116 | CA_13A-66A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32117 | CA_13A-66B (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32118 | CA_13A-66C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32175 | CA_14A-30A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32176 | CA_14A-30A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32119 | CA_14A-66A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32191 | CA_18A-41C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32121 | CA_25A-25A-26A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32122 | CA_25A-25A-41A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32123 | CA_25A-41C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32100 | CA_26A-48C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32104 | CA_42A-42C BW set 1 (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32177 | CA_46A-48A-66A (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32194 | CA_46A-48B (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32178 | CA_46A-48C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32098 | CA_46A-48C (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
32115 | CA_48D (3DL-2UL) |  | 3DL/2UL | [5 empty] | 0%
3DL-3UL CA Configurations
33009 | CA_1A-41C (3DL-3UL) |  | 3DL/3UL | [5 empty] | 0%
33010 | CA_18A-41C (3DL-3UL) |  | 3DL/3UL | [5 empty] | 0%
33002 | CA_41D (3DL-3UL) |  | 3DL/3UL | [5 empty] | 0%
4DL-1UL CA Configurations
41444 | CA_1A-1A-3A-3A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41140 | CA_1A-1A-3A-28A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41434 | CA_1A-1A-7A-28A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41435 | CA_1A-1A-7C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41417 | CA_1A-3A-3A-5A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41458 | CA_1A-3A-5A-7A BCS1 (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41419 | CA_1A-3A-5A-28A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41405 | CA_1A-3A-7A-38A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41406 | CA_1A-3A-7A-46A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41436 | CA_1A-3A-8A-42A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41375 | CA_1A-3A-18A-42A (4DL-1UL) | KDDI | 4DL/1UL | 51254: CA_1A-3A-18A-42C (5DL-1UL) |  |  |  |  | 0%
41459 | CA_1A-3A-28A-40A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41376 | CA_1A-3A-41A-42A (4DL-1UL) | KDDI | 4DL/1UL | 61016: CA_1A-3A-41C-42C (6DL-1UL) | 6DL/1UL: DL-CA_1A-3A-41C-42C (Rel-16: 61016) 5DL/1UL: DL-CA_1A-3A-41A-42C (Rel-16: 51256) 5DL/1UL: DL-CA_1A-3A-41C-42A (Rel-16: 51257) 4DL/1UL: DL-CA_1A-3A-41A-42A (Rel-16: 41376) |  | 5DL/1UL: DL-CA_1A-41C-42C (Rel-14: 51011) 5DL/1UL: DL-CA_3A-41C-42C (Rel-14: 51036) 4DL/1UL: DL-CA_1A-3A-41C (Rel-15: 41297) 4DL/1UL: DL-CA_1A-3A-42C (Rel-13: 96) 4DL/1UL: DL-CA_1A-41A-42C (Rel-14: 41026) 4DL/1UL: DL-CA_1A-41C-42A (Rel-14: 41027) 4DL/1UL: DL-CA_3A-41A-42C (Rel-14: 41081) 4DL/1UL: DL-CA_3A-41C-42A (Rel-14: 41082) 4DL/1UL: DL-CA_41C-42C (Rel-13: 131) 3DL/1UL: DL-CA_1A-3A-41A (Rel-14: 31034) 3DL/1UL: DL-CA_1A-3A-42A (Rel-13: 35) 3DL/1UL: DL-CA_1A-41A-42A (Rel-14: 31040) 3DL/1UL: DL-CA_3A-41A-42A (Rel-13: 61) 3DL/1UL: DL-CA_3A-41C (Rel-13: 60) 3DL/1UL: DL-CA_41A-42C (Rel-13: 78) 2DL/1UL: DL-CA_3A-41A (Rel-13: 9) | RAN5#94 (Feb-22) | 67.47% |  | Contact: Tomoya Michihata(to-michihata@kddi.com)
41418 | CA_1A-3A-42A-42A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41377 | CA_1A-3A-46C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41404 | CA_1A-3A-46C BW set 1 (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41407 | CA_1A-3C-38A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41420 | CA_1A-5A-7A-28A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41437 | CA_1A-7A-7A-20A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41378 | CA_1A-7A-7A-28A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41421 | CA_1A-7A-28A-40A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41408 | CA_1A-7A-46C BW set 1 (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41445 | CA_1A-8A-11A-42A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41438 | CA_1A-8A-42C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41443 | CA_1A-11A-42C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41455 | CA_1A-18A-41C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41373 | CA_1A-18A-42C (4DL-1UL) | KDDI | 4DL/1UL | 51254: CA_1A-3A-18A-42C (5DL-1UL) |  |  |  |  | 0%
41374 | CA_1A-28A-40C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41271 | CA_2A-2A-5B (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41412 | CA_2A-5A-46A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41460 | CA_2A-5A-48A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41456 | CA_2A-5A-48C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41439 | CA_2A-7A-7A-13A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41395 | CA_2A-7A-7A-29A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41382 | CA_2A-7A-7A-46A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41446 | CA_2A-7A-13A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41447 | CA_2A-7A-26A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41394 | CA_2A-7A-29A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41381 | CA_2A-7A-46C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41440 | CA_2A-7C-13A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41422 | CA_2A-7C-28A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41396 | CA_2A-7C-29A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41409 | CA_2A-13A-46A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41062 | CA_2A-46A-46C (4DL-1UL) | CGC | 4DL/1UL | 41062: CA_2A-46A-46C (4DL-1UL) | 4DL/1UL: DL-CA_2A-46A-46C (Rel-14: 41062) 3DL/1UL: DL-CA_2A-46A-46A (Rel-14: 31074) 3DL/1UL: DL-CA_2A-46C (Rel-14: 31077) |  | 2DL/1UL: DL-CA_2A-46A (Rel-13: 143) | RAN5#94 (Feb-22) | 0% |  | Contact: bin.hou@cgctw.com
41410 | CA_2A-46A-66A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41411 | CA_2A-48A-66A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41425 | CA_3A-3A-5A-7A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41424 | CA_3A-3A-5A-28A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41414 | CA_3A-3A-7C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41423 | CA_3A-3A-46C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41426 | CA_3A-5A-7A-28A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41427 | CA_3A-5A-7C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41441 | CA_3A-7A-7A-20A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41387 | CA_3A-7A-7A-28A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41428 | CA_3A-7A-28A-40A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41386 | CA_3A-7A-32A-46A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41429 | CA_3A-7C-46A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41442 | CA_3A-8A-42C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41383 | CA_3A-18A-42C (4DL-1UL) | KDDI | 4DL/1UL | 51254: CA_1A-3A-18A-42C (5DL-1UL) |  |  |  |  | 0%
41397 | CA_3A-28A-42A-42A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41384 | CA_3A-32A-46C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41385 | CA_3A-41A-42A-42A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41430 | CA_5A-7A-66A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41431 | CA_5A-7C-28A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41432 | CA_5A-7C-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41415 | CA_5A-46A-66A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41416 | CA_5A-48A-66A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41457 | CA_5A-48C-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41319 | CA_5B-46C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41400 | CA_7A-7A-29A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41390 | CA_7A-28A-40C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41391 | CA_7A-32A-46C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41449 | CA_7C-13A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41401 | CA_7C-29A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41450 | CA_8A-11A-42C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41433 | CA_13A-46A-46C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41402 | CA_13A-46A-66A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41403 | CA_13A-48A-66A-66A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41451 | CA_18C-41C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41452 | CA_20A-41D (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41379 | CA_25A-26A-41C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41392 | CA_28A-41A-42A-42A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41393 | CA_28A-42A-42C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41388 | CA_41A-42A-42C (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41389 | CA_41C-42A-42A (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41398 | CA_42C-42C BW set 1 (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
41454 | CA_46C-48B (4DL-1UL) |  | 4DL/1UL | [5 empty] | 0%
4DL-2UL CA Configurations
42174 | CA_1A-1A-3C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42175 | CA_1A-1A-7C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42140 | CA_1A-3A-3A-7A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42176 | CA_1A-3A-3A-8A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42177 | CA_1A-3A-3A-8A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42178 | CA_1A-3A-3A-8A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42211 | CA_1A-3A-7A-8A BW set 1 (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42210 | CA_1A-3A-7A-8A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42209 | CA_1A-3A-7A-20A BW set 1 (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42208 | CA_1A-3A-7A-20A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42132 | CA_1A-3A-8A-38A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42129 | CA_1A-3A-41A-42A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42171 | CA_1A-3A-42C (4DL-2UL) ext |  | 4DL/2UL | [5 empty] | 0%
42108 | CA_1A-3C-28A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42180 | CA_1A-7A-7A-8A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42181 | CA_1A-7A-7A-8A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42179 | CA_1A-7A-7A-8A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42223 | CA_1A-18A-41C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42225 | CA_1A-18A-41C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42224 | CA_1A-18A-41C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42215 | CA_1A-42D (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42118 | CA_2A-2A-4A-5A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42154 | CA_2A-2A-5A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42152 | CA_2A-2A-13A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42188 | CA_2A-2A-14A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42187 | CA_2A-2A-14A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42238 | CA_2A-5A-48A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42226 | CA_2A-5A-48C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42158 | CA_2A-5A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42160 | CA_2A-5A-66B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42162 | CA_2A-5A-66C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42164 | CA_2A-5B-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42183 | CA_2A-13A-46A-46A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42182 | CA_2A-13A-46A-46A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42212 | CA_2A-13A-46A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42184 | CA_2A-13A-46C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42239 | CA_2A-13A-48A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42227 | CA_2A-13A-48C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42146 | CA_2A-13A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42148 | CA_2A-13A-66B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42150 | CA_2A-13A-66C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42213 | CA_2A-14A-30A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42185 | CA_2A-14A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42186 | CA_2A-14A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42214 | CA_2A-46A-48A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42194 | CA_2A-46A-48C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42195 | CA_2A-46C-48A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42196 | CA_2A-46C-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42197 | CA_2A-46C-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42156 | CA_2A-48A-48C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42228 | CA_2A-48A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42198 | CA_2A-48C-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42199 | CA_2A-48C-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42157 | CA_2A-48D (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42216 | CA_2A-66A-66B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42136 | CA_3A-3A-7C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42109 | CA_3A-42A-42C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42110 | CA_3C-7A-28A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42125 | CA_4A-4A-5B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42166 | CA_5A-5A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42167 | CA_5A-5A-66B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42127 | CA_5A-5A-66B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42168 | CA_5A-5A-66C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42232 | CA_5A-48A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42233 | CA_5A-48C-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42128 | CA_5A-66A-66B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42218 | CA_5A-66A-66C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42205 | CA_5B-66B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42204 | CA_5B-66B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42207 | CA_5B-66B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42206 | CA_5B-66B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42234 | CA_13A-48A-48A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42236 | CA_13A-48A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42235 | CA_13A-48C-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42173 | CA_14A-30A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42172 | CA_14A-30A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42139 | CA_14A-66A-66A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42144 | CA_25A-25A-41C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42145 | CA_25A-41D (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42135 | CA_28A-42A-42C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42111 | CA_41A-42A-42C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42121 | CA_42C-42C BW set 1 (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42200 | CA_46A-48C-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42137 | CA_46A-48D (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42201 | CA_46C-48A-66A (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42221 | CA_46C-48B (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42112 | CA_46C-48C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42202 | CA_46C-48C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42113 | CA_48C-48C (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
42138 | CA_48E (4DL-2UL) |  | 4DL/2UL | [5 empty] | 0%
4DL-3UL CA Configurations
43007 | CA_1A-3A-42C (4DL-3UL) |  | 4DL/3UL | [5 empty] | 0%
43010 | CA_1A-18A-41C (4DL-3UL) |  | 4DL/3UL | [5 empty] | 0%
43011 | CA_1A-18A-41C (4DL-3UL) |  | 4DL/3UL | [5 empty] | 0%
43001 | CA_41E (4DL-3UL) |  | 4DL/3UL | [5 empty] | 0%
4DL-4UL CA Configurations
44001 | CA_18C-41C (4DL-4UL) |  | 4DL/4UL | [5 empty] | 0%
5DL-1UL CA Configurations
51335 | CA_1A-1A-3A-3A-7A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51334 | CA_1A-1A-3A-3A-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51327 | CA_1A-1A-3A-7A-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51328 | CA_1A-1A-3A-7C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51315 | CA_1A-1A-3C-5A (5DL-1UL) | Hisilicon | 5DL/1UL | 52064: CA_1A-1A-3C-5A (5DL-2UL) |  |  |  |  | 0%
51314 | CA_1A-1A-3C-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51329 | CA_1A-1A-7C-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51316 | CA_1A-3A-3A-5A-7A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51255 | CA_1A-3A-3A-7A-8A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51217 | CA_1A-3A-3A-7A-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51277 | CA_1A-3A-3A-7C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51318 | CA_1A-3A-5A-7A-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51259 | CA_1A-3A-7A-7A-8A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51330 | CA_1A-3A-7A-7A-20A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51258 | CA_1A-3A-7A-7A-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51136 | CA_1A-3A-7A-8A-20A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51349 | CA_1A-3A-7A-20A-32A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51282 | CA_1A-3A-7A-46C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51331 | CA_1A-3A-8A-42C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51254 | CA_1A-3A-18A-42C (5DL-1UL) | KDDI | 5DL/1UL | 51254: CA_1A-3A-18A-42C (5DL-1UL) |  |  |  |  | 0%
51345 | CA_1A-3A-28A-40C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51256 | CA_1A-3A-41A-42C (5DL-1UL) | KDDI | 5DL/1UL | 61016: CA_1A-3A-41C-42C (6DL-1UL) | 6DL/1UL: DL-CA_1A-3A-41C-42C (Rel-16: 61016) 5DL/1UL: DL-CA_1A-3A-41A-42C (Rel-16: 51256) 5DL/1UL: DL-CA_1A-3A-41C-42A (Rel-16: 51257) 4DL/1UL: DL-CA_1A-3A-41A-42A (Rel-16: 41376) |  | 5DL/1UL: DL-CA_1A-41C-42C (Rel-14: 51011) 5DL/1UL: DL-CA_3A-41C-42C (Rel-14: 51036) 4DL/1UL: DL-CA_1A-3A-41C (Rel-15: 41297) 4DL/1UL: DL-CA_1A-3A-42C (Rel-13: 96) 4DL/1UL: DL-CA_1A-41A-42C (Rel-14: 41026) 4DL/1UL: DL-CA_1A-41C-42A (Rel-14: 41027) 4DL/1UL: DL-CA_3A-41A-42C (Rel-14: 41081) 4DL/1UL: DL-CA_3A-41C-42A (Rel-14: 41082) 4DL/1UL: DL-CA_41C-42C (Rel-13: 131) 3DL/1UL: DL-CA_1A-3A-41A (Rel-14: 31034) 3DL/1UL: DL-CA_1A-3A-42A (Rel-13: 35) 3DL/1UL: DL-CA_1A-41A-42A (Rel-14: 31040) 3DL/1UL: DL-CA_3A-41A-42A (Rel-13: 61) 3DL/1UL: DL-CA_3A-41C (Rel-13: 60) 3DL/1UL: DL-CA_41A-42C (Rel-13: 78) 2DL/1UL: DL-CA_3A-41A (Rel-13: 9) | RAN5#94 (Feb-22) | 67.47% |  | Contact: Tomoya Michihata(to-michihata@kddi.com)
51257 | CA_1A-3A-41C-42A (5DL-1UL) | KDDI | 5DL/1UL | 61016: CA_1A-3A-41C-42C (6DL-1UL) | 6DL/1UL: DL-CA_1A-3A-41C-42C (Rel-16: 61016) 5DL/1UL: DL-CA_1A-3A-41A-42C (Rel-16: 51256) 5DL/1UL: DL-CA_1A-3A-41C-42A (Rel-16: 51257) 4DL/1UL: DL-CA_1A-3A-41A-42A (Rel-16: 41376) |  | 5DL/1UL: DL-CA_1A-41C-42C (Rel-14: 51011) 5DL/1UL: DL-CA_3A-41C-42C (Rel-14: 51036) 4DL/1UL: DL-CA_1A-3A-41C (Rel-15: 41297) 4DL/1UL: DL-CA_1A-3A-42C (Rel-13: 96) 4DL/1UL: DL-CA_1A-41A-42C (Rel-14: 41026) 4DL/1UL: DL-CA_1A-41C-42A (Rel-14: 41027) 4DL/1UL: DL-CA_3A-41A-42C (Rel-14: 41081) 4DL/1UL: DL-CA_3A-41C-42A (Rel-14: 41082) 4DL/1UL: DL-CA_41C-42C (Rel-13: 131) 3DL/1UL: DL-CA_1A-3A-41A (Rel-14: 31034) 3DL/1UL: DL-CA_1A-3A-42A (Rel-13: 35) 3DL/1UL: DL-CA_1A-41A-42A (Rel-14: 31040) 3DL/1UL: DL-CA_3A-41A-42A (Rel-13: 61) 3DL/1UL: DL-CA_3A-41C (Rel-13: 60) 3DL/1UL: DL-CA_41A-42C (Rel-13: 78) 2DL/1UL: DL-CA_3A-41A (Rel-13: 9) | RAN5#94 (Feb-22) | 67.47% |  | Contact: Tomoya Michihata(to-michihata@kddi.com)
51317 | CA_1A-3A-42A-42C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51280 | CA_1A-3A-42D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51281 | CA_1A-3A-46D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51260 | CA_1A-3C-7A-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51283 | CA_1A-3C-7A-38A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51319 | CA_1A-7A-28A-40C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51284 | CA_1A-7A-46D BW set 1 (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51336 | CA_1A-8A-11A-42C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51288 | CA_2A-2A-5B-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51198 | CA_2A-2A-13A-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51287 | CA_2A-2A-13A-66B (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51290 | CA_2A-5A-46A-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51291 | CA_2A-5A-46C-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51196 | CA_2A-5A-46D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51346 | CA_2A-5A-48A-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51347 | CA_2A-5A-48C-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51339 | CA_2A-5A-48D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51271 | CA_2A-7A-7A-29A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51262 | CA_2A-7A-7A-46C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51272 | CA_2A-7A-7A-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51261 | CA_2A-7A-46D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51337 | CA_2A-7C-13A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51273 | CA_2A-7C-29A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51274 | CA_2A-7C-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51340 | CA_2A-13A-46A-46C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51285 | CA_2A-13A-46A-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51286 | CA_2A-13A-46C-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51348 | CA_2A-13A-48A-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51033 | CA_2A-46A-46D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51289 | CA_2A-46C-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51341 | CA_2A-48C-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51320 | CA_3A-3A-5A-7A-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51292 | CA_3A-3A-7C-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51321 | CA_3A-5A-7C-28A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51322 | CA_3A-7A-28A-40C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51265 | CA_3A-7A-32A-46C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51323 | CA_3A-7C-46C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51275 | CA_3A-28A-42A-42C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51263 | CA_3A-32A-46D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51264 | CA_3A-41A-42A-42C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51324 | CA_5A-7C-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51295 | CA_5A-46C-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51342 | CA_5A-48C-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51343 | CA_5A-48D-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51205 | CA_5B-46D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51268 | CA_7A-32A-46D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51326 | CA_13A-46A-46D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51325 | CA_13A-46A-46D (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51276 | CA_13A-46C-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51069 | CA_13A-48A-48C-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51344 | CA_13A-48C-66A-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51072 | CA_13A-48D-66A (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51332 | CA_25A-41E (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51269 | CA_28A-41A-42A-42C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51270 | CA_28A-42C-42C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51266 | CA_41A-42C-42C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51267 | CA_41C-42A-42C (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
51338 | CA_46D-48B (5DL-1UL) |  | 5DL/1UL | [5 empty] | 0%
5DL-2UL CA Configurations
52114 | CA_1A-1A-3A-3A-7A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52088 | CA_1A-1A-3A-7C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52064 | CA_1A-1A-3C-5A (5DL-2UL) | Hisilicon | 5DL/2UL | 52064: CA_1A-1A-3C-5A (5DL-2UL) |  |  |  |  | 0%
52090 | CA_1A-1A-3C-7A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52061 | CA_1A-1A-3C-28A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52089 | CA_1A-1A-3C-28A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52091 | CA_1A-1A-7C-28A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52067 | CA_1A-3A-3A-7A-7A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52103 | CA_1A-3A-3A-7A-8A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51296 | CA_1A-3A-3A-7C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52104 | CA_1A-3A-7A-7A-8A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51297 | CA_1A-3A-41A-42C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52087 | CA_1A-3A-41A-42C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51303 | CA_1A-3A-41C-42A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51306 | CA_1A-3A-42D (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52070 | CA_1A-3A-42D (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52043 | CA_1A-3C-7A-28A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
42120 | CA_2A-2A-5A-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52075 | CA_2A-2A-5A-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52076 | CA_2A-2A-5A-66B (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52078 | CA_2A-2A-5A-66C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52107 | CA_2A-2A-14A-30A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52096 | CA_2A-2A-14A-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52097 | CA_2A-2A-14A-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52053 | CA_2A-5A-46D (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52125 | CA_2A-5A-48A-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52126 | CA_2A-5A-48C-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52115 | CA_2A-5A-48D (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52054 | CA_2A-5B-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52083 | CA_2A-5B-66B (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52085 | CA_2A-5B-66C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52092 | CA_2A-13A-46A-46C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52093 | CA_2A-13A-46A-46C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52105 | CA_2A-13A-46C-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
42114 | CA_2A-13A-48A-48A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52050 | CA_2A-13A-48A-48C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52127 | CA_2A-13A-48A-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
42116 | CA_2A-13A-48C-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52116 | CA_2A-13A-48D (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52074 | CA_2A-13A-66A-66B (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52117 | CA_2A-13A-66A-66C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52106 | CA_2A-14A-30A-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52094 | CA_2A-14A-66A-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52095 | CA_2A-14A-66A-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52108 | CA_2A-46A-48C-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52109 | CA_2A-46C-48A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52098 | CA_2A-46C-48C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52080 | CA_2A-46D-48A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52099 | CA_2A-46D-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52100 | CA_2A-46D-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52081 | CA_2A-48A-48D (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52110 | CA_2A-48C-48C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52118 | CA_2A-48C-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52119 | CA_2A-48D-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52082 | CA_2A-48E (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51310 | CA_3A-3A-7C-28A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51309 | CA_3A-28A-42A-42C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52044 | CA_3A-41A-42A-42C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51311 | CA_3A-42C-42C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52045 | CA_3C-7C-28A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52059 | CA_5A-5A-66A-66B (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52111 | CA_5A-5A-66A-66C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52112 | CA_5A-5A-66D (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52121 | CA_5A-48C-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52122 | CA_5A-48D-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52048 | CA_13A-46D-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52123 | CA_13A-48C-66A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52124 | CA_13A-48D-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52072 | CA_25A-25A-41D (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52073 | CA_25A-41E (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51307 | CA_28A-41A-42A-42C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51308 | CA_28A-42C-42C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52046 | CA_41A-42C-42C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52047 | CA_41C-42A-42C (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51312 | CA_46A-48E (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52101 | CA_46C-48C-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
51313 | CA_46C-48D (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52102 | CA_46D-48A-66A (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
52113 | CA_46D-48B (5DL-2UL) |  | 5DL/2UL | [5 empty] | 0%
5DL-3UL CA Configurations
53009 | CA_1A-3A-41A-42C (5DL-3UL) |  | 5DL/3UL | [5 empty] | 0%
53006 | CA_1A-3A-42D (5DL-3UL) |  | 5DL/3UL | [5 empty] | 0%
53000 | CA_41F (5DL-3UL) |  | 5DL/3UL | [5 empty] | 0%
6DL-1UL CA Configurations
61058 | CA_1A-1A-3A-3A-7A-28A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61059 | CA_1A-1A-3A-3A-7C (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61055 | CA_1A-1A-3A-7C-28A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61056 | CA_1A-1A-3C-7A-28A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61057 | CA_1A-1A-3C-7C (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61015 | CA_1A-3A-3A-7A-7A-8A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61060 | CA_1A-3A-3A-7C-28A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61034 | CA_1A-3A-7A-46D (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61016 | CA_1A-3A-41C-42C (6DL-1UL) | KDDI | 6DL/1UL | 61016: CA_1A-3A-41C-42C (6DL-1UL) | 6DL/1UL: DL-CA_1A-3A-41C-42C (Rel-16: 61016) 5DL/1UL: DL-CA_1A-3A-41A-42C (Rel-16: 51256) 5DL/1UL: DL-CA_1A-3A-41C-42A (Rel-16: 51257) 4DL/1UL: DL-CA_1A-3A-41A-42A (Rel-16: 41376) |  | 5DL/1UL: DL-CA_1A-41C-42C (Rel-14: 51011) 5DL/1UL: DL-CA_3A-41C-42C (Rel-14: 51036) 4DL/1UL: DL-CA_1A-3A-41C (Rel-15: 41297) 4DL/1UL: DL-CA_1A-3A-42C (Rel-13: 96) 4DL/1UL: DL-CA_1A-41A-42C (Rel-14: 41026) 4DL/1UL: DL-CA_1A-41C-42A (Rel-14: 41027) 4DL/1UL: DL-CA_3A-41A-42C (Rel-14: 41081) 4DL/1UL: DL-CA_3A-41C-42A (Rel-14: 41082) 4DL/1UL: DL-CA_41C-42C (Rel-13: 131) 3DL/1UL: DL-CA_1A-3A-41A (Rel-14: 31034) 3DL/1UL: DL-CA_1A-3A-42A (Rel-13: 35) 3DL/1UL: DL-CA_1A-41A-42A (Rel-14: 31040) 3DL/1UL: DL-CA_3A-41A-42A (Rel-13: 61) 3DL/1UL: DL-CA_3A-41C (Rel-13: 60) 3DL/1UL: DL-CA_41A-42C (Rel-13: 78) 2DL/1UL: DL-CA_3A-41A (Rel-13: 9) | RAN5#94 (Feb-22) | 67.47% |  | Contact: Tomoya Michihata(to-michihata@kddi.com)
61049 | CA_1A-3A-42C-42C (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61033 | CA_1A-3A-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61017 | CA_1A-3C-7C-28A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61035 | CA_1A-7A-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61041 | CA_2A-5A-46C-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61042 | CA_2A-5A-46D-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61043 | CA_2A-5A-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61067 | CA_2A-5A-48C-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61068 | CA_2A-5A-48D-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61019 | CA_2A-7A-7A-46D (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61018 | CA_2A-7A-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61063 | CA_2A-13A-46A-46D (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61036 | CA_2A-13A-46C-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61037 | CA_2A-13A-46D-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61038 | CA_2A-13A-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61069 | CA_2A-13A-48C-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61070 | CA_2A-13A-48D-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61039 | CA_2A-46D-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61064 | CA_2A-48D-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61040 | CA_2A-48E-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61023 | CA_3A-7A-32A-46D (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61024 | CA_3A-7A-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61053 | CA_3A-7C-46D (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61020 | CA_3A-28A-41C-42C (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61029 | CA_3A-28A-42C-42C (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61021 | CA_3A-32A-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61022 | CA_3A-41A-42C-42C (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61046 | CA_5A-46D-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61047 | CA_5A-46E-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61065 | CA_5A-48D-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61048 | CA_5B-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61027 | CA_7A-7A-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61026 | CA_7A-32A-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61054 | CA_7C-46E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61030 | CA_13A-46D-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61031 | CA_13A-46E-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61066 | CA_13A-48D-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61032 | CA_13A-48E-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61061 | CA_25A-25A-26A-41D (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61050 | CA_25A-25A-41E (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61051 | CA_25A-41F (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61028 | CA_28A-41A-42C-42C (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61025 | CA_41C-42C-42C (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61062 | CA_46E-48B (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
61045 | CA_46E-66A-66A (6DL-1UL) |  | 6DL/1UL | [5 empty] | 0%
6DL-2UL CA Configurations
62029 | CA_1A-1A-3A-3A-7C (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62019 | CA_1A-1A-3A-7C-28A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62020 | CA_1A-1A-3C-7A-28A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62021 | CA_1A-1A-3C-7C (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62022 | CA_1A-1A-3C-7C (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62030 | CA_1A-3A-3A-7A-7A-8A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62031 | CA_1A-3A-3A-7C-28A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62005 | CA_1A-3A-41C-42C (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62001 | CA_1A-3C-7C-28A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62040 | CA_2A-5A-48C-66A-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62041 | CA_2A-5A-48D-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62023 | CA_2A-13A-46A-46D (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62032 | CA_2A-13A-46D-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62024 | CA_2A-13A-46E (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62025 | CA_2A-13A-46E (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62042 | CA_2A-13A-48C-66A-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62043 | CA_2A-13A-48D-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62033 | CA_2A-46C-48C-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62034 | CA_2A-46D-48A-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62026 | CA_2A-46D-48C (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62016 | CA_2A-46E-48A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62027 | CA_2A-46E-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62036 | CA_2A-48D-66A-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62037 | CA_2A-48E-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62002 | CA_3A-28A-41C-42C (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62012 | CA_3A-28A-42C-42C (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62003 | CA_3A-41A-42C-42C (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62038 | CA_5A-48D-66A-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62039 | CA_13A-48D-66A-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62014 | CA_25A-25A-41E (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62015 | CA_25A-41F (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62011 | CA_28A-41A-42C-42C (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62004 | CA_41C-42C-42C (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62013 | CA_46C-48E (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62028 | CA_46D-48C-66A (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
62035 | CA_46E-48B (6DL-2UL) |  | 6DL/2UL | [5 empty] | 0%
6DL-3UL CA Configurations
63003 | CA_1A-3A-41C-42C (6DL-3UL) |  | 6DL/3UL | [5 empty] | 0%
7DL-1UL CA Configurations
71019 | CA_1A-1A-3A-3A-7C-28A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71018 | CA_1A-1A-3C-7C-28A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71009 | CA_1A-3A-7A-46E (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71013 | CA_2A-5A-46D-66A-66A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71014 | CA_2A-5A-46E-66A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71022 | CA_2A-5A-48D-66A-66A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71007 | CA_2A-7A-7A-46E (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71010 | CA_2A-13A-46D-66A-66A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71024 | CA_2A-13A-46E-66A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71023 | CA_2A-13A-48D-66A-66A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71011 | CA_2A-46E-48A-66A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71012 | CA_2A-46E-66A-66A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71021 | CA_2A-48E-66A-66A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71008 | CA_3A-7A-32A-46E (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71017 | CA_3A-7C-46E (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71015 | CA_5A-46E-66A-66A (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71020 | CA_25A-25A-26A-41E (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
71016 | CA_25A-25A-41F (7DL-1UL) |  | 7DL/1UL | [5 empty] | 0%
7DL-2UL CA Configurations
72006 | CA_1A-1A-3A-3A-7C-28A (7DL-2UL) |  | 7DL/2UL | [5 empty] | 0%
72004 | CA_1A-1A-3C-7C-28A (7DL-2UL) |  | 7DL/2UL | [5 empty] | 0%
72005 | CA_1A-1A-3C-7C-28A (7DL-2UL) |  | 7DL/2UL | [5 empty] | 0%
72010 | CA_2A-5A-48D-66A-66A (7DL-2UL) |  | 7DL/2UL | [5 empty] | 0%
72007 | CA_2A-13A-46E-66A (7DL-2UL) |  | 7DL/2UL | [5 empty] | 0%
72011 | CA_2A-13A-48D-66A-66A (7DL-2UL) |  | 7DL/2UL | [5 empty] | 0%
72008 | CA_2A-46D-48C-66A (7DL-2UL) |  | 7DL/2UL | [5 empty] | 0%
72001 | CA_2A-46E-48A-66A (7DL-2UL) |  | 7DL/2UL | [5 empty] | 0%
72009 | CA_2A-48E-66A-66A (7DL-2UL) |  | 7DL/2UL | [5 empty] | 0%
72003 | CA_25A-25A-41F (7DL-2UL) |  | 7DL/2UL | [5 empty] | 0%
8DL-1UL CA Configurations
81001 | CA_25A-25A-26A-41F (8DL-1UL) |  | 8DL/1UL | [5 empty] | 0%

## New Rel-16 TCs
RAN5 CA WI | CCs | TS | Clause | New TC | Description | Responsible company | Completion level [%] | Target completion [RAN5#xx] | Remains
Rel-16 | 8DL | 36.521-1 | 7.3A.13 | Y | Reference sensitivity level for 8DL CA |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 7.4A.11 | Y | Maximum input level for 8DL CA |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 7.4A.11_H | Y | Maximum input level for 8DL CA for 256QAM in DL |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 7.5A.11 | Y | Adjacent Channel Selectivity (ACS) for 8DL CA |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 7.6.1A.11 | Y | In-band blocking for 8DL CA |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 7.6.2A.11 | Y | Out-of-band blocking for 8DL CA |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 7.6.3A.11 | Y | Narrow band blocking for 8DL CA |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 7.7A.11 | Y | Spurious response for 8DL CA |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 7.8.1A.11 | Y | Wideband intermodulation for 8DL CA |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.1.1.1_A.8 | Y | FDD PDSCH Single Antenna Port Performance for CA (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.1.3.1_A.8 | Y | FDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.1.4.2_A.7 | Y | FDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.2.1.1_A.7 | Y | TDD PDSCH Single Antenna Port Performance for CA (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.2.3.1_A.7 | Y | TDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.2.4.2_A.8 | Y | TDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.3.1.1.7 | Y | TDD FDD CA PDSCH Single Antenna Port Performance for FDD PCell (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.3.1.2.7 | Y | TDD FDD CA PDSCH Single Antenna Port Performance for TDD PCell (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.3.2.1.7 | Y | TDD FDD CA PDSCH Open Loop Spatial Multiplexing 2x2 for FDD PCell (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.3.2.2.7 | Y | TDD FDD CA PDSCH Open Loop Spatial Multiplexing 2x2 for TDD PCell (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.3.3.1.7 | Y | TDD FDD CA PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for FDD PCell (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.2.3.3.2.7 | Y | TDD FDD CA PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for TDD PCell (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.7.1.1_A.8 | Y | FDD Sustained data rate performance for CA (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.7.1.1_H.8 | Y | FDD Sustained data rate performance for CA (8DL CA) for 256QAM in DL |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.7.2.1_A.8 | Y | TDD sustained data rate performance for CA (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.7.2.1_H.8 | Y | TDD sustained data rate performance for CA (8DL CA) for 256QAM in DL |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.7.5.1.7 | Y | TDD FDD CA Sustained data rate performance for FDD PCell (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.7.5.1_H.7 | Y | TDD FDD CA Sustained data rate performance for FDD PCell (8DL CA) for 256QAM in DL |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.7.5.2.7 | Y | TDD FDD CA Sustained data rate performance for TDD PCell (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 8.7.5.2_H.7 | Y | TDD FDD CA Sustained data rate performance for TDD PCell (8DL CA) for 256QAM in DL |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 9.6.1.1_A.7 | Y | FDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 9.6.1.2_A.7 | Y | TDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 9.6.1.3.7 | Y | TDD FDD CA CQI Reporting under AWGN conditions – PUCCH 1-0 for FDD PCell (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-1 | 9.6.1.4.7 | Y | TDD FDD CA CQI Reporting under AWGN conditions – PUCCH 1-0 for TDD PCell (8DL CA) |  | 0% | TBD
Rel-16 | 8DL | 36.521-3 | 8.16.103 | Y | 8DL CA Event Triggered Reporting under Deactivated SCells in Non-DRX with generic duplex modes |  | 0% | TBD
Rel-16 | 8DL | 36.521-3 | 8.16.104 | Y | 8DL CA Event Triggered Reporting on Deactivated SCell with PCell and SCell Interruptions in Non-DRX with generic duplex modes |  | 0% | TBD
Rel-16 | 8DL | 36.521-3 | 8.16.105 | Y | 8DL CA Activation and Deactivation of Known SCell in Non-DRX with generic duplex modes |  | 0% | TBD
Rel-16 | 8DL | 36.521-3 | 8.16.106 | Y | 8DL CA Activation and Deactivation of Unknown SCell in Non-DRX with generic duplex modes |  | 0% | TBD
Rel-16 | 8DL | 36.521-3 | 9.1.73 | Y | 8DL RSRP for E-UTRAN in Carrier Aggregation with generic duplex modes |  | 0% | TBD
Rel-16 | 8DL | 36.521-3 | 9.2.60 | Y | 8DL RSRQ for E-UTRAN in Carrier Aggregation with generic duplex modes |  | 0% | TBD