## Cover sheet
3GPP TSG-RAN Meeting #93-e | [10 empty] | RP-211934
Electronic Meeting, 13th Sep 2021 - 17th Sep 2021
Agenda Item: | 13.5.30
Source: | Nokia, Nokia Shanghai Bell
Title: | WP LTE-NR & NR-NR Dual Connectivity and NR CA enhancements
Work item code: | LTE_NR_DC_CA_enh-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The technical objective of this work item is to provide conformance test specifications for the Release 16 DCCA enhancements requirements. More specifically, the WI covers the following conformance areas: Develop RRM test cases for DCCA enhancement requirements defined in RAN4; Develop MAC and RRC signaling test cases for DCCA enhancement requirements defined in RAN2;
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 6% (+1%) | 0 | 58
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 6.7% (+1.7%) | 0 | 34
FR1 |  | 6.4% (+1.4%) | 0 | 24
FR2 |  | 6.2% (+1.2%) | 0 | 16
FR1 + FR2 |  | 9.1% (+4.1%) | 0 | 5
NSA Option 3 (EN-DC) |  | 5% (+0%) | 0 | 24
FR1 |  | 5% | 0 | 15
FR2 |  | 5% | 0 | 10
FR1 + FR2 |  | 5% | 0 | 3
LTE
FDD
TDD
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [8 empty] | NSA Option 3 (EN-DC) | [8 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 | [5 empty] | FR1 |  |  | FR2 |  |  | FR1 + FR2 |  |  | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
UE specific test functions | 38.509 | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
NR RF/RRM
RRM test cases | 38.533 | 0% | 0 | 33 | 0% | 0 | 7 | 0% | 0 | 6 | 0% | 0 | 4 | 0% | 0 | 7 | 0% | 0 | 6 | 0% | 0 | 3
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 1.6% (+1.6%) | 0 | 25 | 1.8% (+1.8%) | 0 | 17 | 1.5% (+1.5%) | 0 | 10 | 5% (+5%) | 0 | 1 | 0% | 0 | 8 | 0% | 0 | 4
Applicability Protocol test cases | 38.523-2 | 31.6% (+31.6%) |  |  | 35% (+35%) |  |  | 30% (+30%) |  |  | 100% (+100%) |  |  | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0%
5 References
[1] RP-yyxxxx | <WID document title>
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP LTE-NR & NR-NR Dual Connectivity and NR CA enhancements | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_NR_DC_CA_enh-UEConTest
WP Scope: |  | <WP Scope description> | [14 empty] | vs Area
WP Resp: |  | Matti Kangas |  |  | matti.kangas@nokia.com | [5 empty] | WP item completion |  |  |  |  | SA Option 2 (SA NR) |  |  | NSA Option 3 (EN-DC) |  |  | LTE
TS Resp: |  | - |  |  | -
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) | LTE |  | FR1 | FR2 | FR1 + FR2 | FR1 | FR2 | FR1 + FR2 | FDD | TDD | FDD + TDD
[14 empty] | Overall |  | 6.4% (+1.4%) | 6.2% (+1.2%) | 9.1% (+4.1%) | 5% | 5% | 5%
[14 empty] | Number of WP items |  | 33 | 24 (+2) | 13 (+2) | 23 (+2) | 18 (+2) | 11 (+2) | 0 | 0 | 0
[14 empty] | Sum weight of WP items |  | 24.9 | 16.8 (+0.2) | 5.8 (+0.2) | 15.8 (+0.2) | 10.8 (+0.2) | 3.8 (+0.2) | 0 | 0 | 0
[14 empty] | Contribution by work plan analysis |  | 5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
52 |  | 38.508-1 | TBD | TBD | Update common testcase environment as per need. | TBD | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0%
TS 38.508-2: Common ICS
53 |  | 38.508-2 | TBD | TBD | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0%
TS 38.509: UE specific testing functions
54 |  | 38.509 | TBD | TBD | Update UE specific testing functions as per need. | TBD | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0%
NR RF/RRM
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
1 |  | 38.522 | 4.0 | Test case conditions and selection criteria | Add new ICS statements. | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0%
2 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0%
TS 38.533: RRM test cases
3 | Y | 38.533 | 4.7.1.1.X | EN-DC FR1 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): MR-DC Early measurement RSRP absolute accuracy, intra frequency carriers at FR1 | Ericsson | RAN5#92 (Aug-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
4 | Y | 38.533 | 4.7.1.2.X | EN-DC FR1-FR1 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): MR-DC Early measurement RSRP absolute accuracy, inter frequency NR carriers at FR1 | Ericsson | RAN5#92 (Aug-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
5 | Y | 38.533 | 4.7.2.X | EN-DC FR1 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): MR-DC Early measurement RSRQ absolute accuracy, intra frequency carriers at FR1 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
6 | Y | 38.533 | 4.7.2.2.X | EN-DC FR1-FR1 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): MR-DC Early measurement RSRQ absolute accuracy, inter frequency NR carriers at FR1 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
7 | Y | 38.533 | 5.7.1.X | EN-DC FR2 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): MR-DC Early measurement RSRP absolute accuracy, intra frequency NR carriers at FR2 | Ericsson | RAN5#92 (Aug-21) |  |  | 1 | 0% |  | 0% | [6 empty] | 0%
8 | Y | 38.533 | 5.7.1.Y | EN-DC FR2-FR2 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): MR-DC Early measurement RSRP absolute accuracy, inter frequency NR carriers at FR2 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% |  | 0% | [6 empty] | 0%
9 | Y | 38.533 | 5.7.1.Z | EN-DC FR1-FR2 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): MR-DC Early measurement RSRP absolute accuracy, NR carriers at FR1 and FR2 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% |  | 0% | [7 empty] | 0%
10 | Y | 38.533 | 5.7.2.X | EN-DC FR2 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): MR-DC Early measurement RSRQ absolute accuracy, intra frequency NR carriers at FR2 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% |  | 0% | [6 empty] | 0%
11 | Y | 38.533 | 5.7.2.Y | EN-DC FR2-FR2 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): MR-DC Early measurement RSRQ absolute accuracy, inter frequency NR carriers at FR2 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% |  | 0% | [6 empty] | 0%
12 | Y | 38.533 | 5.7.2.Z | EN-DC FR1-FR2 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): MR-DC Early measurement RSRQ absolute accuracy, NR carriers at FR1 and FR2 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% |  | 0% | [7 empty] | 0%
13 | Y | 38.533 | 6.7.1.1.X | NR SA FR1 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR Early measurement RSRP absolute accuracy, intra frequency NR carriers at FR1. TS:38.133 4.4 | Ericsson | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
14 | Y | 38.533 | 6.7.1.2.X | NR SA FR1-FR1 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR-NR Early measurement RSRP absolute accuracy, inter frequency NR carriers at FR1 TS:38.133 4.4 | Ericsson | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
15 | Y | 38.533 | 6.7.2.X | NR SA FR1 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR Early measurement RSRQ absolute accuracy, intra frequency NR carriers at FR1 TS:38.133 4.4 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
16 | Y | 38.533 | 6.7.2.2.X | NR SA FR1-FR1 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR-NR Early measurement RSRQ absolute accuracy, inter frequency NR carriers at FR1 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
17 | Y | 38.533 | 7.7.1.X | NR SA FR2 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR Early measurement RSRP absolute accuracy, intra frequency NR carriers at FR2 | Ericsson | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
18 | Y | 38.533 | 7.7.1.Y | NR SA FR2-FR2 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR-NR Early measurement RSRP absolute accuracy, inter frequency NR carriers at FR2 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
19 | Y | 38.533 | 7.7.1.3.X | NR SA FR1-FR2 SS-RSRP absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR-NR Early measurement RSRP absolute accuracy, NR carriers at FR1 and FR2 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% | [5 empty] | 0%
20 | Y | 38.533 | 7.7.2.X | NR SA FR2 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR Early measurement RSRQ absolute accuracy, intra frequency NR carriers at FR2 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
21 | Y | 38.533 | 7.7.2.Y | NR SA FR2-FR2 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR-NR Early measurement RSRQ absolute accuracy, inter frequency NR carriers at FR2 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
22 | Y | 38.533 | 7.7.2.Z | NR SA FR1-FR2 SS-RSRQ absolute measurement accuracy for idle/inactive mode CA/DC measurements | Test Purpose(s): NR-NR Early measurement RSRQ absolute accuracy, NR carriers at FR1 and FR2 | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% | [5 empty] | 0%
23 | Y | 38.533 | 4.5.3.X | EN-DC FR1 Direct SCell activation at SCell addition of known SCell | Test Purpose(s): MR-DC Direct SCell activation delay, NR carrier at FR1 | TBD | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
24 | Y | 38.533 | 5.5.3.X | EN-DC FR2 Direct SCell activation at SCell addition of known Scell | Test Purpose(s): MR-DC Direct SCell activation delay, NR carrier at FR2 | TBD | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% | [6 empty] | 0%
25 | Y | 38.533 | 6.5.3.X | NR SA FR1 Direct SCell activation at SCell addition of known Scell | Test Purpose(s): NR-NR Direct SCell activation delay, NR carriers at FR1 | TBD | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  |  | 0%
26 | Y | 38.533 | 7.5.3.X | NR SA FR2 - FR2 Direct SCell activation at SCell addition of known Scell | Test Purpose(s): NR-NR Direct SCell activation delay, NR carriers at FR2 | TBD | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
27 | Y | 38.533 | 7.5.3.Y | NR SA FR1 - FR2 Direct SCell activation at SCell addition of known Scell | Test Purpose(s): NR-NR Direct SCell activation delay, NR carriers at FR1 and FR2 | TBD | RAN5#93 (Nov-21) |  |  | 1 | 0% | 0% | [5 empty] | 0%
28 | Y | 38.533 | 4.5.6.X | EN-DC FR1 PSCell SCell dormancy switch of single FR1 SCell outside active time | Test Purpose(s): MR-DC SCell dormancy outside active time switching delay, NR carrier at FR1 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
29 | Y | 38.533 | 4.5.6.Y | EN-DC FR1 PSCell SCell dormancy switch of two FR1 SCells inside active time | Test Purpose(s): MR-DC SCell dormancy inside active time switching delay, NR carriers at FR1 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
30 | Y | 38.533 | 5.5.6.X | EN-DC FR2 PSCell SCell dormancy switch of single FR2 SCell inside active time | Test Purpose(s): MR-DC SCell dormancy inside active time switching delay, NR carriers at FR2 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% |  | 0% | [6 empty] | 0%
31 | Y | 38.533 | 5.5.6.Y | EN-DC FR1 PSCell SCell dormancy switch of two FR2 SCells inside active time | Test Purpose(s): MR-DC SCell dormancy inside active time switching delay, NR carriers at FR1 and FR2 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% |  | 0% | [7 empty] | 0%
32 | Y | 38.533 | 6.5.6.X | NR SA FR1 PSCell SCell dormancy switch of single FR1 SCell outside active time | Test Purpose(s): NR-NR SCell dormancy outside active time switching delay, NR carriers at FR1 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
33 | Y | 38.533 | 6.5.6.Y | NR SA FR1 PSCell SCell dormancy switch of two FR1 SCells inside active time | Test Purpose(s): NR-NR SCell dormancy inside active time switching delay, NR carriers at FR1 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
34 | Y | 38.533 | 7.5.6.X | NR SA FR2 PSCell SCell dormancy switch of single FR2 SCell inside active time | Test Purpose(s): NR-NR SCell dormancy inside active time switching delay, NR carriers at FR2 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  |  | 0%
35 | Y | 38.533 | 7.5.6.Y | NR SA FR1 PSCell SCell dormancy switch of two FR2 SCells outside active time | Test Purpose(s): NR-NR SCell dormancy inside active time switching delay, NR carriers at FR1 and FR2 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% | [5 empty] | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
55 |  | 38.903 | TBD | TBD | Define TT and MU for the RRM testcases | TBD | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Layer 2
36 | Y | 38.523-1 | 7.1.1.8.2 | Dormant Bandwidth Part (BWP) operation UL/DL | Test Purpose(s): SCell having dormant BWP, BWP switching | TBD | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
RRC
|  | 38.523-1 | 8.1.5.11 | Idle/Inactive Measurements | New sub-clause header |  | RAN5#92 (Aug-21) |  |  | 0
37 | Y | 38.523-1 | 8.1.5.11.1 | Idle/Inactive Measurements / Idle mode / SIB1 configuration | Test Purpose(s): NR-NR Early measurement reporting, Idle mode, Measurement configuration through SIB1. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
38 | Y | 38.523-1 | 8.1.5.11.2 | Idle/Inactive Measurements / Idle mode / RRCRelease configuration | Test Purpose(s): NR-NR Early measurement reporting, Idle mode, Measurement configuration through RRCRelease message. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
39 | Y | 38.523-1 | 8.1.5.11.3 | Idle/Inactive Measurements / Inactive mode / SIB1 configuration | Test Purpose(s): NR-NR Early measurement reporting, Inactive mode, Measurement configuration through SIB1. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
40 | Y | 38.523-1 | 8.1.5.11.4 | Idle/Inactive Measurements / Inactive mode / RRCRelease configuration | Test Purpose(s): NR-NR Early measurement reporting, Inactive mode, Measurement configuration through RRCRelease message. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#92 (Aug-21) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
|  | 38.523-1 | 8.2.6.3 | Idle/Inactive Measurements | New sub-clause header |  | RAN5#93 (Nov-21) |  |  | 0
41 | Y | 38.523-1 | 8.2.6.3.1 | Idle/Inactive Measurements / Idle mode / EN-DC / SIB2 & SIB24 configuration | Test Purpose(s): LTE-NR Early measurement reporting, Idle mode, Measurement configuration through LTE SIB2 and LTE SIB24. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0% | 0%
42 | Y | 38.523-1 | 8.2.6.3.2 | Idle/Inactive Measurements / Idle mode / EN-DC / RRCConnectionRelease configuration | Test Purpose(s): LTE-NR Early measurement reporting, Idle mode, Measurement configuration through RRCConnectionRelease. TS:38.331 5.7.8 | Nokia, Nokia Shanghai Bell | RAN5#93 (Nov-21) |  |  | 1 | 0% |  | 0% | [5 empty] | 0% | 0%
43 | Y | 38.523-1 | 8.1.1.4.4 | RRC resume / Suspend-Resume / RRC reconfiguration / Active MCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell while resuming from inactive state after receiving RRCResume message. Intra-band contiguous carriers. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 5% (+5%) | 5% (+5%) |  |  |  | 5% | 5%
64 | Y | 38.523-1 | 8.1.1.4.5 | RRC resume / Suspend-Resume / RRC reconfiguration / Active MCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell while resuming from inactive state after receiving RRCResume message. Intra-band non-contiguous carriers. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 5% (+5%) | 5% (+5%) |  |  |  | 5% | 5%
65 | Y | 38.523-1 | 8.1.1.4.6 | RRC resume / Suspend-Resume / RRC reconfiguration / Active MCG SCell addition / Inter-band CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell while resuming from inactive state after receiving RRCResume message. Inter-band carriers. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 5% (+5%) | 5% (+5%) |  |  |  | 5% | 5% | 5%
44 | Y | 38.523-1 | 8.1.1.4.7 | RRC resume / Suspend-Resume / RRC setup / Active SCG SCell addition / Intra-band Contiguous CA | NR-CA Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCResume message. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 5% (+5%) | 5% (+5%) |  |  |  | 5%
66 | Y | 38.523-1 | 8.1.1.4.8 | RRC resume / Suspend-Resume / RRC setup / Active SCG SCell addition / Intra-band non-Contiguous CA | NR-CA Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCResume message. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 5% (+5%) | 5% (+5%) |  |  |  | 5%
67 | Y | 38.523-1 | 8.1.1.4.9 | RRC resume / Suspend-Resume / RRC setup / Active SCG SCell addition / Inter-band CA | NR-CA Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCResume message. TS:38.331 5.3.13.4, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#93 (Nov-21) |  |  | 1 | 5% (+5%) | 5% (+5%) |  |  |  | 5%
|  | 38.523-1 | 8.2.7 | RRC resume | New sub-clause header |  | RAN5#94 (Feb-22) |  |  | 0
45 | Y | 38.523-1 | 8.2.7.1 | RRC resume / Suspend-Resume / RRC reconfiguration / EN-DC / Active SCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): MR-DC Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCConnectionResume message. Intra-band contiguous carriers. TS:36.331 5.3.3.4a; TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#94 (Feb-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
56 | Y | 38.523-1 | 8.2.7.2 | RRC resume / Suspend-Resume / RRC reconfiguration / EN-DC / Active SCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): MR-DC Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCConnectionResume message. Intra-band non-contiguous carriers. TS:36.331 5.3.3.4a; TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#94 (Feb-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
57 | Y | 38.523-1 | 8.2.7.3 | RRC resume / Suspend-Resume / RRC reconfiguration / EN-DC / Active SCG SCell addition / Inter-band CA | Test Purpose(s): MR-DC Direct SCell activation, adding active SCG SCell while resuming from inactive state after receiving RRCConnectionResume message. Inter-band carriers. TS:36.331 5.3.3.4a; TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#94 (Feb-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0% | 0%
46 | Y | 38.523-1 | 8.1.2.1.5.4 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active MCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
58 | Y | 38.523-1 | 8.1.2.1.5.5 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active MCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band non-contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
59 | Y | 38.523-1 | 8.1.2.1.5.6 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active MCG SCell addition / Inter-band CA | Test Purpose(s): NR-CA Direct SCell activation, adding active MCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Inter-band carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Ericsson | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
47 | Y | 38.523-1 | 8.1.2.1.5.7 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active SCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | Motorola Mobility | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
60 | Y | 38.523-1 | 8.1.2.1.5.8 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active SCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): NR-CA Direct SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Intra-band non-contiguous carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0%
61 | Y | 38.523-1 | 8.1.2.1.5.9 | NR CA / RRC reconfiguration / SCell addition / modification / release / Success / Active SCG SCell addition / Inter-band CA | Test Purpose(s): NR-CA Direct SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRCReconfiguration message. Inter-band carriers. TS:38.331 5.3.5.3, 5.3.5.5; TS:38.321 5.9 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  |  |  | 0% | 0%
48 | Y | 38.523-1 | 8.2.4.1.1.4 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Active SCG SCell addition / Intra-band Contiguous CA | Test Purpose(s): MR-DC Direct NR SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRC(Connection)Reconfiguration message. Intra-band contiguous carriers. TS:36.331 5.3.5.3; TS:38.331 5.3.5.3; TS38.321 5.9 | Motorola Mobility | RAN5#94 (Feb-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
62 | Y | 38.523-1 | 8.2.4.1.1.5 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Active SCG SCell addition / Intra-band non-Contiguous CA | Test Purpose(s): MR-DC Direct NR SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRC(Connection)Reconfiguration message. Intra-band non-contiguous carriers. TS:36.331 5.3.5.3; TS:38.331 5.3.5.3; TS38.321 5.9 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0%
63 | Y | 38.523-1 | 8.2.4.1.1.6 | NR CA / NR SCell addition / modification / release / Success / EN-DC / Active SCG SCell addition / Inter-band CA | Test Purpose(s): MR-DC Direct NR SCell activation, adding active SCG SCell during UE cell reconfiguration after receiving RRC(Connection)Reconfiguration message. Inter-band carriers. TS:36.331 5.3.5.3; TS:38.331 5.3.5.3; TS38.321 5.9 | TBD | RAN5#94 (Feb-22) |  |  | 1 | 0% |  | 0% | [5 empty] | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
49 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add new ICS statements. | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) |  |  | 0.1 | 27.5% (+27.5%) | 55% (+55%) | 0% |  |  | 35% | 30% | 100% | 0% | 0% | 0%
50 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 | Nokia, Nokia Shanghai Bell | RAN5#94 (Feb-22) |  |  | 0.1 | 27.5% (+27.5%) | 55% (+55%) | 0% |  |  | 35% | 30% | 100% | 0% | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
51 |  | 38.523-3 | TBD | TBD | Update test environment if necessary. | TBD | RAN5#94 (Feb-22) |  |  | 0.1 | 0% | 0% |  |  |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.