## Cover sheet
RAN5 meeting #91e | [10 empty] | R5-214732
Electronic meeting, 16th August 2021 - 27th August 2021
Agenda Item: | 7.4.2
Source: | Qualcomm
Title: | WP UE Conformance Test Aspects - Rel-16 Private Network Support for NG-RAN
Work item code: | NG_RAN_PRN_Vertical_LAN-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 45% (+45%) | 2 (+2) | 14 (+14)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 45.2% (+45.2%) | 2 (+2) | 14 (+14)
FR1 |  | 46% (+46%) | 6 (+6) | 14 (+14)
FR2 |  | 44.5% (+44.5%) | 2 (+2) | 14 (+14)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
Common ICS | 38.508-2 | 100% (+100%) |  |  | 100% (+100%) |  |  | 100% (+100%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 33.2% (+33.2%) | 2 (+2) | 14 (+14) | 34.2% (+34.2%) | 6 (+6) | 14 (+14) | 32.1% (+32.1%) | 2 (+2) | 14 (+14)
Applicability Protocol test cases | 38.523-2 | 40% (+40%) |  |  | 40% (+40%) |  |  | 40% (+40%)
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-201152 | UE Conformance Test Aspects - Private Network Support for NG-RAN
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Private Network Support for NG-RAN | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NG_RAN_PRN_Vertical_LAN-UEConTest
WP Scope: |  | <WP Scope description> | [12 empty] | vs Area
WP Resp: |  | Yogesh Tugnawat |  |  | Yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 46% (+46%) | 44.5% (+44.5%)
[14 empty] | 23 (+23) | 23 (+23)
[14 empty] | 25.4 (+25.4) | 25.4 (+25.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4, 6 | Introduction of General and Signaling Test Environment for Rel-16 Private Network Tests | SNPN, PNI-NPN cell definitions, ASN.1 updates (SIB1, SIB10, other messages), USIM updates Cell Definitions - SNPN, CAG Generic Procedure SI Combinations | Qualcomm | RAN5#92 (Aug-21) | R5-211465 R5-211548 R5-211466 R5-213573 R5-213574 R5-214900 |  | 2 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | TBD | Introduction of common implementation conformance statements for Rel-16 Private Network Tests T. | CAG PICS Resolve Applicability for SNPN | Qualcomm | RAN5#91-e (May-21) | R5-213575 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Idle Mode
29 |  | 38.523-1 | 6.5 | SNPN and CAG Selection | New sub-clause header
30 |  | 38.523-1 | 6.5.1 | SNPN Only Selection | New sub-clause header |  |  |  |  | 0
5 | Y | 38.523-1 | 6.5.1.1 | SNPN Selection in Manual Mode | 23.122 cl 4.9.3 (1) with { UE in Manual network/SNPN selection mode and an SNPN cell is available for which an entry does not exist in the "list of subscriber data" } ensure that { when { UE is switched on or return to coverage } then { UE does not indicate to the user any available SNPNs } } (2) with { UE in Manual network/SNPN selection mode } ensure that { when { an SNPN cell is available for which an entry exists in the "list of subscriber data" } then { UE indicates to the user that an SNPN is available and user selects the SNPN } } (3) with { UE in Manual network/SNPN selection mode and has registered on an SNPN selected by the user } ensure that { when { an SNPN cell is available for which an entry exists in the "list of subscriber data" } then { UE does not automatically register on the SNPN cell until the user selects automatic SNPN selection mode } } | Qualcomm | RAN5#96 (May-22) | R5-213578 R5-214894 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
6 | Y | 38.523-1 | 6.5.1.2 | SNPN Selection in Automatic Mode | 23.122 cl 4.9.3 (1) with { UE in Automatic SNPN selection mode and SNPN cell is available for which an entry does not exist in the "list of subscriber data" } ensure that { when { UE is switched on or return to coverage } then { UE does not only select the SNPN cell and continues searching for an allowable SNPN Cell } } (2) with { UE in Automatic SNPN selection mode and a Registered SNPN cell along with another better ranked allowable SNPN cell becomes available } ensure that { when { UE is switched on or return to coverage } then { UE selects the Registered SNPN cell and UE attempts a Registration on the selected cell } } (3) with { UE in Automatic SNPN selection mode and Registration on a SNPN cell is unsuccessful} ensure that { when { UE continues searching for a allowable SNPN Cell and a new allowable SNPN cell becomes available } then { the UE registers on the new SNPN cell } } | Qualcomm | RAN5#96 (May-22) | R5-213576 R5-214895 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
7 | Y | 38.523-1 | 6.5.1.3 | SNPN / User Reselection in Automatic Mode | 23.122 cl 4.9.3 |  | RAN5#96 (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
|  | 38.523-1 | 6.5.2 | CAG (Closed Acccess Group) | New sub-clause header |  |  |  |  | 0
9 | Y | 38.523-1 | 6.5.2.1 | CAG Selection in Manual Mode | 23.122 cl 4.4.3 (1) with { UE in Manual network selection mode and provided with CAG information list } ensure that { when { there exists an entry with the PLMN ID of the PLMN in the "CAG information list" and the CAG-ID is included in the "Allowed CAG list" } then { UE manually selects the CAG cell } } (2) with { UE in Manual network selection mode and PLMN ID of the PLMN in the "CAG information list" and the CAG-ID are not included in the "Allowed CAG list" } ensure that { when { the available CAG cell broadcasts that the PLMN allows a user to manually select the CAG-ID } then { UE manually selects the CAG cell that is outside the UE's Allowed CAG list} } (3) with { UE in Manual network selection mode } ensure that { when { there exists an entry for the presented PLMN in the "CAG information list" and the entry includes an "indication that the MS is only allowed to access 5GS via CAG cells" } then { UE manually selects the CAG cell } | Qualcomm | RAN5#96 (May-22) | R5-213579 R5-214747 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
10 | Y | 38.523-1 | 6.5.2.2 | CAG Selection in Automatic Mode | 23.122 cl 4.4.3 (1) with { UE in Automatic network selection mode and provisioned with an empty "CAG information list” } ensure that { when { UE is switched on or returned to coverage, and a cell which is not a CAG cell becomes available} then { UE selects the cell } } (2) with { UE in Automatic network selection mode provisioned with a "CAG information list” } ensure that { when { UE is switched on or returned to coverage, and a CAG cell with a CAG-ID present in the "Allowed CAG list" becomes available} then { UE selects the CAG cell } } (3) with { UE in Automatic network selection mode provisioned with a "CAG information list” } ensure that { when { UE is switched on and a cell which is not a CAG cell becomes available, and there is an entry with the PLMN ID of the PLMN in the "CAG information list" but the "indication that the MS is only allowed to access 5GS via CAG cells" is not included in the entry} then { UE selects the cell } } | Qualcomm | RAN5#96 (May-22) | R5-213577 R5-214746 |  | 1 | 95% (+95%) | 95% (+95%) |  | 100% | 90%
11 | Y | 38.523-1 | 6.5.2.3 | CAG / Limited Service / No Suitable cell | TS 23.122 cl 3.5 |  | RAN5#96 (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
12 | Y | 38.523-1 | 6.5.2.4 | CAG / cell reselection / Within allowed CAG/ non-CAG cell to CAG cell | FFS |  | RAN5#96 (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
13 | Y | 38.523-1 | 6.5.2.5 | CAG/ cell selection/reselection / allowed CAG list empty | FFS |  | RAN5#96 (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
14 | Y | 38.523-1 | 6.5.2.6 | CAG/ Cell Reservation | FFS |  | RAN5#96 (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-1 | 6.5.x | SNPN only cell Selection, RRC_INACTIVE | New sub-clause header |  | RAN5#96 (May-22) |  | Sub tasks to be identified: All Relevant test cases fron NG RAN 6.1.2 and 6.4 replace the cells with SNPN cells | 1 | 0% | 0% |  | 0% | 0%
RRC
17 |  | 38.523-1 | 8.1.7 | Non-public networks | New sub-clause header |  |  |  |  | 0
19 |  | 38.523-1 | 8.1.7.1 | Measurement for self-optimized networks | New sub-clause header |  |  |  |  | 0
20 | Y | 38.523-1 | 8.1.7.1.1 | Measurement configuration control and reporting / CGI reporting of NR NPN cell | TS 38.331, cl 5.5.5.1 |  | RAN5#96 (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
NAS
27 |  | 38.523-1 | 9.1.11 | SNPN / Mobility management aspects | New sub-clause header |  |  |  |  | 0
21 | Y | 38.523-1 | 9.1.11.1 | SNPN / Initial registration / Rejected / Temporarily not authorized for this SNPN | TS 24.501 clauses 5.5.1.2.5, 5.1.3.2.1, 5.1.3.2.2, TS 23.122 clause 4.9.3.0 (1) with { UE in Automatic SNPN selection mode and a SNPN cell is available for which an entry exists in the "list of subscriber data" and the UE in 5GMM-REGISTERED-INITIATED state } ensure that { when { the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #74 (Temporarily not authorized for this SNPN) } then { the UE deletes any 5G-GUTI, last visited registered TAI and ngKSI, and stores the SNPN identity in the "temporarily forbidden SNPNs" } } (2) with { the initial registration request cannot be accepted by the network } ensure that { when { the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #74 (Temporarily not authorized for this SNPN) } then { The UE stores the SNPN identity in the "temporarily forbidden SNPNs" and does not remove it atleast until 60 minutes or the UE is switched off } } (3) with { the UE is in 5GMM-DEREGISTERED.PLMN-SEARCH state and the SNPN identity of the current cell belongs to the list of "temporarily forbidden SNPNs" } ensure that { when { the UE enters a cell belonging to a SNPN cell for which an entry exists in the "list of subscriber data" } then { the UE attempts registration on the SNPN cell } } | Qualcomm | RAN5#92 (Aug-21) | R5-216273 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
22 | Y | 38.523-1 | 9.1.11.2 | SNPN / Initial registration / Rejected / Permanently not authorized for this SNPN | TS 24.501 clauses 5.5.1.2.5, 5.1.3.2.1, 5.1.3.2.2, TS 23.122 clause 4.9.3.0 (1) with { UE in Automatic SNPN selection mode and a and SNPN cell is available for which an entry exists in the "list of subscriber data" and the UE in 5GMM-REGISTERED-INITIATED state } ensure that { when { the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #75 (Permanently not authorized for this SNPN) } then { the UE deletes any 5G-GUTI, last visited registered TAI and ngKSI, and store the SNPN identity in the "permanently forbidden SNPNs" } } (2) with { the UE is in 5GMM-DEREGISTERED.PLMN-SEARCH state } ensure that { when { User manually selects the SNPN cell which belongs to the "permanently forbidden SNPNs" list } then { the UE attempts registration on the SNPN cell } } | Qualcomm | RAN5#92 (Aug-21) | R5-215671 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
26 | Y | 38.523-1 | 9.1.11.3 | SNPN / EAP based primary authentication and key agreement / EAP-AKA' related procedures |  |  | RAN5#96 (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
28 |  | 38.523-1 | 10.1.7 | SNPN / Session management aspects | New sub-clause header |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
24 | Y | 38.523-1 | 10.1.7.1 | SNPN / Network-requested PDU session release / Accepted / Insufficient resources / T3396, Accepted / Insufficient resources for specific slice and DNN / T3584 | 24.501, 6.2.7 |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
32 |  | 38.523-1 | 11.3 | Unified Access Control (UAC) | Existing sub-clause header |  |  |  | Sub tasks to be identified | 1 | 0% | 0% |  | 0% | 0%
15 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Qualcomm | RAN5#94 (Feb-22) | R5-212808 R5-216274 |  | 1.4 | 40% (+40%) | 40% (+40%) |  | 40% | 40%
TS 38.523-3: Protocol test suites (TTCN)
3 |  | 38.523-3 | TBD | Introduction of General and Signaling Test Environment for SNPN and PNI-NPN | <Describe task> | MCC TF160 | RAN5#93 (May-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
Overall WP completion
16 |  |  |  | Overall Definition and scope of WI |  |  | RAN5#96 (May-22) |  |  | 1 | 90% (+90%) | 90% (+90%) |  | 90% | 90%
31 |  | 38.523-1 | TBD | Scoping of NR option 2 Rel-15 applicable TCs for SNPN Only UE |  |  | RAN5#96 (May-22) | R5-213408 R5-214736 |  | 2 | 25% (+25%) | 25% (+25%) |  | 25% | 25%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.