## Slide 1: RAN Chair's input for joint CT/RAN/SA session at TSG #94-e about Rel-18
Source: RAN Chair
RP-212745
3GPP TSG RAN#94-e
6th – 17th, December 2021
Agenda: 6.1

## Slide 2: Outline
Approved RAN Rel-18 package
Detailed list of RAN Rel-18 projects with potential interaction with CT/SA

## Slide 3: Approved RAN Rel-18 Package 1/2
RAN Rel-18 package is approved in RP-213469
Project | TU estimate
NR-MIMO Evolution | ~3 TUs
AI/ML - Air Interface | SI only, ~3 TUs
Evolution of duplex operation | SI only, ~2 TUs
NR Sidelink Evolution | ~2 TUs
Positioning Evolution | 9 month SI, followed by 9 month WI, ~3 TUs
RedCap Evolution | 6 month SI, followed by 12 month WI, ~1 TU
Network energy savings | 9 month SI, followed by 9 month WI, ~1-2 TUs
Further UL coverage enhancement | ~1 TU for 12 months
Smart Repeater | 6 month SI, followed by 6 month WI, ~1 TU
DSS | ~1 TU for 6 months
Low power WUS | SI only, ~1 TU for 12 months
CA Enhancements | ~1 TU for 9 months
RAN1-led Projects
Project | TU estimate
Mobility Enhancements | ~2 TUs
Enhancements for XR | 6 month (RAN2)/9 month (RAN1) SI, followed by WI, ~2 TUs
Sidelink Relay Enhancements | ~1.5 TUs
NTN (Non-Terrestrial Networks) evolution - NR | ~1 TU
NTN (Non-Terrestrial Networks) evolution - IoT | ~1 TU
Evolution for MBS | ~0.5 TU
UAV (Uncrewed Aerial Vehicle) | ~1 TU
Multiple SIM (MUSIM) Enhancements | ~1 TU for 9 months
In-Device Co-existence (IDC) Enhancements | ~1 TU for 9 months
Small data | ~0.5 TU for 9 months
RAN2-led Projects
Legend - XX: WI; XX: SI only; XX: SI followed WI

## Slide 4: Approved RAN Rel-18 Package 2/2
RAN Rel-18 package is approved in RP-213469
RAN3-led Projects
RAN4-led Projects
Project | TU estimate
Additional topological improvements – IAB/VMR | ~1-1.5TUs
AI/ML for NG-RAN WI | First 12 month, ~2 TUs
AI/ML for NG-RAN SI | Last 6 month, ~2 TUs
SON/MDT Enhancements | ~1 TU
QoE Enhancements | ~1 TU
The following RAN4-led project is to be approved in RAN#94-e:
  Bandwidths lower than 5 MHz in dedicated spectrum
Other RAN4-led projects are to be approved in March’2022
Legend - XX: WI; XX: SI only; XX: SI followed WI
Note: Subsequently, an additional RAN3-led SI was endorsed, a 0.5TU in one quarter project: Study on enhancement for resiliency of gNB-CU

## Slide 5: List of RAN Rel-18 projects with potential interaction with CT/SA 1/5
Tdoc# | Title | Potential Interaction with CT/SA
RP-213598 | MIMO Evolution for Downlink and Uplink | None identified so far
RP-213599 | Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR Air Interface | None identified so far
RP-213591 | Study on Evolution of NR Duplex Operation | None identified so far
To be approved | NR sidelink evolution | None identified so far
RP-213588 | Study on expanded and improved NR positioning | From “Objective” Study of positioning architecture and signalling procedures (e.g. configuration, measurement reporting, etc) to enable sidelink positioning covering both UE based and network based positioning [RAN2, including coordination and alignment with RAN3 and SA2 as required] From “Aspects that involve other WGs” Study of positioning architecture and signalling procedures to enable sidelink positioning covering both UE based and network based positioning may require coordination and alignment with SA2.
RP-213661 | Study on further NR RedCap UE complexity/cost reduction | None identified so far
RP-213554 | Study on network energy savings | From “Aspects that involve other WGs” The study should coordinate with SA5 as needed, e.g. on how the potential energy saving techniques integrate 3GPP management system
RP-213579 | Further NR coverage enhancements | None identified so far
RP-213592 | Study on NR Smart Repeaters | From “Objective” Study the following aspects of smart repeater management Identification and authorization of smart repeaters [RAN2, RAN3] NOTE2: Coordination with SA3 may be needed.

## Slide 6: List of RAN Rel-18 projects with potential interaction with CT/SA 2/5
Tdoc# | Title | Potential Interaction with CT/SA
RP-213575 | Enhancement of NR Dynamic spectrum sharing (DSS) | None identified so far
RP-213645 | Study on low-power Wake-up Signal and Receiver for NR | None identified so far
RP-213577 | Multi-carrier enhancements for NR | None identified so far
RP-213565 | Further NR Mobility Enhancements | None identified so far
RP-213587 | Study on XR Enhancements for NR | From “Objective” The study is to be based on Release 17 TR 38.838, on corresponding Release 17 work from SA4 (as per SP-210043) and on Release 18 work from SA2 (as per SP-211166). From “Aspects that involve other WGs” SA2 is involved for determination of XR specific information made available in the network and the UE.
RP-213585 | NR sidelink relay enhancements | From “Objective” Specify mechanisms to support single-hop Layer-2 and Layer-3 UE-to-UE relay (i.e., source UE -> relay UE -> destination UE) for unicast [RAN2, RAN3, RAN4]. A. Common part for Layer-2 and Layer-3 relay to be prioritized until RAN#98 […..] Signalling support for Relay and remote UE authorization if SA2 concludes it is needed [RAN3] B. Layer-2 relay specific part [……] QoS handling if needed, subject to SA2 progress [RAN2] Note 3C: Support of Layer-3 UE-to-Network relay in multi-path scenario is assumed to have no RAN impact and the work and solutions are subject to SA2 to progress. From “Aspects that involve other WGs” SA2/CT1 have to capture impacts of NR Sidelink Relay on Discovery/PC5-S and CN. SA3 has to capture impacts of NR Sidelink Relay on security related part.

## Slide 7: List of RAN Rel-18 projects with potential interaction with CT/SA 3/5
Tdoc# | Title | Potential Interaction with CT/SA
To be approved | NR NTN (Non-Terrestrial Networks) enhancements | From “Objective” • Improved performance of low-rate codecs in link budget limited situation including reducing RAN protocol overhead for VoNR [RAN2,RAN1] [Liaise with SA2/SA4 as necessary] From “Aspects that involve other WGs” Possible cooperation/alignment with: • SA2, SA3 and SA3-LI with respect to ‘Network verified UE location’ and the possible impact on regulatory requirements (e.g. LI, PWS,…). • SA2 & SA4 with respect to ‘coverage enhancement’ and in particular the potential low-rate codecs performance enhancements for in link budget limited context.
RP-213596 | New WID on IoT NTN enhancements | From “Objective” Further enhancement to discontinuous coverage This objective will be revisited at RAN#96e / June 2022, subject to Rel-17 IoT-NTN status on discontinuous coverage at RAN#96e, SA#94e, CT#95e. From “Aspects that involve other WGs” Possible cooperation/alignment with: SA2 and CTx WGs with respect to the improvements related to the operation under discontinuous coverage: this will be revisited at RAN#96e / June 2022 depending on the status on the above objective on further enhancement to discontinuous coverage.
RP-213600 | WI on NR Support for UAV | From “Objective” Specify the signaling to support subscription-based aerial-UE identification [RAN3/SA2 interaction/RAN2] Study and specify, if needed, enhancements for UAV identification broadcast [RAN2, SA2]. Note: This description is a placeholder for a more detailed objective to be drafted once SA2 will have concluded their study on the architectural aspects. From “Aspects that involve other WGs” SA2: Subscription-based aerial-UE identification Enhancements for UAV identification

## Slide 8: List of RAN Rel-18 projects with potential interaction with CT/SA 4/5
Tdoc# | Title | Potential Interaction with CT/SA
RP-213584 | WI on Dual Tx/Rx MUSIM | None identified so far
RP-213589 | In-Device Co-existence (IDC) enhancements for NR and MR-DC | None identified so far
RP-213583 | Mobile Terminated-Small Data Transmission (MT-SDT) for NR | None identified so far
RP-213568 | Enhancements of NR Multicast and Broadcast Services | From “Objective” Note: collaboration with SA2 is expected in due course for the above objectives (That is, i) Specify support of multicast reception by UEs in RRC_INACTIVE [and RRC_IDLE] state; ii) Study and if necessary, specify enhancements to improve the resource efficiency for MBS reception in RAN sharing scenarios)
RP-213601 | Mobile IAB | From “Aspects that involve other WGs” Alignment and coordination with Rel-18 SA2 work on VMR should be considered, if needed.
RP-213602 | Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | From “Objective” Note: On security impacts, coordination with SA3 when needed. On OAM aspects, coordination with SA5 when needed.
RP-213553 | Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | From “Objective” If needed, co-operate with RAN1, SA2, SA5, CT4.

## Slide 9: List of RAN Rel-18 projects with potential interaction with CT/SA 5/5
Tdoc# | Title | Potential Interaction with CT/SA
RP-213594 | Enhancement on NR QoE management and optimizations for diverse services | From “Objective” Support for new service type, such as AR, MR, MBS and other new service type defined or to be supported by SA4. Support RAN-visible parameters for the additional service types, and the existing service if needed, and the coordination with SA4 is needed[RAN3, RAN2]. Specify the new service and the existing service defined or to be supported by SA4, combined with high mobility scenarios, e.g., High Speed Trains. […] Other objectives: Note 3: If needed, co-operate with other working groups, e.g. SA4/SA5/SA2/CT1. From “Aspects that involve other WGs” TSG SA4: for Codec aspects TSG SA5: for the QoE measurement configuration and reporting aspects TSG SA2: for the QoE measurement related procedures aspects TSG CT1: for the UE internal handling between its Access Stratum and upper layers
RP-213603 | NR support for dedicated spectrum less than 5MHz for FR1 | None identified so far
To be approved | Study on enhancement for resiliency of gNB-CU | None identified so far