## Slide 1: Status Report RAN WG4
3GPP RAN WG4 Chair
Xizeng Dai
3GPP TSG-RAN Meeting #97-e
Electronic Meeting, September 12 – 16, 2022
Agenda Item: 5.4
RP-221892

## Slide 2: Summary (1/2)
In Q3 2022, RAN4 had one e-meetings, i.e., RAN4#104-e
  Totally 113 email threads were arranged with a moderator per thread in three parallel sessions (Main, RRM, BSRF_Demod_Test). 4800+ emails.
  28 GTW calls (18 GTW for Main + BSRF_Demod_Test sessions and 10 for RRM sessions) were used to treat critical or controversial topics.
    The overtime for each GTW is less than half an hour except for one GTW to complete Rel-17 controversial topic for which there is 40 min overtime.
Rel-15 and Rel-16 maintenance
  Tdoc number for Rel-15/16 maintenance was 566, which accounted for 15.6% of total submitted contributions in Q3 2022 (16.7% in last quarter).
Rel-17 WI
  Core part of Rel-17 extended WIs
    NR_ext_to_71GHz can be closed, although some company have different views. More discussions are needed.
    NR_RAIL_EU_900MHz is closed (Perf part was completed in June 2022).
  Performance part of Rel-17 WIs: 17 WI can be closed, 5 WIs need be extended by one quarter
The Perf. parts of following WIs are closed
The Perf parts to be extended to Dec2022
The Perf parts with target completion date Dec 2022
NR_SL_enh-Perf
NR_pos_enh-Perf
NR_UE_pow_sav_enh-Perf
LTE_NR_DC_enh2-Perf
NR_IAB_enh-Perf
NR_SL_relay-Perf
NR_demod_enh2
NR_MIMO_OTA-Perf *
NR_FR1_TRP_TRS-Perf
NR_FeMIMO-Perf (RRM, Demod)
NR_cov_enh-Perf (Demod)
NR_IIOT_URLLC_enh-Perf (Demod)
NR_SmallData_INACTIVE-Perf (RRM)
NR_repeaters-Perf (BS RF conformance)
NR_ext_to_71GHz
NR_redcap-Perf
NR_NTN_solutions
NR_HST_FR1_enh-Perf
NR_HST_FR2-Perf
NR_RF_FR1_enh
NR_RF_FR2_req_enh2-Perf
NR_RRM_enh2-Core
NR_MG_enh-Perf
NR_6GHz-Perf
NB_IOTenh4_LTE_eMTC6-Perf
* Some company had different views and discussions are needed
Notes: 404 for Rel-15 9%
381 for Rel-16 8.1%
838 for Rel-17 spectrum related
1475 for Rel-17 non-spectrum related

## Slide 3: Summary (2/2)
Rel-18 WI/SI
  RAN4 starts working on Rel-18 SIs and Rel-18 WI core parts from Q3 2022
    Black color: items which have been started. Gray color: items to be started in future meetings.
FS_NR_pos_enh2
FS_NR_duplex_evo
FS_NR_AIML_Air (start from Q2/23)
FS_NR_LPWUS (start from Q1/23)
NR_DSS_enh (start from Q4/23)
NR_MC_enh
NR_cov_enh2 (start from Q4/22)
NR_MIMO_evo_DL_UL (start from Q1/23)
NR_SL_enh2 (start from Q1/23)
NR_Mob_enh2
NR_DualTxRx_MUSIM
NR_SL_relay_enh (start from Q1/23)
NR_IDC_Enh-Core (start from Q2/23)
NR_NTN_enh (start from Q4/22)
NR_mobile_IAB (start from Q1/23)
IoT_NTN_enh (start from Q1/23)
FS_NR_700800900_combo_enh
DC_R18_1BLTE_1BNR_2DL2UL
DC_R18_2BLTE_1BNR_3DL2UL
DC_R18_xBLTE_1BNR_yDL2UL
DC_R18_xBLTE_2BNR_yDL2UL-Core
DC_R18_xBLTE_yBNR_zDL2UL
DC_R18_xBLTE_yBNR_zDL3UL
NR_CA_R18_Intra
NR_CADC_R18_2BDL_xBUL
NR_CADC_R18_3BDL_xBUL
NR_CADC_R18_yBDL_xBUL
NR_SUL_combos_R18
LTE_CA_R18_xBDL_yBUL
LTE_NR_HPUE_FWVM_R18
NR_RAIL_HPUE_n100_n101-Core
NR_LTE_V2X_PC5_combos_R18
NR_unlic_enh
DL_intrpt_combos_TxSW_R18
NR_6GHz_add_bands
NR_bands_UL_MIMO_R18
NR_600MHz_APT-Core
LTE_terr_bcast_bands_part2
LTE_TDD_1670_1675MHz
LTE_CA_intra_B8-Core
FS_NR_eff_BW_util
FS_NR_FR2_OTA_enh
FS_SimBC
FS_NR_BS_RF_evo
NR_FR1_lessthan_5MHz_BW (start next year)
NR_ENDC_RF_FR1_enh2
NR_RF_FR2_req_Ph3
NR_FR2_multiRX_DL
NR_HST_FR2_enh (start from Q4/22)
NR_RRM_enh3-Core
NR_MG_enh2
NR_LTE_EMC_enh (start from Q4/22)
NR_ATG
NonCol_intraB_ENDC_NR_CA
NR_demod_enh3-Perf (start from Q4/22)
LTE_NBIOT_eMTC_NTN_req
RAN1~3 led WI/SI (RAN4 work needed)
RAN4 led non-spectrum WI/SI
RAN4 led spectrum WI/SI
Notes: 404 for Rel-15 9%
381 for Rel-16 8.1%
838 for Rel-17 spectrum related
1475 for Rel-17 non-spectrum related

## Slide 4: Statistics
Meeting | Date | Location | Host | Delegates registered/attendees | Documents requested/uploaded
RAN4 #104-e | Aug 15 – Aug 26, 2022 | Electronic meeting | --- | 452/452 | 3619/3761
Chart: 
| #91 | #92 | #92bis | #93 | #94-e | #95-e | #96-e | #97-e | #98-e | #98-bis-e | #99-e | #100-e | #101-e | #101-bis-e | #102-e | #103-e | #104-e
Delegates | 387 | 266 | 298 | 382 | 226 | 308 | 349 | 367 | 400 | 527 | 401 | 403 | 396 | 404 | 444 | 382 | 452
Chart: 
| #91 | #92 | #92bis | #93 | #94-e | #95-e | #96-e | #97-e | #98-e | #98-bis-e | #99-e | #100-e | #101-e | #101-bis-e | #102-e | #103-e | #104-e
Contributions | 2337 | 2576 | 2230 | 2886 | 2883 | 3297 | 2971 | 3736 | 3740 | 2460 | 3622 | 3903 | 3450 | 2663 | 3690 | 3628 | 3619

## Slide 5: Rel-17 NR and LTE WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN1 | NR_ext_to_71GHz | RP-222477 | SR for Extending current NR operation to 71GHz | Intel | (09/22 95%,12/22 25%) | (09/22 100%,12/22 60%) | Company had different views on whether the WI can be closed.
 |  | RP-222478 | WI Summary for WI Extending current NR operation to 71GHz |  |  |  | 
 |  | RP-222479 | Revised WID for Extending current NR operation to 71GHz |  |  |  | 
RAN1 | NR_FeMIMO-Perf | RP-222239 | Status report for WI: Perf. part: Further enhancements on MIMO for NR | Samsung | (03/22 closed, 09/22 60%) | (03/22 closed, 12/22 85%) | Perf. Extended. TU changed
RAN1 | NR_SL_enh-Perf | RP-221943 | Status report on NR sidelink enhancement in Rel-17; Rapporteur: LG Electronics | LGE | (03/22 closed, 09/22 95%) | (03/22 closed, 09/22 100%) | Closed
RAN1 | NR_cov_enh-Perf | RP-222294 | Status report of WI Perf. part: NR coverage enhancements; rapporteur: China Telecom | China Telecom | (03/22 closed, 09/22 60%) | (03/22 closed, 12/22 90%) | Perf. Extended. TU changed
RAN1 | NR_pos_enh-Perf | RP-222357 | Status report for WI Perf Part: NR positioning enhancements; rapporteur: Intel Corporation | Intel | (03/22 closed, 09/22 40%) | (03/22 closed, 09/22 100%) | Closed
RAN1 | NR_redcap-Perf | RP-222204 | Status report for WI perf. part: Support of reduced capability NR devices; rapporteur: Ericsson | Ericsson | (06/22 100%, 12/22 50%) | (06/22 100%, 12/22 75%) | On-going
RAN2 | NR_IIOT_URLLC_enh-Perf | RP-222212 | Status_Report for Rel-17 WI NR IIoT_URLLC_enh-Perf | Nokia | (03/22 closed, 09/22 50%) | (03/22 closed, 12/22 85%) | Perf. Extended. TU changed
RAN2 | NR_NTN_solutions | RP-222018 | Status report for WI Perf. part: Solutions for NR to support non-terrestrial networks (NTN); rapporteur: Thales | Thales | (06/22 100%, 12/22 20%) | (06/22 100%, 12/22 35%) | On-going
 |  | RP-221946 | WI summary for WI Solutions for NR to support non-terrestrial networks (NTN) |  |  |  | 
RAN2 | NR_UE_pow_sav_enh-Perf | RP-222324 | Status report for WI: UE Power Saving Enhancements for NR | Mediatek | (03/22 closed, 09/22 65%) | (03/22 closed, 09/22 100%) | Closed
RAN2 | LTE_NR_DC_enh2-Perf | RP-222493 | Status report for WI Perf Part: Multi-Radio Dual-Connectivity enhancements; rapporteur: Huawei | Huawei | (03/22 closed, 09/22 30%) | (03/22 closed, 09/22 100%) | Closed
RAN2 | NR_IAB_enh-Perf | RP-222157 | Status report for WI NR_IAB_enh; rapporteur: Qualcomm, Samsung | Qualcomm, Samsung | (06/22 100%, 09/22 40%) | (06/22 closed, 09/22 100%) | Closed
RAN2 | NR_SmallData_INACTIVE-Perf | RP-222362 | Status Report to TSG: NR small data transmissions in INACTIVE state | ZTE | (03/22 closed, 09/22 35%) | (03/22 closed, 12/22 70%) | Perf. Extended. TU changed
 |  | RP-222364 | Revised WID on NR small data transmissions in INACTIVE state |  |  |  | 

## Slide 6: Rel-17 NR and LTE WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN2 | NR_SL_relay-Perf | RP-222017 | Status report for WI: NR Sidelink relay; rapporteur: OPPO | OPPO | (03/22 closed, 09/22 95%) | (03/22 closed, 09/22 100%) | Closed
RAN4 | NR_demod_enh2 | RP-222286 | Status report of WI: Further enhancement on NR demodulation performance; rapporteur: China Telecom | China Telecom, Huawei, Intel | (06/22 100% closed, 09/22 95%) | (06/22 closed, 09/22 100%) | Closed
RAN4 | NR_MIMO_OTA-Perf | RP-222347 | Status report for WI: Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs; Rapporteur: CAICT | CAICT,OPPO | (06/22 100% closed, 09/22 55%) | (06/22 closed, 09/22 90%) | Need discussions on revsied WID first. Then decide whether to close Perf. Part.
 |  | RP-222348 | Revised WID: Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR Ues |  |  |  | 
RAN4 | NR_FR1_TRP_TRS-Perf | RP-222152 | Status report for WI perf.part: Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC); rapporteur: vivo | vivo | (03/22 closed, 09/22 65%) | (03/22 closed, 09/22 100%) | Closed
 |  | RP-222269 | Revised WID: Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) |  |  |  | 
RAN4 | NR_HST_FR1_enh-Perf | RP-222111 | Status report for FR1 HST | CMCC | (03/22 closed, 09/22 90%) | (03/22 closed, 09/22 100%) | Closed
RAN4 | NR_HST_FR2-Perf | RP-222240 | Status report for WI: Perf. part: NR support for high speed train scenario for frequency range 2 (FR2) | Samsung | (03/22 closed, 09/22 80%) | (03/22 closed, 09/22 100%) | Closed
RAN4 | NR_RF_FR1_enh | RP-222494 | Status report for WI Perf Part: RF requirements enhancement for NR frequency range 1 (FR1); rapporteur: Huawei | Huawei, China Telecom | (03/22 closed, 09/22 90%) | (03/22 closed, 09/22 100%) | Closed
 |  | RP-222495 | WID revision: RF requirements enhancement for NR frequency range 1 (FR1) |  |  |  | 

## Slide 7: Rel-17 NR and LTE WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN4 | NR_RF_FR2_req_enh2-Perf | RP-222165 | Status report on Perf. part: Further enhancements of NR RF requirements for frequency range 2 (FR2) | Nokia | (06/22 100% closed, 09/22 80%) | (06/22 100% closed, 09/22 100%) | Closed
RAN4 | NR_RRM_enh2-Core | RP-222424 | Status report of Further RRM enhancement for NR and MR-DC; rapporteur: Apple, CATT | Apple, CATT | (03/22 closed, 09/22 50%) | (03/22 closed, 09/22 100%) | Closed
RAN4 | NR_MG_enh-Perf | RP-222328 | Status report for WI: NR and MR-DC measurement gap enhancements | Mediatek, Intel | (03/22 closed, 09/22 40%) | (03/22 closed, 09/22 100%) | Closed
RAN4 | NR_repeaters-Perf | RP-222274 | Status report for WI: Perf. part: NR repeaters; rapporteur: Qualcomm | Qualcomm | (03/22 closed, 09/22 30%) | (03/22 closed, 12/22 80%) | Perf. Extended. TU changed
 |  | RP-222275 | Revised WID on NR Repeaters |  |  |  | 
RAN4 | NR_6GHz-Perf | RP-222496 | Status report for WI Perf Part: Introduction of 6GHz NR licensed bands; rapporteur: Huawei | Huawei, Ericsson, Nokia, ZTE | (06/22 100% closed, 09/22 80%) | (06/22 100% closed, 09/22 100%) | Closed
RAN4 | NR_RAIL_EU_900MHz | RP-222373 | Status report for WI Introduction of 900MHz NR band for Europe for Rail Mobile Radio (RMR); rapporteur: Union Inter. Chemins de Fer | UIC | (09/22 95%, 06/22 100% closed) | (09/22 100%, 06/22 100% closed) | Closed
RAN4 | NB_IOTenh4_LTE_eMTC6-Perf | RP-222492 | Status report for WI Perf Part: Additional enhancements for NB-IoT and LTE-MTC; rapporteur: Huawei | Huawei | (03/22 closed, 09/22 70%) | (03/22 closed, 09/22 100%) | Closed

## Slide 8: Rel-18 RAN1~3-led NR and LTE WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN1 | FS_NR_pos_enh2 | RP-222257 | Revised SID on Study on expanded and improved NR positioning | Intel Corporation | (12/22 12%) | (12/22 40%) | 
 |  | RP-222258 | Status report of SI: Study on expanded and improved NR positioning; rapporteur: Intel Corporation |  |  |  | 
RAN1 | FS_NR_duplex_evo | RP-222109 | Status Report for SI Study on evolution of NR duplex operation;rapporteur: CMCC | CMCC | (12/23 10%) | (12/23 15%) | 
 |  | RP-222110 | Revised SID: Study on evolution of NR duplex operation |  |  |  | 
 |  | RP-222458 | Revised SID: Study on evolution of NR duplex operation | Vodafone, Telecom Italia, Deutsche Telekom, Charter, Ericsson |  |  | 
RAN1 | FS_NR_netcon_repeater | RP-222138 | Status report of SI: Study on NR network-controlled repeaters | ZTE | (09/22 40%) | (09/22 100%) | No RAN4 impact
RAN1 | FS_NR_AIML_Air | RP-222486 | SR for Study on AI/ML for NR air interface | Qualcomm, CAICT, Ericsson | (12/23 5%) | (12/23 10%) | 
RAN1 | FS_NR_LPWUS | RP-222144 | Status report for SI: Study on low-power wake-up signal and receiver for NR; rapporteur: vivo | vivo | (12/23 0%) | (12/23 0%) | 
 |  | RP-222145 | Revised SID: Study on low-power Wake-up Signal and Receiver for NR |  |  |  | 
RAN1 | FS_NR_redcap_enh | RP-222205 | Status report for Study on further NR RedCap (reduced capability) UE complexity reduction; rapporteur: Ericsson | Ericsson | (09/22 33%) | (09/22 100%) | No RAN4 impact
RAN2 | FS_NR_XR_enh | RP-222218 | Study on XR Enhancements for NR | Nokia, Qualcomm | (12/22 20%) | (12/22 30%) | 
RAN3 | FS_gNB_CU_CP_resiliency | RP-222249 | Revised SID on enhancement for resiliency of gNB-CU-CP | NTT DOCOMO, INC. | (09/22 0%) | (09/22 100%) | No RAN4 impact
 |  | RP-222250 | Status report for SI: Study on enhancement for resiliency of gNB-CU-CP |  |  |  | 

## Slide 9: Rel-18 RAN1~3-led NR and LTE WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN1 | FS_NR_pos_enh2 | RP-222257 | Revised SID on Study on expanded and improved NR positioning | Intel Corporation | (12/22 12%) | (12/22 40%) | 
RAN1 | NR_DSS_enh | RP-222322 | Status report for WI: Enhancement of NR Dynamic spectrum sharing (DSS); rapporteur: Ericsson | Ericsson | (12/22 40%, 06/24 0%) | (12/22 95%, 06/24 0%) | 
RAN1 | NR_MC_enh | RP-222251 | Revised WID on Multi-carrier enhancements | NTT DOCOMO, INC. | (12/22 10%, 06/24 0%) | (12/22 30%, 06/24 0%) | 
 |  | RP-222252 | Status report for WI: Multi-carrier enhancements for NR |  |  |  | 
RAN1 | NR_cov_enh2 | RP-222284 | Status report of WI: Further NR coverage enhancements; rapporteur: China Telecom | China Telecom | (12/23 0%, 06/24 0%) | (12/23 0%, 06/24 0%) | 
RAN1 | NR_MIMO_evo_DL_UL | RP-222232 | Status Report to TSG: NR MIMO Evolution for Downlink and Uplink | Samsung, Huawei, NTT DOCOMO | (12/23 10%, 06/24 0%) | (12/23 20%, 06/24 0%) | 
RAN1 | NR_SL_enh2 | RP-221937 | Status report for WI NR sidelink evolution; rapporteur: OPPO | OPPO, LGE | (12/23 7%, 06/24 0%) | (12/23 20%, 06/24 0%) | 
 |  | RP-221938 | Revised WID: NR sidelink evolution |  |  |  | 
RAN2 | NR_Mob_enh2 | RP-222331 | Status Report for WI: Mobility Enhancements | Mediatek, Apple | (12/23 0%, 06/24 0%) | (12/23 10%, 06/24 0%) | 
 |  | RP-222332 | Revised WI: Mobility Enhancements |  |  |  | 
RAN2 | NR_MT_SDT | RP-222363 | Status Report to TSG: Mobile Terminated-Small Data Transmission (MT-SDT) for NR | ZTE | (09/23 0%, n/a) | (09/23 0%, n/a) | No RAN4 impact
RAN2 | NR_DualTxRx_MUSIM | RP-222150 | Status report for WI: Dual Transmission Reception (TxRx) Multi-SIM for NR; rapporteur: vivo | vivo | (12/23 0%, 06/24 0%) | (12/23 5%, 06/24 0%) | 
RAN2 | NR_SL_relay_enh | RP-221947 | Status report on NR sidelink relay enhancements | LGE | (12/23 0%, 06/24 0%) | (12/23 10%, 06/24 0%) | 
RAN2 | NR_IDC_Enh-Core | RP-222082 | Status report for WI Core part In-Device Co-existence (IDC) enhancements for NR and MR-DC | Xiaomi | (12/23 0%, n/a) | (12/23 10%, n/a) | 
RAN2 | NR_UAV | RP-222169 | Status Report for Rel-18 NR Support for UAV (Uncrewed Aerial Vehicles) | Nokia | (12/23 0%, n/a) | (12/23 5%, n/a) | No RAN4 impact
 |  | RP-222171 | Revised WID: NR Support for UAV (Uncrewed Aerial Vehicles) |  |  |  | 
 |  | RP-222246 | Rev of RP-213600 Revised WID on NR support for UAV, LG Uplus, KT, SKT, ETRI |  |  |  | 
RAN2 | NR_NTN_enh | RP-222019 | Status report for WI NR NTN (Non-Terrestrial Networks) enhancements; rapporteur: Thales | Thales | (12/23 5%, 06/24 0%) | (12/23 10%, 06/24 0%) | 

## Slide 10: Rel-18 RAN1~3-led NR and LTE WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN3 | NR_ENDC_SON_MDT_enh2-Core | RP-222122 | Status report for WI on further enhancement of data collection for SONMDT in NR standalone and MR-DC | CMCC | (12/23 0%, n/a) | (12/23 10%, n/a) | No RAN4 impact
RAN3 | NR_QoE_enh | RP-222219 | Status report for Enhancement on NR QoE management and optimizations for diverse services | China Unicom | (12/23 0%, n/a) | (12/23 10%, n/a) | No RAN4 impact
RAN3 | NR_mobile_IAB | RP-222159 | Status report for WI NR_mobile_IAB; rapporteur: Qualcomm, Samsung | Qualcomm | (12/23 5%, 06/24 0%) | (12/23 5%, 06/24 0%) | 
 |  | RP-222226 | Revised WID on mobile IAB (KT Corp., LG Uplus, SK Telecom, ETRI, AT&T) |  |  |  | 
RAN3 | NR_AIML_NGRAN-Core | RP-222123 | Status report for WI on Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | CMCC, Ericsson | (06/23 0%, n/a) | (06/23 10%, n/a) | No RAN4 impact
RAN2 | IoT_NTN_enh | RP-222329 | Status report for WI: IoT NTN Enhancements | Mediatek | (12/23 3%, 06/24 0%) | (12/23 10%, 06/24 0%) | 

## Slide 11: Rel-18 RAN4-led NR and LTE non-spectrum WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN3 | NR_ENDC_SON_MDT_enh2-Core | RP-222122 | Status report for WI on further enhancement of data collection for SONMDT in NR standalone and MR-DC | CMCC | (12/23 0%, n/a) | (12/23 10%, n/a) | TU changed (No RAN4 TU)
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN4 | FS_NR_eff_BW_util | RP-222377 | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | Ericsson | (09/22 85%) | (12/22 85%) | TU changed
RAN4 | FS_NR_FR2_OTA_enh | RP-222277 | Status Report for SI Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements; rapporteur: Qualcomm | Qualcomm | (12/23 0%) | (12/23 10%) | 
 |  | RP-222278 | Revised SID for Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements |  |  |  | 
RAN4 | FS_SimBC | RP-222216 | Revised SID: Study on simplification of band combination specification for NR and LTE | ZTE | (06/23 0%) | (06/23 15%) | 
 |  | RP-222217 | Status report for SI: Study on simplification of band combination specification for NR and LTE; rapporteur: ZTE |  |  |  | 
RAN4 | FS_NR_BS_RF_evo | RP-222500 | Status report for SI: NR base station (BS) RF requirement evolution; rapporteur: Huawei | Huawei | (06/23 0%) | (06/23 10%) | 
 |  | RP-222501 | WID revision: NR BS RF requirement evolution |  |  |  | 
RAN4 | FS_NR_700800900_combo_enh | RP-222387 | Status report for SI Study on enhancement for 700/800/900MHz band combinations for NR | CATT | (03/23 0%) | (03/23 20%) | 
RAN4 | NR_FR1_lessthan_5MHz_BW | RP-222057 | Status report for NR support for dedicated spectrum less than 5MHz for FR1 | Nokia | (12/23 0%, 06/24 0%) | (12/23 0%, 06/24 0%) | 
RAN4 | NR_ENDC_RF_FR1_enh2 | RP-222499 | Status report for WI: RF requirements enhancement for NR frequency range 1; rapporteur: Huawei | Huawei, NTT DOCOMO | (12/23 0%, 06/24 0%) | (12/23 10%, 06/24 10%) | 
RAN4 | NR_RF_FR2_req_Ph3 | RP-222059 | Status report on NR RF requirements enhancement for frequency range 2 (FR2), Phase 3; Rapporteur: Nokia, Xiaomi | Nokia, Xiaomi | (12/23 0%, 03/24 0%) | (12/23 10%, 03/24 10%) | 
 |  | RP-222228 | Revised WID: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 |  |  |  | 
RAN4 | NR_FR2_multiRX_DL | RP-221936 | Status report for WI NR_FR2_multiRx_DL; rapporteur: Qualcomm, vivo | Qualcomm, vivo | (09/23 0%, 03/24 0%) | (09/23 10%, 03/24 0%) | 
RAN4 | NR_HST_FR2_enh | RP-222236 | Status report for WI: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | Samsung | (09/23 0%, 03/24 0%) | (09/23 0%, 03/24 0%) | 
 |  | RP-222272 | Revised WID on enhanced NR support for high speed train scenario in frequency range 2 (FR2) |  |  |  | 

## Slide 12: Rel-18 RAN4-led NR and LTE non-spectrum WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN3 | NR_ENDC_SON_MDT_enh2-Core | RP-222122 | Status report for WI on further enhancement of data collection for SONMDT in NR standalone and MR-DC | CMCC | (12/23 0%, n/a) | (12/23 10%, n/a) | TU changed (No RAN4 TU)
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN4 | NR_RRM_enh3-Core | RP-222423 | Status report of Even Further RRM enhancement for NR and MR-DC; rapporteur: Apple, OPPO | Apple, OPPO | (12/23 0%, 06/24 0%) | (12/23 5%, 06/24 0%) | 
RAN4 | NR_MG_enh2 | RP-222334 | Status Report: WI Further Enhancements on NR and MR-DC Measurement Gaps and Measurements without Gaps | MediaTek, Intel | (12/23 0%, 06/24 0%) | (12/23 10%, 06/24 0%) | 
 |  | RP-222356 | Revised WID on Further Enhancements on NR and MR-DC Measurement Gaps and Measurements without Gaps |  |  |  | 
RAN4 | NR_LTE_EMC_enh | RP-222164 | Status report WI on BS/UE EMC enhancements for NR and LTE | Ericsson | (09/23 0%, 12/23 0%) | (09/23 0%, 12/23 0%) | 
RAN4 | NR_ATG | RP-222108 | Status report for Air-to-ground network for NR; rapporteur CMCC | CMCC | (12/23 0%, 03/24 0%) | (12/23 5%, 03/24 0%) | 
RAN4 | NonCol_intraB_ENDC_NR_CA | RP-222308 | Status report for WI Support of intra-band non-collocated EN-DC/NR-CA deployment; rapporteur: KDDI | KDDI | (09/23 0%, 12/23 0%) | (09/23 10%, 12/23 0%) | 
 |  | RP-222309 | Revised WI: Support of intra-band non-collocated EN-DC/NR-CA deployment |  |  |  | 
RAN4 | NR_demod_enh3-Perf | RP-222295 | Status report of WI: Perf. part: NR demodulation performance evolution; rapporteur: China Telecom | China Telecom | (n/a, 12/23 0%) | (n/a, 12/23 0%) | 
 |  | RP-222300 | Revised WID on NR demodulation performance evolution |  |  |  | 
RAN4 | LTE_NBIOT_eMTC_NTN_req | RP-222330 | Status Report for WI: NB-IoT/eMTC core & performance requirements for Non-Terrestrial Networks | Mediatek | (12/22 0%, 06/23 0%) | (12/22 50%, 06/23 0%) | 
RAN4 | FS_FR2_enhTestMethods |  | Study on enhanced test methods for FR2 NR UEs [RAN4 SI: FS_FR2_enhTestMethods] | Apple, vivo, Intel | (06/22 100% closed) | closed | 

## Slide 13: Rel-18 RAN4-led NR and LTE spectrum WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN3 | NR_ENDC_SON_MDT_enh2-Core | RP-222122 | Status report for WI on further enhancement of data collection for SONMDT in NR standalone and MR-DC | CMCC | (12/23 0%, n/a) | (12/23 10%, n/a) | TU changed (No RAN4 TU)
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN4 | NR_6GHz_add_bands | RP-222497 | Status report for WI: Introduction of additional 6GHz NR licensed bands; rapporteur: Huawei | Huawei | (12/23 0%, 12/23 0%) | (12/23 0%, 12/23 0%) | 
 |  | RP-222498 | WID revision: Introduction of additional 6GHz NR licensed bands |  |  |  | 
RAN4 | NR_bands_UL_MIMO_R18 | RP-222508 | Status report for WI: Additional NR bands for UL-MIMO in Rel-18; rapporteur: Huawei | Huawei | (12/23 0%, 12/23 0%) | (12/23 0%, 12/23 0%) | 
 |  | RP-222509 | WID revision: Additional NR bands for UL-MIMO in Rel-18 |  |  |  | 
RAN4 | NR_600MHz_APT-Core | RP-222013 | Status report for WI Core part: APT 600MHz NR band | Spark NZ Ltd | (12/22 0%, 03/23 0%） | (12/22 10%, 03/23 10%） | 
RAN4 | DC_R18_1BLTE_1BNR_2DL2UL | RP-222089 | Status report for WI: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); rapporteur: CHTTL | CHTTL | (12/23 0%, 12/23 0%) | (12/23 5%, 12/23 0%) | 
 |  | RP-222091 | Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) |  |  |  | 
RAN4 | DC_R18_2BLTE_1BNR_3DL2UL | RP-222504 | Status report for WI: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL); rapporteur: Huawei | Huawei | (12/23 0%, 12/23 0%) | (12/23 10%, 12/23 10%) | 
 |  | RP-222505 | WID revision: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) |  |  |  | 
RAN4 | DC_R18_xBLTE_1BNR_yDL2UL | RP-222311 | SR for WI on DC of x bands LTE inter-band CA (x345) and 1 NR band, Rapporteur: Nokia | Nokia | (12/23 0%, 12/23 0%) | (12/23 5%, 12/23 5%) | 
 |  | RP-222312 | Revised Rel-18 WID on DC of x bands LTE inter-band CA (x345) and 1 NR band |  |  |  | 
RAN4 | DC_R18_xBLTE_2BNR_yDL2UL-Core | RP-221944 | Revised WID on Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | LGE | (12/23 0%, 12/23 0%) | (12/23 5%, 12/23 5%) | 
 |  | RP-221945 | Status report on Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR (2DL/1UL); Rapporteur: LG Electronics |  |  |  | 

## Slide 14: Rel-18 RAN4-led NR and LTE spectrum WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN3 | NR_ENDC_SON_MDT_enh2-Core | RP-222122 | Status report for WI on further enhancement of data collection for SONMDT in NR standalone and MR-DC | CMCC | (12/23 0%, n/a) | (12/23 10%, n/a) | TU changed (No RAN4 TU)
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN4 | DC_R18_xBLTE_yBNR_zDL2UL | RP-222094 | Revised WID on Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) | ZTE | (12/23 0%, 12/23 0%) | (12/23 5%, 12/23 5%) | 
 |  | RP-222095 | Status report for WI: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL); Rapporteur; ZTE Corporation |  |  |  | 
RAN4 | DC_R18_xBLTE_yBNR_zDL3UL | RP-222237 | Revised Rel-18 WID: Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL | Samsung | (12/23 0%, 12/23 0%) | (12/23 5%, 12/23 5%) | 
 |  | RP-222238 | Status report for WI: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL |  |  |  | 
RAN4 | NR_CA_R18_Intra | RP-222104 | Status report of WI NR_CA_R18_Intra; rapporteur: Ericsson | Ericsson | (12/23 0%, 12/23 0%) | (12/23 0%, 12/23 0%) | 
 |  | RP-222105 | Revised WID: Basket Rel-18 WID NR_CA_R17_Intra |  |  |  | 
RAN4 | NR_CADC_R18_2BDL_xBUL | RP-222079 | Revised WID:Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | ZTE | (12/23 0%, 12/23 0%) | (12/23 5%, 12/23 5%) | 
 |  | RP-222080 | Status report for WID:Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) Rapporteur; ZTE Corporation |  |  |  | 
RAN4 | NR_CADC_R18_3BDL_xBUL | RP-222092 | Revised WID on Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) | ZTE | (12/23 0%, 12/23 0%) | (12/23 10%, 12/23 0%) | 
 |  | RP-222093 | Status report for WI: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2); Rapporteur; ZTE Corporation |  |  |  | 

## Slide 15: Rel-18 RAN4-led NR and LTE spectrum WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN3 | NR_ENDC_SON_MDT_enh2-Core | RP-222122 | Status report for WI on further enhancement of data collection for SONMDT in NR standalone and MR-DC | CMCC | (12/23 0%, n/a) | (12/23 10%, n/a) | TU changed (No RAN4 TU)
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN4 | NR_CADC_R18_yBDL_xBUL | RP-222317 | Status report of WI NR_CADC_R18_yBDL_xBUL (y=4,5,6, x=1,2); rapporteur: Ericsson | Ericsson | (12/23 0%, 12/23 0%) | (12/23 25%, 12/23 25%) | 
 |  | RP-222318 | Revised WID: Basket Rel-18 WID NR_CADC_R18_yBDL_xBUL (y=4,5,6, x=1,2) |  |  |  | 
RAN4 | NR_SUL_combos_R18 | RP-222506 | Status report for WI: Rel-18 Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP); rapporteur: Huawei | Huawei | (12/23 0%, 12/23 0%) | (12/23 10%, 12/23 10%) | 
 |  | RP-222507 | WID revision: Rel-18 Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) |  |  |  | 
RAN4 | LTE_NR_HPUE_FWVM_R18 | RP-222058 | WI status report for High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands | Nokia | (12/23 0%, 12/23 0%) | (12/23 10%, 12/23 0%) | 
RAN4 | NR_RAIL_HPUE_n100_n101-Core |  | Status report for WI: Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe | UIC |  |  | 
RAN4 | NR_LTE_V2X_PC5_combos_R18 | RP-222385 | Revised WID for Rel-18 band combinations for Uu and V2X concurrent operation | CATT | (12/23 0%, 12/23 0%) | (12/23 5%, 12/23 5%) | 
 |  | RP-222386 | SR for Rel-18 band combinations for Uu and V2X concurrent operation |  |  |  | 
RAN4 | NR_unlic_enh | RP-222174 | Revised WID: Enhancements of NR shared spectrum bands | Apple | (03/23 0%, 03/23 0%) | (03/23 15%, 03/23 0%) | Perf. part is missing from SR
 |  | RP-222175 | Status report for Enhancements of NR shared spectrum bands |  |  |  | 
RAN4 | DL_intrpt_combos_TxSW_R18 | RP-222288 | Revised WID: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | China Telecom | (12/23 0%, 12/23 0%) | (12/23 10%, 12/23 0%) | 
 |  | RP-222289 | Status report of WI: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink; rapporteur: China Telecom |  |  |  | 

## Slide 16: Rel-18 RAN4-led NR and LTE spectrum WI/SIs
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN3 | NR_ENDC_SON_MDT_enh2-Core | RP-222122 | Status report for WI on further enhancement of data collection for SONMDT in NR standalone and MR-DC | CMCC | (12/23 0%, n/a) | (12/23 10%, n/a) | TU changed (No RAN4 TU)
WG | Related WIs | Tdoc | Title | Rapporteur | Status in previous RAN (Target date, completion level) | Status in this RAN (target date, completion level) | Notes
RAN4 | LTE_terr_bcast_bands_part2 | RP-222224 | Revised WID on New bands and bandwidth allocation for LTE based 5G terrestrial broadcast - part 2 | Qualcomm, EBU | (06/23 0%, n/a) | (06/23 15%, n/a) | 
 | LTE_terr_bcast_bands_part2 | RP-222225 | Status report for New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 |  |  |  | 
RAN4 | LTE_TDD_1670_1675MHz | RP-221933 | Status report for WI Introduction of LTE TDD band in 1670-1675 MHz; rapporteur: Ligado Networks | Ligado | (12/22 15%, 12/22 0%) | (12/22 50%, 12/22 0%) | 
RAN4 | LTE_CA_R18_xBDL_yBUL | RP-222502 | Status report for WI: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL; rapporteur: Huawei | Huawei | (12/23 0%, 12/23 0%) | (12/23 20%, 12/23 20%) | 
 |  | RP-222503 | WID revision: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL |  |  |  | 
RAN4 | LTE_CA_intra_B8-Core | RP-222125 | Status report for LTE intra-band contiguous Carrier Aggregation for band 8; rapporteur CMCC | CMCC | (09/22 0%, n/a) | (09/22 99%, n/a) | Need discuss how to handle WI together with LTE basket WIs.

## Slide 17: RAN4 new WI/SI proposals (Rel-18)
  New Rel-18 spectrum related WI proposals
  HPUE basket WIs
  Other basket WIs
  Spectrum WIs
RP-222083 | New WID on high power for FR1 for FDD single band(s) with power class 2 | China Unicom
RP-222084 | New WID on high power for FR1 for NR_CADC_R18_yBDL_xBUL with power class 2 and high power on FDD band(s) | China Unicom
RP-222106 | New WID on high power for FR1 for DC_R18_xBLTE_yBNR_zDLnUL with power class PC2 and PC1.5 | Ericsson
RP-222287 | New WID: High power UE for FR1 NR CA/DC or NR SUL (supplementary uplink) band combination with y bands downlink (1<y<=6) and x bands uplink (x=1,2) and power class z (z<3) and high power on TDD band(s) | China Telecom
RP-222351 | WID on High power UE (power class 1.5) for NR TDD bands | CMCC
RP-222512 | High power for FR1 for NR_CA_R18_intra with power class 2 and 1.5 on TDD band(s) | Huawei, HiSilicon
RP-222341 | Discussion on potential basket WID for HPUE FDD bands | MediaTek Inc.
RP-222012 | Basket WID: adding new channel bandwidth(s) support to existing NR bands | Ericsson
RP-222451 | Proposed new WID: 4Rx support for NR FR1 bands (<2.6GHz) in Rel-18 | ZTE, Sanechips
RP-222452 | Motivation on basket WID on 4Rx support for NR FR1 bands (<2.6GHz) in Rel-18 | ZTE, Sanechips
RP-222514 | New WID: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | Huawei, HiSilicon
RP-222130 | New WID: NR CA band combinations with dual SUL bands in Rel-18 | CMCC
RP-222131 | Motivation on NR CA band combinations with dual SUL bands in Rel-18 | CMCC

## Slide 18: RAN4 new WI/SI proposals (Rel-18)
  New Rel-18 non-spectrum related WI proposals
  MRP requirements for LTE intra-band non-contiguous CA with gap >35MHz
  TRP/TRS
  MIMO OTA
  High power UE
RP-222307 | MPR requirements for LTE itrabCA with >35 MHz CC gap | Vodafone Ireland Plc
RP-222370 | Motivation for MPR requirements for LTE itrabCA with >35 MHz CC gap | Vodafone Ireland Plc
RP-222071 | Motivation of R18 FR1 TRP TRS | OPPO
RP-222072 | R18 New WID on FR1 TRP TRS | OPPO
RP-222073 | R18 motivation of introducing high capability handheld UE | OPPO
RP-222074 | R18 New WI on high capability handheld UE | OPPO
RP-222141 | Motivation for new WID: Rel-18 TRP/TRS | vivo
RP-222142 | New WID: Rel-18 TRP/TRS | vivo
RP-222178 | Motivation paper for NR FR1 TRP TRS work in Rel-18 | Apple
RP-222179 | New WID: Continuation of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | Apple
RP-222345 | Motivation for Rel-18 new WI on NR MIMO OTA | CAICT
RP-222346 | New WI: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs | CAICT,OPPO, Keysight
RP-222320 | New WID: PC1.5 Inter-band and Intra-band uplink CA | T-Mobile USA Inc.
RP-222340 | New WID: Reference sensitivity degradation mitigation for High-Power UEs in NR FDD sub-1GHz bands | MediaTek Inc.
RP-222341 | Discussion on potential basket WID for HPUE FDD bands | MediaTek Inc.

## Slide 19: RAN4 related issues (Rel-17)
  Rel-17 open issues
  Rel-17 Canadian spectrum regulation issue
  Signaling for intra-band EN-DC combination
  BWP without restriction (Feature group 6-1a)
  LS to ITU
RP-222490 | CR to 38.101-1 on new NS for Canadian WCS regulation R17 | Apple, Telus
RP-222344 | Operation in the n77 frequency range in US and Canada | Nokia, Nokia Shanghai Bell
RP-222350 | Extension of operation in the n77 frequency range in US | Nokia, Nokia Shanghai Bell
RP-222352 | Extension of operation in the n77 frequency range in US | Nokia, Nokia Shanghai Bell
RP-222353 | Extension of operation in the n77 frequency range in Canada | Nokia, Nokia Shanghai Bell
RP-222513 | Discussion on intra-band EN-DC combination | Huawei, HiSilicon
RP-222427 | On BWP without restriction | Apple
RP-222132 | Discussion on Feature Group 6-1a "bwp-WithoutRestriction" | CMCC
RP-222067 | Support of BWP without restriction | Qualcomm Incorporated
RP-222155 | On BWP operation without CD-SSB | vivo
RP-222241 | On BWP operation without bandwidth restriction | Samsung
RP-222306 | On FG6-1a - BWP without restriction | Nokia, Nokia Shanghai Bell
RP-222338 | Discussion on support of BWP without restriction | MediaTek Inc.
RP-222366 | Discussion on per-FR gap capabilities | Nokia, Nokia Shanghai Bell
RP-222395 | Discussion on BWP operation without bandwidth restriction | CATT
RP-221912 | Draft reply LS to ITU-R WP5D/TEMP/482(Rev.1) = RP-212699 on work towards two new recommendations "Generic unwanted emission characteristics of base stations/mobile stations using the terrestrial radio interfaces of IMT-2020" (R4-2214737; to: RAN; cc: RAN5; contact: Ericsson) | RAN4

## Slide 20: RAN4 related issues (Rel-17)
  Rel-17 open issues
  Rel-17 MIMO OTA
  Rel-17 TRP/TRS
  Rel-17 U6GHz
  Rel-17 Coverage enhancement
RP-222070 | Views on R17 MIMO OTA | OPPO
RP-222267 | Discussion on NR MIMO OTA | vivo
RP-222280 | Views on conclusions of MIMO OTA | Qualcomm Incorporated
RP-222347 | Status report for WI: Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR UEs; Rapporteur: CAICT | RAN4
RP-222348 | Revised WID: Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirements for NR Ues | CAICT,OPPO
RP-222349 | Discussion on NR MIMO OTA | CAICT
RP-222160 | Considerations on TRP and TRS measurement campaign | TELECOM ITALIA S.p.A.
RP-222269 | Revised WID: Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | vivo
RP-222361 | Discussion on 4Rx for 6GHz bands | vivo
RP-222511 | 4 Rx support for 6GHz band n104 | Huawei, HiSilicon, China Telecom, Orange, Telecom Italia, Telefonica, Bouygues Telecom
RP-222065 | Views on Rel-17 NR coverage enhancement open issues | Qualcomm Incorporated
RP-222181 | On remaining open issues in the Rel-17 coverage enhancement work item | Apple

## Slide 21: RAN4 related issues (Rel-18)
  Rel-18 open issues
  Rel-18 OAT testing
  Rel-18 band combination simplification
  Rel-18 irregular channel bandwidth
  Rel-18 MUSIM
  Rel-18 RAN4-led further MG enhancement WI
  Rel-18 ATG
RP-222268 | Discussion on FR2 OTA testing enhancements | vivo
RP-222279 | Views on NR FR2 OTA testing enhancements | Qualcomm Incorporated
RP-222215 | On simplification of V2X band combinations in FS_SimBC | ZTE, vivo
RP-222216 | Revised SID: Study on simplification of band combination specification for NR and LTE | ZTE, vivo
RP-222176 | Next steps on SI for irregular channel bandwidths | Apple
RP-222377 | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | Ericsson
RP-222489 | RF impact for Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | Apple
RP-222336 | Views on scope of Rel-18 further MG enhancement | MediaTek Inc.
RP-222337 | Revised WI: Further Enhancements on NR and MR-DC Measurement Gaps and Measurements without Gaps | MediaTek Inc.
RP-222356 | Revised WID on Further Enhancements on NR and MR-DC Measurement Gaps and Measurements without Gaps | Intel Corporation, MediaTek Inc.
RP-222426 | Motivation of WID revision for Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | Apple
RP-222302 | Discussion on system performance evaluation for aerial networks | SK Telecom

## Slide 22: RAN4 related issues (Rel-18)
  Rel-18 open issues
  U6GHz 4Rx
RP-222361 | Discussion on 4Rx for 6GHz bands | vivo
RP-222511 | 4Rx support for band n104 | Huawei, HiSilicon, China Telecom, Orange, Telecom Italia, Telefonica, Bouygues Telecom, Deutsche Telekom, Telenor, CBN, Vodafone

## Slide 23: RAN4 TU Planning
The RAN4 TU budget for Rel-17 and Rel-18 approved WI/SI
WG | RAT | WI code | WI or SI | Rel | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD
 |  |  |  |  | 104bis | 104bis | 105 | 105 | 106 | 106 | 106bis | 106bis | 107 | 107 | 108 | 108 | 108bis | 108bis | 109 | 109
R4 | NR | NR_feMIMO-Perf | WI | REL-17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R1 | NR | NR_ext_to_71GHz-Core | WI | REL-17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | NR_ext_to_71GHz-Perf | WI | REL-17 | 0.5 | 1 | 0.5 | 1 |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | NR_redcap-Perf | WI | REL-17 |  | 0.75 |  | 0.5 |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | NR_cov_enh-Perf | WI | REL-17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | NR_IIOT_URLLC_enh-Perf | WI | REL-17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | NR_NTN_solutions-Perf | WI | REL-17 | 0.75 | 0.5 | 0.75 | 0.5 |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | REL-17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | NR_repeaters-Perf | WI | REL-17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R1 | NR | NR_MIMO_evo_DL_UL-Core | WI | REL-18 |  |  |  |  | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
R4 | NR | NR_MIMO_evo_DL_UL-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25
R1 | NR | NR_cov_enh2-Core | WI | REL-18 | 0.25 |  | 0.25 |  | 0.25 |  | 0.5 |  | 0.5 |  | 1 |  | 1 |  | 1 | 
R4 | NR | NR_cov_enh2-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25
R1 | NR | NR_DSS_enh-Core | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | NR_DSS_enh-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25
R1 | NR | NR_MC_enh-Core | WI | REL-18 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  |  |  |  |  |  |  | 
R4 | NR | NR_MC_enh-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25
R1 | NR | NR_SL_enh2-Core | WI | REL-18 |  |  |  |  | 0.5 | 0.25 | 1 | 0.5 | 1.5 | 0.5 | 1.5 | 1 | 1.5 | 1 | 1.5 | 1
R4 | NR | NR_SL_enh2-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25
R1 | NR | FS_NR_netcon_repeater | SI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R1 | NR | FS_NR_AIML_air | SI | REL-18 |  |  |  |  |  |  |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
R1 | NR | FS_NR_duplex_evo | SI | REL-18 | 0.5 |  | 0.5 |  | 1 |  | 0.5 |  | 1 |  | 0.5 |  | 0.25 |  | 0.25 | 
R1 | NR | FS_NR_pos_enh2 | SI | REL-18 | 0.25 | 0.5 | 0.25 | 0.5 |  |  |  |  |  |  |  |  |  |  |  | 
R1 | NR | FS_Netw_Energy_NR | SI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R1 | NR | FS_NR_LPWUS | SI | REL-18 |  |  |  |  | 0.25 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.25 |  | 0.25 | 
R1 | NR | FS_NR_redcap_enh | SI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R2 | NR | NR_Mob_enh2-Core | WI | REL-18 |  | 0.5 |  | 0.5 | 0.25 | 1 | 0.5 | 1.5 | 0.5 | 1.5 | 0.5 | 1.5 | 0.25 | 1.5 | 0.25 | 1.5
R4 | NR | NR_Mob_enh2-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25
R2 | NR | FS_NR_XR_enh | SI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R2 | LTE | IoT_NTN_enh-Core | WI | REL-18 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.5 | 0.25
R4 | LTE | IoT_NTN_enh-Perf | WI |  |  |  |  |  |  |  |  |  |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25

## Slide 24: RAN4 TU Planning
The RAN4 TU budget for Rel-17 and Rel-18 approved WI/SI
WG | RAT | WI code | WI or SI | Rel | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD
 |  |  |  |  | 104bis | 104bis | 105 | 105 | 106 | 106 | 106bis | 106bis | 107 | 107 | 108 | 108 | 108bis | 108bis | 109 | 109
R2 | NR | NR_NTN_enh-Core | WI | REL-18 | 0.5 |  | 0.5 |  | 1 | 0.25 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5
R4 | NR | NR_NTN_enh-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 | 0.25 | 0.25 | 0.25
R2 | NR | NR_UAV-Core | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R2 | NR | NR_SL_relay_enh | WI | REL-18 |  |  |  |  |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
R4 | NR | NR_SL_relay_enh | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25
R2 | NR | NR_DualTxRx_MUSIM-Core | WI | REL-18 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.25
R2 | NR | NR_DualTxRx_MUSIM-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25
R2 | NR | NR_IDC_enh-Core | WI | REL-18 |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25 |  |  |  | 
R3 | NR | NR_mobile_IAB-Core | WI | REL-18 |  |  |  |  | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
R4 | NR | NR_mobile_IAB-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 | 0.25
R3 | NR | NR_ENDC_SON_MDT_enh2-Core | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | R18 RAN4-led spectrum items | SI/WI | REL-18 | 6.5 | 0.25 | 6.5 | 0.25 | 6.5 | 0.25 | 6.5 | 0.25 | 6.5 | 0.25 | 6.5 | 0.25 | 6.5 | 0.25 | 6.5 | 0.25
R4 | NR | NR_FR1_lessthan_5MHz_BW-Core | WI | REL-18 |  |  |  |  | 0.25 | 0.25 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  | 
R4 | NR | NR_FR1_lessthan_5MHz_BW-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25
R4 | NR | NR_ENDC_ RF_FR1_enh2-Core | WI | REL-18 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1.5 |  | 1.5 |  | 1.5 | 
R4 | NR | NR_ENDC_ RF_FR1_enh2-Perf | WI | REL-18 |  | 1.5 |  | 1.5 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0.5
R4 | NR | NR_RF_FR2_req_Ph3-Core | WI | REL-18 | 1 |  | 1 |  | 0.75 |  | 0.5 |  | 0.75 |  | 1 |  | 1 |  | 1 | 
R4 | NR | NR_RF_FR2_req_Ph3--Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25 |  | 0.25
R4 | NR | NR_FR2_multiRX_DL-Core | WI | REL-18 | 1 | 1 | 1 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  | 
R4 | NR | NR_FR2_multiRX_DL-Perf | WI | REL-18 |  |  |  |  |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
R4 | NR | NR_RRM_enh3 | WI | REL-18 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0.5 |  | 0.5 |  | 0.5
R4 | NR | NR_RRM_enh3 | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.5
R4 | NR | [NR_MG_enh2-core] | WI | REL-18 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
R4 | NR | [NR_MG_enh2-perf] | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25
R4 | NR | NR_demod_enh3-Perf | WI | REL-18 |  | 0.5 |  | 1 |  | 1 |  | 1 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
R4 | NR | FS_SimBC | SI | REL-18 | 0.5 |  | 0.5 |  | 1 |  | 0.5 |  | 0.25 |  |  |  |  |  |  | 
R4 | NR | FS_NR_700800900_combo_enh | SI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | FS_NR_BS_RF_evo | SI | REL-18 | 0.25 |  | 0.25 |  | 0.5 |  | 0.5 |  | 0.25 |  |  |  |  |  |  | 
R4 | NR | FS_NR_FR2_OTA_enh | SI | REL-18 | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 1 | 0.5
R4 | NR | NonCol_intraB_ENDC_NR_CA-Core | WI | REL-18 | 0.5 |  | 0.5 | 0.25 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 |  |  |  | 
R4 | NR | NonCol_intraB_ENDC_NR_CA-Perf | WI | REL-18 |  |  |  |  |  |  |  | 0.25 |  | 0.25 |  | 0.25 |  | 0.25 |  | 0.25

## Slide 25: RAN4 TU Planning
The RAN4 TU budget for Rel-17 and Rel-18 approved WI/SI
Q4 2022 meeting plans:
  Finalization of Rel-17 Perf part
    A number of Rel-17 Perf parts will be postponed
  Start more Rel-18 items according to the TU planning
WG | RAT | WI code | WI or SI | Rel | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD | R4RF | R4RD
 |  |  |  |  | 104bis | 104bis | 105 | 105 | 106 | 106 | 106bis | 106bis | 107 | 107 | 108 | 108 | 108bis | 108bis | 109 | 109
R4 | NR | NR_HST_FR2_enh_Core | WI | REL-18 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 |  |  |  | 
R4 | NR | NR_HST_FR2_enh_Perf | WI | REL-18 |  |  |  |  |  |  |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
R4 | LTE, NR | NR_LTE_EMC_enh-Core | WI | REL-18 | 0.25 |  | 0.25 |  | 0.25 |  | 0.25 |  | 0.25 |  | 0.25 |  |  |  |  | 
R4 | LTE, NR, U/G | NR_LTE_EMC_enh-Perf | WI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  | 0.25 |  | 0.25 | 
R4 | NR | NR_ATG | WI | REL-18 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 1 | 0.25 | 1 |  | 1 | 
R4 | NR | NR_ATG | WI | REL-18 |  |  |  |  |  | 0.5 |  | 0.25 |  | 0.5 |  | 0.25 | 0.5 | 0.5 | 0.5 | 0.5
R4 | NR | FS_NR_eff_BW_util | SI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | FS_FR2_enhTestMethods | SI | REL-18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
R4 | LTE | LTE_NBIoT_eMTC_NTN_req-Core | WI | REL-18 | 0.5 | 0.25 | 0.5 | 0.25 |  |  |  |  |  |  |  |  |  |  |  | 
R4 | LTE | LTE_NBIoT_eMTC_NTN_req-Perf | WI | REL-18 |  | 0.25 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  |  |  |  | 
R4 | NR | Nominal TUs for Maintenance |  |  | 3.75 | 4.25 | 3.75 | 6.5 | 3 | 5 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2
R4 |  | Reserved TUs ([5%-15%] capacity) |  | REL-18 | 2.5 | 1.5 | 2.5 | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2.75 | 2
R4 | LTE, NR | Rel-17 performance part (remaining) |  | REL-17 |  | 3 |  | 0 |  |  |  |  |  |  |  |  |  |  |  | 
R4 | NR | Rel-18 TEIs & additional reserved TU |  |  | 0.5 |  | 0.5 |  | 0.5 | 0 | 0.5 | 0 | 0.25 | 0 | 0.5 | 0 | 0.5 |  | 0.5 | 
R4 | LTE, NR | Misc. impacts from other RAN WGs and TSGs (Rel-18 LS reply) |  | REL-18 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  |  |  | 
Total TUs |  |  |  |  | 24.5 | 20.5 | 24.5 | 20.5 | 24.25 | 20 | 23.75 | 18.5 | 23.5 | 18 | 23.5 | 17.5 | 23.5 | 18 | 23.5 | 18
RAN4 Capacity |  |  |  |  | 24.5 | 20.5 | 24.5 | 20.5 | 24.5 | 20.5 | 24.5 | 20.5 | 24.5 | 20.5 | 24.5 | 20.5 | 24.5 | 20.5 | 24.5 | 20.5
Available TUs |  |  |  |  | 0 | 0 | 0 | 0 | 0.25 | 0.5 | 0.75 | 2 | 1 | 2.5 | 1 | 3 | 1 | 2.5 | 1 | 2.5
The Perf parts to be extended to Dec2022
The Perf parts with target completion date Dec 2022
NR_FeMIMO-Perf (RRM, Demod)
NR_cov_enh-Perf (Demod)
NR_IIOT_URLLC_enh-Perf (Demod)
NR_SmallData_INACTIVE-Perf (RRM)
NR_repeaters-Perf (BS RF conformance)
NR_ext_to_71GHz
NR_redcap-Perf
NR_NTN_solutions

## Slide 26: Rel-17 feature list
Rel-17 feature list discussion was extensively discussed
  A number of LS-s were sent to RAN2
New Tdoc number | Title | Source
R4-2214217 | LS on Rel-17 RAN4 UE feature list for NR | CMCC
R4-2215144 | LS on Rel-17 RAN4 UE feature list for NR | CMCC

## Slide 27: TEI CR
No TEI Cat-B CR is agreed in RAN4 this quarter

## Slide 28: ITU-R on Generic unwanted emission (IMT-2020)
The dedicated agenda for ITU-R response was set in RAN4#104-e meeting.
  Generic unwanted emission (IMT-2020)
    The following LS was approved in RAN4 and sent to RAN
RP-221912 | Draft reply LS to ITU-R WP5D/TEMP/482(Rev.1) = RP-212699 on work towards two new recommendations "Generic unwanted emission characteristics of base stations/mobile stations using the terrestrial radio interfaces of IMT-2020" (R4-2214737; to: RAN; cc: RAN5; contact: Ericsson) | RAN4 | LS in |  | RAN #94e answered LSin ITU-R WP5D/TEMP/482(Rev.1) = RP-212699 in LSout RP-213642 (indicating that RAN can not reply by Jan.22 but plans a reply for June 22); RAN action requested | 8.2

## Slide 29: ITU-R on Generic unwanted emission (IMT-2020)
The dedicated agenda for ITU-R response was set in RAN4#104-e meeting.
  Generic unwanted emission (IMT-2020)
    The following LS was approved in RAN4 and sent to RAN
RP-221912 | Draft reply LS to ITU-R WP5D/TEMP/482(Rev.1) = RP-212699 on work towards two new recommendations "Generic unwanted emission characteristics of base stations/mobile stations using the terrestrial radio interfaces of IMT-2020" (R4-2214737; to: RAN; cc: RAN5; contact: Ericsson) | RAN4 | LS in |  | RAN #94e answered LSin ITU-R WP5D/TEMP/482(Rev.1) = RP-212699 in LSout RP-213642 (indicating that RAN can not reply by Jan.22 but plans a reply for June 22); RAN action requested | 8.2

## Slide 30: Thank You!
Many thanks to：
Vice chair Haijie Qiu and Session chair Meng Zhang for helping structure the e-meeting and chairing sessions
Carolyn Taylor for support
Email moderators for leading the email discussions and providing summaries
  Jinqiang Xing, Aida Vera Lopez, Aijun Cao, Alexander Sayenko, Ato Yu, Axel Muller, Basaier Jialade, Bin Han, Bo Liu, CH Park, Chrisitian Bergljung, Chunhui Zhang, Chunxia Guo, Daniel Poop, Dmitry Petrov, Dominique Brunel, Dominique Everaere, Dorin Panaitopol, Esther Sienkiewicz, Fei Xue, Gaurav Nigam, Gene Fong, Han Jing, He (Jackson) Wang, Hsuanli Lin, Hua Li, Huiping Shan, Ingo Wendler, Iwo Angelow, Jerry Cui, Jiakai Shi, Jin Wang, Jingjing Chen, Jingzhou Wu, Jin-yup Hwang, Johan Sköld, Johannes Hejselbaek, Kazuyoshi Uesaka, Lars Dalsgaard, Lei Du, Li Zhang, Liehai Liu, Man Hung Ng, Manasa Raghavan, Meng Zhang, Miao Wang, Michal Szydelko, Mueller Axel, Mohammad Abdi Abyaneh, Muhammad Kazmi, Ojas Choksi, Peng Zhang, Per Lindell, Petri Vasenkari, Phil Coan, Prashant Sharma, Qian Yang, Qifei Liu, Qiming Li, Qiuge Guo, Rafael Paiva, Richard Kybett, Richie Leo, Roy Hu, Rui Huang, Ruixin Wang, Sanjun Feng, Santhan Thangarasa, Shan Yang, Shiyuan Wang, Steven Chen, Su Hwan Lim, Sumant Iyer, Susanne Rath, Suzuki Yasuki, Taekhoon Kim, Tim Frost, Toni lahteensuo, Tricia Li, Ville Vintola, Wubin Zhou, Xiaoran Zhang, Xuan Yi, Xuhua Tao, Xusheng Wei, Yang Tang, Yankun Li, Ye Liu, Yiyan Zhang, Yoonoh Yang, Yuan Gao, Yuexia Song, Yunchuan Yang, Zhifeng Ma, Zhixun Tang, Zhongyi Shen
All the volunteer delegates help RAN4 merge endorsed draft CRs
Delegates for great contributions and discussions for finalization of Rel-17 extended WI and performance part in RAN4