## TS38.521-1<>TS38.101-1
POC - Company | email
Shirley (RAN5) - Huawei | yangyinghong@huawei.com
Ashwin(RAN5)- Qualcomm | mohana@qti.qualcomm.com
Ville (RAN4) - Qualcomm | vvintola@qti.qualcomm.com
Requirements Area | Items Pending on Ran-4 in 38.101-1 | example 36.101 LTE spec reference | Requested RAN4 completion Date | Anticipated target date for ran5 | Comments RAN5 | Comments RAN4
6.2.1 MOP and 6.3.3 Tx ON/OFF | 1. A few "?" in Section 6.2.1 related to Pmax 2. UL RMC(pi/2 BPSK, QPSK): Pending in Annex A.2 3. how to deal with TDD slots with transients for Tx On/Off test: Pending in sections 6.3.3.2/6.3.3.3 | UL RMC : Annex A.2 UL Transients: Section 6.3.4.1 | May-18 | Aug-18 | Huawei : UL RMC -> RAn5 will need guideline for code rate calculation for differnet RMC /Modulation scheme Assumption is no simulation work is needed for UL RMC | May'18 generic reequirements for MOP for some bands will be completed after May'18 the requirements for band which is not completed will be removed from REL15 WI UL RMC - Proposal to handover this work to RAN5 , RAn4 will give the guideline to RAN5 , way fwd is not agreed yet. UL RMC: E/// : UL/DL config is not finalized Target code rate can be provided, however not all modulation schemes has been finalized suggestion to propose the draft proposal of the work split QC: RAn4 expertize is needed for RMC Xutao: July'18 can be targetted for UL RMC TDD slots with transients: DCM: Agreement has not been reached on SSF Tx ON/OFF mask transients (time mask ) requirements is being worked on in May'18 Meeting UL RMC and Transient mask will be finalized in July, Agreement not to send the RMC work to RAN5
7.3 General Reference Sensitivity | 1 UL RMC : pending in Annex A.2 2. DL RMC for TDD pending in Annex A.3 3. OCNG defintion pending in Annex A.5 4. DL Signal level (PDSCH, PDCCH) pending in Annex C | UL RMC : Annex A.2 DL RMC : Annex A.3 OCNG: Annex A.5 DL Signal levels: Annex C.3.1 | May-18 | Aug-18 |  | DL RMC is full allocation we don’t need OCNG , however requirements does indicate OCNG as needed Suggest to have DL RMC /UL RMC , OCNG be completed in July Agreement not to send RMC and OCNG work to RAN5
6.4 Freq error and EVM | 1 Requirements are still in square brackets or TBD in section 6.4.1 and 6.4.2.x 2 Transmit modulation is incomplete in Annex-- Remove TBDs and square brackets | Section 6.5.1 and 6.5.2 Annex F.1 (Measurement point), F.2( EVM measurement defintion), F.4 ( Signal under test defintion), F.5 (Window Length) , F.6 (EVM averaging defintion) | May-18 | Aug-18 | 1 6.3 an 6.4 are EN-DC Dependencies | Will be on the agenda in Aug, discussions are happening in RAN4 and dependency not concluded

## TS38.521-3<>TS38.101-3
POC - Company | email
Ashwin(RAN5)- Qualcomm | mohana@qti.qualcomm.com
Yufeng(RAN5) - CATR(CAICT) | zhangyufeng@caict.ac.cn
Shirley (RAN5) - Huawei | yangyinghong@huawei.com
Ville (RAN4) - Qualcomm | vvintola@qti.qualcomm.com
Requirements Area | Items Pending on Ran-4 in 38.101-3 | Requested RAN4 Target Completion Date | Anticipated Ran-5 Completion Date | Comments RAN5 | Comments RAN4
Finalize requirement plan in 38.101-3 | Requirements for 6.2/6.3/6.4/ 6.5/7.4/7.5, if they would be added to 38.101-3 spec at all or not . What will be finalized by May-18 | May-18 | Aug-18 |  | 6.2 - > Planned to be completed in May meeting for both FR1/FR2- MPR and PCMax conclusion for FR2 EN-DC may take additional time 6.3 -> Planned to be completed in May meeting for both FR1/FR2 6.4 -> Same as standalone 6.5 -> Planned to be complete for FR1/FR2 in May 7.3 -> planned to be complete for FR1/FR2 in May 7.4-> SA requirement apply 7.5 -> SA requirements apply Applicability of SA requirement for EN-DC UE depends on UE capability For Interband with FR1/FR2 RAN5 can work based on SA requirements All interband cases Annex will not be completed
LTE Configuration | DL RMC, UL RMC, OCNG -- existing LTE configuration in 36.101 for each requirement be used? | May-18 | Aug-18 |  | for Inter band ENDC leverage LTE config from 36.101 for intraband ENDC LTE config is pending disucssion
5G-NR config dependency is same as 38.101-1/-2 | same as listed in 38.101-1/-2 sheets MPR config for EN-DC | Same dates as 38.101-1/-2 sheets | Same dates as 38.101-1/-2 sheets |  | MPR Config Is pending conclusion

## TS38.521-2<>TS38.101-2
POC - Company | email
Yufeng(RAN5) - CATR(CAICT) | zhangyufeng@caict.ac.cn
Ashwin (RAN5)- Qualcomm | mohana@qti.qualcomm.com
Ville (RAN4) - Qualcomm | vvintola@qti.qualcomm.com
Requirements Area | Items Pending on Ran-4 in 38.101-2 | Requested RAN4 Target Completion Date | RAN5 Target Completion Date of corresponding test cases (except for TT) | Comments RAN5 | Comments RAN4
Finalize requirement plan in 38.101-2 | Requirements for 6.2/6.3/6.4/ 6.5/7.4/7.5 are pending What will be finalized by May-18 | May-18 | Aug-18 |  | 6.2 may be completed in May 6.3 Pcmax discussion pending , Measurement BW pending 6.4 To be completed in May 6.5 To be completed in May 7.3 To be completed in July due to RMC 7.4 To be completed in July due to RMC 7.5 to be completed in July due to RMC
MOP (with EIRP and TRP requirements) | UL RMC , Tx Beam lock, UE vendor declaration (Different DUT categories, and radiating aperture), MPR Config to be finalized | May-18 | Aug-18 |  | UL RMC if there is no dependency on the requirement it can be handled in JULY , else it will be handled later Tx only beam lock can be used and if there are concerns then RAN5 sends an LS to RAN4 asking for clarity UE vendor declaration planned to be addressed in May MPR Config -> Is pending discussion
Ref sensitivity (with Rx peak beam EIS requirement) | DL RMC, Downlink physical channel , UL RMC, OCNG, Rx Beam lock, UE vendor declaration (Different DUT categories, and radiating aperture),, RSRP accuracy requirements | May-18 | Nov-18 |  | Requirement values to be finalized for EIS in May DL/UL RMC - can be planned in July UL RMC since this has requirment dependency it will need additional meeting time Rx Beam lock can be used and if there are concerns then RAN5 sends an LS to RAN4 UE vendor declaration planned to be addressed in MAY RSRP accuracy requirements: will need additional meeting time

## TR38.903<>TR38.810<>MU
POC - Company | email
Chunying(RAN5) - Huawei | guchunying <guchunying@huawei.com>
Edwin(RAN5)- R&S | Edwin Menzel <Edwin.Menzel@rohde-schwarz.com>
Ron(RAN5) - PC Test | Ron Borsato <ron.borsato@pctest.com>
Kim(RAN5)- MVG | RUTKOWSKI' <kim.rutkowski@mvg-world.com>
Emilio(RAN5)- Keysight | emilio_ruiz@keysight.com
Baba (RAN5)- Anritsu | Baba, Hiroyuki <Hiroyuki.Baba@anritsu.com>
Andrey (RAN4)- INTEL | andrey.chervyakov@intel.com
Requirements Area | Items Pending on Ran-4 | Requested RAN4 Target Completion Date | Anticipated Ran-5 Completion Date | Comments RAN5 | Comments RAN4
Type of UBF for MOP , REF sense | Need input on what type of UBF (Tx only , Rx Only , Tx+Rx) shall be used for MOP , Ref sense | May-18 | Aug-18 |  | upto RAn5 decision
Power supply cable | Whether to test with power supply cable or to test with battery is not yet concluded in RAN4(Editor's Note in 38.101-2 E.2.2 ). This can affect the MU estimation work(especially, QZ quality) in RAN5. All of the TRx tests are impacted. | May-18 | Aug-18 |  | Pending conclusion in RAN4, however it has been decided to have this in RAn5 scope, the suggestion is to use battery for testing
TRP Measurement grid | Expected RAN4 output: 1. Determine the minimum number of grid points for constant step size and constant density grids. 2. Clarify whether the TRP mean error for constant step size grid will be avoided in the test procedure for TRP measurements, e.g., by pointing the beam peak towards the equator. If yes, finalize the test procedure of TRP measurement for constant step size grid. If no, provide the additional MU due to the mean TRP error. 3. Clarify who(RAN4/RAN5) and how to decide the applicability of new type of measurement grid. 4. Provide baseline MU associated with the minimally acceptable grid for constant step size and constant density grids. | May-18 | Aug-18 |  | To be concluded in May and LS to be sent all listed items will be part of the LS in May
Tx and Rx Beam peak search grid | Expected RAN4 output: 1. Determine the minimum number of grid points for Tx beam peak search for constant step size and constant density grids. 2. Determine the minimum number of grid points for Rx beam peak search for constant step size and constant density grids. 3. Clarify who(RAN4/RAN5) and how to decide the applicability of new type of Tx/Rx beam peak search grid. 4. Provide baseline MU associated with the minimally acceptable grid for constant step size and constant density grids. | May-18 | Aug-18 |  | Will be included in the LS to be sent to RAN5 in May

## TS38.521-4<>TS38.101-4
POC - Company | email
Vijay (RAN5) - Qualcomm | vijayb@qti.qualcomm.com
Haijie (RAN4)- Samsung | haijie.qiu@samsung.com
Requirements Area | Items Pending on Ran-4 in 38.101-4 | example 36.101 LTE spec reference | Requested RAN4 Target Completion Date | Anticipated Ran-5 Completion Date | Comments RAN5 | Comments RAN4
DL Physical channel configuration | downlink physical channels that are needed for setting a connection and channels that are needed during a connection. Downlink Physical Channels transmitted during a connection | LTE 36.101 Annex C.3.2 | May-18 | Aug-18 |  | DL Physical channel signal depends on test case finalization
FR1 Single carrier Demodulation performance and CSI reporting requirements | Test area definition: PDSCH, PDCCH, SDR, CSI reporting, PMI/RI reporting | LTE 36.101 PDSCH: Section 8.2.x , PDCCH: 8.4.x SDR: 8.7.x CSI: 9.2.x, 9.3.x PMI : 9.4.x RI : 9.5.x | Aug-18 | Nov-18 |  | will be finalized by Dec
| Test case parameters definition: ChBW, SCS, BWP, CORESET, TDD UL/DL slot config, DL power allocation, Antenna correlation | LTE 36.101 Table 8.2.1-1, Table 8.2.1.4.1-1/-2 | Aug-18 | Jan-19 |  | will be finalized by Dec
| Annex contents: RMC, OCNG, propagation conditions (channel model, SNR, antenna correlation matrix) | LTE 36.101 Annex A.3.3, A.5, B, C | Aug-18 | Nov-18 |  | will be finalized by Dec
FR1 propagation conditions | Use the LTE channel models to start with | LTE 36.101 Annex B | Aug-18 | Nov-18 |  | will be finalized by Dec
NSA applicability | Applicability of FR1/FR2 demod test cases in NSA mode. Additional details like LTE config to use. |  | Aug-18 | Nov-18
FR2 single carrier Demodulation performance and CSI reporting requirements | Test area definition: for example PDSCH, PDCCH, SDR, CSI reporting, PMI/RI reporting | LTE 36.101 PDSCH: Section 8.2.x , PDCCH: 8.4.x SDR: 8.7.x CSI: 9.2.x, 9.3.x PMI : 9.4.x RI : 9.5.x | Nov-18 | Feb-19
| Test case parameters definition: for example ChBW, SCS, BWP, CORESET, TDD UL/DL slot config, DL power allocation, Antenna correlation | LTE 36.101 Table 8.2.1-1, Table 8.2.1.4.1-1/-2 | Nov-18 | May-19
| Annex contents: RMC, OCNG, propagation conditions (channel model, SNR, antenna correlation matrix) Reference LTE 36.101 Annex A.3.3, A.5, B, C, | LTE 36.101 Annex A.3.3, A.5, B, C | Nov-18 | Feb-19
FR2 propagation conditions | FR2 channel model to be used | LTE 36.101 Annex B | Nov-18 | Feb-19
RSRPB accuracy for FR2 Stage1/Stage2 Test Procedure | Finalize Accuracy of RSRPB to within single digit dB, it is critical for initial gNB<>DUT link calibration in FR2 mode |  | Aug-18 | Feb-19 |  | To be prioritized to help the FR2 testing procedure calibration RSRPB power meausrement relative or abs is not finalized

## TS38.533<>TS38.133
POC - Company | email
Adrian(RAN5) - R&S | Adrian Cardalda-Garcia <Adrian.Cardalda-Garcia@rohde-schwarz.com>
Yang (RAN4)- INTEL | yang.tang@intel.com
Test Requirements Area | Items Pending on Ran-4 | Requested RAN4 Target Completion Date | Anticipated target date for ran5 | Comments RAN5 | Comments RAN4
Finalize Annex plan in 38.133 | Test Case Annexes structure shall be finalized including at least high-level test case headers (i.e. Re-selection, Handover, RLM, etc.) | Aug-18 | Jan-19 |  | Planned in July
FR1 Test Cases #1 | 1. Initial set of high prio FR1 test cases shall be defined with test case title, test purpose and test metrics. 2. Critical test parameters (e.g. number of cells, number of time periods, approximate power levels) for the above mentioned test cases are specified. | Aug-18 | Feb-19 | TT+3 months | Planned in Dec
FR2 Test Method #1 | OTA Test method baseline shall be finalized | Aug-18 | N.A. | Test Method is a pre-requisite to be able to test FR2 | Planned completion was June it may be extended to Aug
RSRPB accuracy for FR2 Stage1/Stage2 Test Procedure | Finalize Accuracy of RSRPB to within single digit dB, it is critical for initial gNB<>DUT link calibration in FR2 mode | Aug-18 | Feb-19 |  | To be prioritized to help the FR2 testing procedure calibration RSRPB power meausrement relative or abs is not finalized
RSRP accuracy | finalize Accuracy of RSRP, it is critical for 3D Beam peak search used for Reference sensitivity, MOP | May-18 | Nov-18 |  | RSRP accuracy requirements: will need additional meeting time

## TS37.571-1<>TS36_37.171,38.133
POC - Company | email
Adrian (RAN5)- R&S | Adrian Cardalda-Garcia <Adrian.Cardalda-Garcia@rohde-schwarz.com>
Yang (RAN4)- INTEL | yang.tang@intel.com
Test Requirements Area | Items Pending on Ran-4 | Requested RAN4 Target Completion Date | Anticipated target date for ran5 | Comments RAN5 | Comments RAN4
Open questions about positioning for NR | - Do the RAT Independent positioning requirements in TS 36.171 (A-GNSS) and TS 37.171 (TBS, WLAN, BLE) apply also to NR (in particular SA, Option 2)? - If yes, for FR2, the OTA Test method shall be defined (probably as NR is just a link for the positioning session, NF NR link with conducted A-GNSS, WLAN, BLE or TBS is sufficient). - Do we expect any test requirements for RSTD / RxTx measurements in TS 38.133 for NR? | Nov-18 | May-19 |  | RAT independent requirement is not in the scope of 5G-NR WID RSTD / RxTx measurements in TS 38.133 for NR is part of 5G-NR Rel15 WID planned by dec