## Cover sheet
3GPP TSG-RAN WG5 Meeting #92-e | [10 empty] | R5-214577
Electronic Meeting, 16th – 27th Aug 2021
Agenda Item: | 7.4.2
Source: | CATT
Title: | Work plan: UE Conformance Test Aspects for NR Positioning Support
Work item code: | NR_pos-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#90-e meeting a Rel-16 RAN5 work item for UE Conformance Test Aspects for NR Positioning Support (NR_pos-UEConTest) was approved [1]. The purpose of this present document is to provide a work plan for the RAN5 work item for this. The work plan is updated after each RAN5 meeting to give the status of this work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 13% (+2%) | 0 | 20 (+4)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 12.6% (+2.5%) | 0 | 20 (+4)
FR1 |  | 12.6% (+2.5%) | 0 | 20 (+4)
FR2 |  | 12.6% (+2.5%) | 0 | 20 (+4)
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0% |  |  | 0%
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0%
Special conformance testing functions | 38.509 | 0% |  |  | 0% |  |  | 0%
NR RF/RRM
Test Tolerances analysis RRM and RF Rx test cases | 38.903
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1 | 3.8% (+3.8%) | 0 | 20 (+4) | 3.8% (+3.8%) | 0 | 20 (+4) | 3.8% (+3.8%) | 0 | 20 (+4)
UE Positioning Protocol test cases | 37.571-2 | 96.4% (+13.6%) |  |  | 96.4% (+13.6%) |  |  | 96.4% (+13.6%)
Applicability and ICS UE Positioning test cases | 37.571-3 | 83.3% (-0%) |  |  | 83.3% |  |  | 83.3%
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-202727 | UE Conformance Test Aspects for NR Positioning Support
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects for NR Positioning Support | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_pos-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for NR Positioning Support | [12 empty] | vs Area
WP Resp: |  | Xiaoyang TIAN, CATT |  |  | tianxiaoyang@catt.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2 | FR1 + FR2
[14 empty] | 12.6% (+2.5%) | 12.6% (+2.5%)
[14 empty] | 51 (+1) | 51 (+1) | 0
[14 empty] | 26.5 (+5) | 26.5 (+5) | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.6 | Introduction of information elements for Release-16 NR positioning support | 1. Adding positioning UL-SRS parameters in SRS-Config 2. Adding positioning system information blocks associated parameters in chapter 4.6.2A |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | A.4 | Introduction of UE capabilities for Release-16 NR positioning support | Adding Release-16 NR positioning capability parameters according to TS 38.306 |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
TS 38.509: Special conformance testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
31 |  | 38.509 |  | Update RESET UE POSITIONING STORED INFORMATION message | Update RESET UE POSITIONING STORED INFORMATION message for Rel 16 NR positioning support |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
NR RF/RRM
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
3 |  | 38.903 | <Clause> | Introduction of test tolerances and measurements uncertainty for Release-16 NR positioning support | Introduction of test tolerances and measurements uncertainty for Release-16 NR positioning support |  | TBD |  |  | TBD | 0% | 0% |  | 0% | 0%
UE Positioning
TS 37.571-1: UE Positioning -Performance
|  | 37.571-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
4 |  | 37.571-1 | 2, 3 | Introduction of Release-16 NR positioning RF conformance contents | 1. Adding reference of TS 38.133 2. Adding Release-16 NR positioning methods associated definitions and abbreviations |  | TBD | R5-215973 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
5 |  | 37.571-1 | 4.15 | Addition of Multi-RTT test conditions | Adding Multi-RTT conditions |  | TBD | R5-215973 |  | 0.1 | 70% (+70%) | 70% (+70%) |  | 70% | 70%
6 |  | 37.571-1 | 4.16 | Addition of DL-AoD test conditions | Adding DL-AoD test conditions |  | TBD | R5-215973 |  | 0.1 | 67.5% (+67.5%) | 67.5% (+67.5%) |  | 65% | 70%
7 |  | 37.571-1 | 4.17 | Addition of DL-TDOA test conditions | Adding DL-TDOA test conditions |  | TBD | R5-215973 |  | 0.1 | 70% (+70%) | 70% (+70%) |  | 70% | 70%
8 |  | 37.571-1 | 14 | NR RSTD measurement requirements |  |  | TBD
32 | Y | 37.571-1 | 14.2 | NR RSTD measurement period test case for single positioning frequency layer in FR1 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.2.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
33 | Y | 37.571-1 | 14.3 | NR RSTD measurement period test case for dual positioning frequency layers in FR1 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.2.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
34 | Y | 37.571-1 | 14.4 | NR RSTD measurement accuracy test case for single positioning frequency layer in FR1 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 10.1.23 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
35 | Y | 37.571-1 | 14.5 | NR RSTD measurement accuracy test case for dual positioning frequency layer in FR1 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 10.1.23 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
36 | Y | 37.571-1 | 14.6 | NR RSTD measurement period test case for single positioning frequency layer in FR2 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.2.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
37 | Y | 37.571-1 | 14.7 | NR RSTD measurement period test case for dual positioning frequency layers in FR2 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.2.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
38 | Y | 37.571-1 | 14.8 | NR RSTD measurement accuracy test case for single positioning frequency layer in FR2 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 10.1.23 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
39 | Y | 37.571-1 | 14.9 | NR RSTD measurement accuracy test case for dual positioning frequency layer in FR2 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 10.1.23 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
9 |  | 37.571-1 | 15 | NR Rx-Tx Time Difference measurement requirements |  |  | TBD
40 | Y | 37.571-1 | 15.2 | UE Rx-Tx time difference measurement period for single positioning frequency layer in FR1 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.4.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
41 | Y | 37.571-1 | 15.3 | UE Rx-Tx time difference measurement period for dual positioning frequency layers in FR1 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.4.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
42 | Y | 37.571-1 | 15.4 | UE Rx-Tx time difference measurement accuracy for single positioning frequency layer in FR1 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 10.1.25 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
43 | Y | 37.571-1 | 15.5 | UE Rx-Tx time difference measurement period for single positioning frequency layer in FR2 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.4.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
44 | Y | 37.571-1 | 15.6 | UE Rx-Tx time difference measurement period for single positioning frequency layer in FR2 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.4.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
45 | Y | 37.571-1 | 15.7 | UE Rx-Tx time difference measurement accuracy for dual positioning frequency layers in FR2 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 10.1.25 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
10 |  | 37.571-1 | 16 | PRS-RSRP measurement requirements
46 | Y | 37.571-1 | 16.2 | PRS-RSRP measurement period test case for single positioning frequency layer in FR1 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.3.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
47 | Y | 37.571-1 | 16.3 | PRS-RSRP measurement period test case for dual positioning frequency layer in FR1 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.3.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
48 | Y | 37.571-1 | 16.4 | PRS-RSRP measurement accuracy with PRS in FR1 | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 10.1.24 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
49 | Y | 37.571-1 | 16.5 | PRS-RSRP measurement period test case for single positioning frequency layer in FR2 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.3.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
50 | Y | 37.571-1 | 16.6 | PRS-RSRP measurement period test case for dual positioning frequency layer in FR2 SA | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 9.9.3.5 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
51 | Y | 37.571-1 | 16.7 | PRS-RSRP measurement accuracy with PRS in FR2 | Adding test cases to verify the UE meet the measurements requirements in TS 38.133 clause 10.1.24 |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
52 |  | 37.571-1 | Annex | Annex
53 |  | 37.571-1 | Annex | Addition of conditions for NR PRS-based measurements and connection diagrams | Addition of conditions for NR PRS-based measurements and connection diagrams |  | TBD | R5-215974 |  | 1 | 50% (+50%) | 50% (+50%) |  | 50% | 50%
TS 37.571-2: UE Positioning -Protocol
|  | 37.571-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
11 |  | 37.571-2 | 2, 3 | Introduction of Release-16 NR positioning protocol conformance contents | 1. Adding reference of TS 37.355, TS 38.305 and TS 38.331 2. Adding Release-16 NR positioning methods associated abbreviations | CATT | RAN5#91-e (May-21) | R5-202537 |  | 0.1 | 100% | 100% |  | 100% | 100%
12 |  | 37.571-2 | 8 | Addition of Release-16 NR positioning into default conditions for NR | 1. Adding sub-test definitions in Table 8.1-1 2. Adding Multi-RTT, DL-AoD and DL-TDOA simulated environment in clause 8.2 3. Adding RRC message contents to configure sounding reference signal (SRS) in clause 8.3 4. Adding definition of LPP REQUEST CAPABILITIES message in 8.4 5. Adding definition of LPP REQUEST LOCATION INFORMATION message in 8.4 6. Adding Multi-RTT, DL-AoD and DL-TDOA Assistance Data Elements in clause 8.4.1 | CATT | RAN5#92 (Aug-21) | R5-202537 R5-216323 R5-215616 |  | 0.5 | 100% (+30%) | 100% (+30%) |  | 100% | 100%
13 |  | 37.571-2 | 9.3.1.1 | Introduction of Release-16 NR positioning methods in Position Capability Transfer | Updating the tables in specific message contents | CATT | RAN5#91-e (May-21) | R5-202536 R5-216322 |  | 0.1 | 100% | 100% |  | 100% | 100%
14 |  | 37.571-2 | 9.3.1.2 | Introduction of Release-16 NR positioning methods in LPP Abort | 1. Adding Release-16 NR positioning methods associated sub-test 2. Updating the tables in specific message contents | CATT | RAN5#91-e (May-21) | R5-202536 |  | 0.1 | 100% | 100% |  | 100% | 100%
15 |  | 37.571-2 | 9.3.2 | Introduction of Release-16 NR positioning methods into LPP Transport | Updating the tables in specific message contents | CATT | RAN5#91-e (May-21) | R5-202536 |  | 0.1 | 100% | 100% |  | 100% | 100%
16 |  | 37.571-2 | 9.3.3.1B | Introduction of Release-16 NR positioning methods into LPP Error handling | 1. Adding Release 16 NR positioning methods features into the test case 2. Updating the tables in specific message contents 3. Addting the table for RESET UE POSITIONING STORED INFORMATION message | CATT | RAN5#91-e (May-21) | R5-202536 |  | 0.1 | 80% | 80% |  | 80% | 80%
17 |  | 37.571-2 | 9.3.4 | Introduction of Release-16 NR positioning methods into LPP Positioning Procedures | 1. Adding Release 16 NR positioning methods features into the test case 2. Updating the tables in specific message contents 3. Addting the table for RESET UE POSITIONING STORED INFORMATIONi message | CATT | RAN5#91-e (May-21) | R5-202536 |  | 0.1 | 80% | 80% |  | 80% | 80%
TS 37.571-3: Applicability and ICS UE Positioning test cases
|  | 37.571-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
18 |  | 37.571-3 | 2, 3 | Introduction of Release-16 NR positioning support in common contents | 1. Adding reference of TS 37.355 2. Adding Release-16 NR positioning methods associated definitions and abbreviations | CATT | RAN5#91-e (May-21) | R5-202535 |  | 0.1 | 100% | 100% |  | 100% | 100%
19 |  | 37.571-3 | 4 | Introduction of test case applicability for Release-16 NR positioning support | 1. Adding test applicability and additional information for new TS 37.571-2 NR test cases in Table 4-9 2. Adding test applicability and additional information for new TS 37.571-1 NR test cases in Table 4-11 | CATT | TBD | R5-202534 |  | 0.1 | 50% | 50% |  | 50% | 50%
20 |  | 37.571-3 | Annex A | Addition of PICS for Release-16 NR Positioning Support | Adding Release-16 NR positioning support related PICS according to TS 37.355 | CATT | RAN5#91-e (May-21) | R5-202535 R5-216324 |  | 0.1 | 100% | 100% |  | 100% | 100%
TS 37.571-4: UE Positioning test suites (TTCN)
|  | 37.571-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
21 |  | 37.571-4 | <Clause> | Test suites for R16 NR positioning support | <Describe task> |  | TBD |  | Progress of TTCN development is tracked in MCC TF160 reports to RAN5/RAN | TBD | 0% | 0% |  | 0% | 0%
TS 37.571-5: UE Positioning test scenarios and assistance data
|  | 37.571-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
22 |  | 37.571-5 | 2, 3 | Introduction of Release-16 NR positioning protocol conformance contents | 1. Adding reference of TS 37.355 2. Adding Release-16 NR positioning methods associated definitions and abbreviations |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
23 |  | 37.571-5 | 4.6 | Addition of Multi-RTT scenario and assistance data | Adding description of Multi-RTT scenario and assistance data |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
24 |  | 37.571-5 | 4.7 | Addition of DL-AoD scenario and assistance data | Adding description of DL-AoD scenario and assistance data |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
25 |  | 37.571-5 | 4.8 | Addition of DL-TDOA scenario and assistance data | Adding description of DL-TDOA scenario and assistance data |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
26 |  | 37.571-5 | 4.9 | Addition of NR Enhanced Cell ID scenario and assistance data | Adding description of NR-ECID scenario and assistance data |  | TBD |  |  | 0.1 | 0% | 0% |  | 0% | 0%
27 |  | 37.571-5 | 11 | Addition of Multi-RTT positioning information | Adding Multi-RTT scenario and assistance data for signalling and minimum performance test cases in TS 37.571-1 and TS 37.571-2 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
28 |  | 37.571-5 | 12 | Addition of DL-AoD positioning information | Adding DL-AoD scenario and assistance data for signalling and minimum performance test cases in TS 37.571-1 and TS 37.571-2 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
29 |  | 37.571-5 | 13 | Addition of DL-TDOA positioning information | Adding DL-TDOA scenario and assistance data for signalling and minimum performance test cases in TS 37.571-1 and TS 37.571-2 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
30 |  | 37.571-5 | 14 | Addition of NR-ECID positioning information | Adding NR-ECID scenario and assistance data for signalling and minimum performance test cases in TS 37.571-1 and TS 37.571-2 |  | TBD |  |  | 0.5 | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.