## Cover sheet
RAN5 meeting #92e | [10 empty] | R5-214954
Electronic meeting, 16th August - 27th August 2021
Agenda Item: | 7.4.2
Source: | Qualcomm Incorporated
Title: | WP UE Conformance Test Aspects - Support of eCall over IMS for NR
Work item code: | NR_EIEI-UEConTest
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work plan is to define the UE conformance test aspects corresponding to WID on Rel-16 Support of eCall over IMS for NR.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 14% (+14%) | 0 | 17 (+17)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 14.1% (+14.1%) | 0 | 17 (+17)
FR1 |  | 14.1% (+14.1%) | 0 | 17 (+17)
FR2 |  | 14.1% (+14.1%) | 0 | 17 (+17)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 53.3% (+53.3%) |  |  | 53.3% (+53.3%) |  |  | 53.3% (+53.3%)
Common ICS | 38.508-2 | 0% |  |  | 0% |  |  | 0%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% | 0 | 8 (+8) | 0% | 0 | 8 (+8) | 0% | 0 | 8 (+8)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5 | 11% (+11%) | 0 | 9 (+9) | 11% (+11%) | 0 | 9 (+9) | 11% (+11%) | 0 | 9 (+9)
Applicability and ICS IMS test cases | 34.229-2 | 5% (+5%) |  |  | 5% (+5%) |  |  | 5% (+5%)
IMS Test suite (TTCN) | 34.229-3
5 References
[1] RP-210704 | Support of eCall over IMS for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Support of eCall over IMS for NR | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_EIEI-UEConTest
WP Scope: |  | The objective of this work plan is to define the UE conformance test aspects corresponding to WID on Rel-16 Support of eCall over IMS for NR. | [12 empty] | vs Area
WP Resp: |  | Bharadwaj Kumar Cheruvu |  |  | bcheruvu@qti.qualcomm.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 14.1% (+14.1%) | 14.1% (+14.1%)
[14 empty] | 28 (+28) | 28 (+28)
[14 empty] | 19.9 (+19.9) | 19.9 (+19.9)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
3 |  | 38.508-1 | 4 | Addition of generic procedures for ecall over IMS for NR |  |  | RAN5#93 (Nov-21) | R5-216328 | 1. Genric procedure for NR ecall over IMS when UE is in normal service 2. Genric procedure for NR ecall over IMS when UE is in limited service | 0.5 | 40% (+40%) | 40% (+40%) |  | 40% | 40%
26 |  | 38.508-1 | 4 | ASN.1 update for ecall over IMS for NR |  |  | RAN5#92 (Aug-21) | R5-216327 |  | 0.5 | 60% (+60%) | 60% (+60%) |  | 60% | 60%
27 |  | 38.508-1 | 4 | USIM configuration update |  |  | RAN5#92 (Aug-21) | R5-216329 |  | 0.5 | 60% (+60%) | 60% (+60%) |  | 60% | 60%
TS 38.508-2: Common ICS
4 |  | 38.508-2 | A.4 | Introduce PICS parameters for eCall over IMS for NR test cases | Add new ICS statements |  | RAN5#93 (Nov-21) |  | If there is any UE which supports NR eCall but not NG eCall? | 0.1 | 0% | 0% |  | 0% | 0%
RAN and CN protocol
TS 38.523-1: Protocol test cases
General tests
2 |  | 38.523-1 | 11.5 | eCall over IMS | New sub-clause header |  |  |  |  | 0
5 | Y | 38.523-1 | 11.5.1 | eCall Only mode / T3444 / eCall inactivity procedure / Removal of eCall only restriction after an eCall over IMS / 5GS to EPS |  |  | RAN5#93 (Nov-21) |  | LTE test case 11.3.1 | 1 | 0% | 0% |  | 0% | 0%
6 | Y | 38.523-1 | 11.5.2 | eCall Only mode / T3445 / eCall inactivity procedure / Removal of eCall only restriction after a call to URI for test service / 5GS to EPS |  |  | RAN5#93 (Nov-21) |  | LTE test case 11.3.2 | 1 | 0% | 0% |  | 0% | 0%
7 | Y | 38.523-1 | 11.5.3 | eCall Only mode / 5GS supports IMS voice over PS session / 5GS does not support emergency service / eCall over EPS / eCall using eCall using CS domain / eCall failure if EPS and CS domain are not available |  |  | RAN5#93 (Nov-21) |  | LTE test case 11.3.4 | 1 | 0% | 0% |  | 0% | 0%
8 | Y | 38.523-1 | 11.5.4 | eCall Only mode / 5GS supports IMS voice over PS session / 5GS supports emergency service / eCall over IMS is supported / RACH failure in NR cell / eCall over EPS |  |  | RAN5#94 (Feb-22) |  |  | 1 | 0% | 0% |  | 0% | 0%
9 | Y | 38.523-1 | 11.5.5 | eCall Only mode / Limited service state / Call to URI for test service should not be attempted / eCall over IMS should be attempted / 5GS |  |  | RAN5#94 (Feb-22) |  | LTE test case 11.3.6 | 1 | 0% | 0% |  | 0% | 0%
10 | Y | 38.523-1 | 11.5.6 | eCall capable / 5GS supports IMS voice over PS session / 5GS supports emergency service / eCall over IMS is not supported / eCall using the CS domain / emergency call over IMS if eCall using the CS domain is not available / UTRA |  |  | RAN5#94 (Feb-22) |  | LTE test case 11.3.3 | 1 | 0% | 0% |  | 0% | 0%
29 | Y | 38.523-1 | 11.5.7 | eCall Only mode / SRVCC Handover to CS domain / UTRAN / MSD Update / Success / 5GS |  |  | RAN5#94 (Feb-22) |  | LTE test case 11.3.7 | 1 | 0% | 0% |  | 0% | 0%
30 | Y | 38.523-1 | 11.5.8 | eCall Only mode / 5GS supports IMS voice over PS session / 5GS supports emergency service / eCall over IMS is supported / RACH failure in NR cell / eCall using the CS domain |  |  | RAN5#94 (Feb-22) |  | LTE test case 11.3.5 | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
11 |  | 38.523-2 | 4.1, 4.2 | Add test case applicability statements for the new test cases introduced in 38.523-1 | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | RAN5#94 (Feb-22) |  | Addition of applicability conditions for 38.523-1 test cases | 0.1 | 0% | 0% |  | 0% | 0%
TS 38.523-3: Protocol test suites (TTCN)
12 |  | 38.523-3 | TBD | Introduction of Signaling Test Environment for eCall over IMS for NR |  |  | RAN5#94 (Feb-22) |  | Test model for NR EIEI | TBD | 0% | 0% |  | 0% | 0%
IMS
TS 34.229-1: IMS over LTE protocol test cases
1 |  | 34.229-1 | TBD | TBD | New sub-clause header sub-clause task to be identified |  | TBD |  | Placeholder for adding conditions related to NR EIEI in Annex A | 0 | 0% | 0% |  | 0% | 0%
TS 34.229-5: IMS over 5GS protocol test cases
28 |  | 34.229-5 | Annex | Addition of generic procedures for ecall over IMS for NR |  |  | RAN5#93 (Nov-21) | R5-216331 | Generic procedure for NR EIEI call setup and MSD update | 1 | 40% (+40%) | 40% (+40%) |  | 40% | 40%
13 |  | 34.229-5 | 11 | eCall over IMS | New sub-clause header |  |  |  |  | 0
14 | Y | 34.229-5 | 11.1 | eCall over IMS / Manual initiation / Normal registration / Emergency registration / Success / 200 OK with ACK / 5GS | 24.229, cl. 5.1.6.11.1, 5.1.6.11.2 |  | RAN5#93 (Nov-21) | R5-216332 | LTE test case 21.1 | 1 | 70% (+70%) | 70% (+70%) |  | 70% | 70%
15 | Y | 34.229-5 | 11.2 | eCall over IMS / Automatic initiation / Normal registration / Emergency registration / Success / 200 OK with ACK / 5GS | 24.229, cl. 5.1.6.11.1, 5.1.6.11.2 |  | RAN5#93 (Nov-21) |  | LTE test case 21.2 | 1 | 0% | 0% |  | 0% | 0%
16 | Y | 34.229-5 | 11.3 | eCall over IMS / Manual initiation / MSD transfer Failure / UE performs eCall in CS domain after Timer expiry / UTRAN or GERAN / 5GS | 24.229, 5.1.6.11.3 |  | RAN5#93 (Nov-21) |  | LTE test case 21.3 | 1 | 0% | 0% |  | 0% | 0%
17 | Y | 34.229-5 | 11.4 | eCall over IMS / Manual initiation / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / Success / 5GS | 24.229, 5.1.6.11.3 |  | RAN5#93 (Nov-21) |  | LTE test case 21.4 | 1 | 0% | 0% |  | 0% | 0%
18 | Y | 34.229-5 | 11.5 | eCall over IMS / Automatic initiation / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / Success / 5GS | 24.229, 5.1.6.11.3 |  | RAN5#94 (Feb-22) |  | LTE test case 21.5 | 1 | 0% | 0% |  | 0% | 0%
19 | Y | 34.229-5 | 11.6 | eCall over IMS / Automatic initiation / MSD transfer and 200 OK with ACK / SIP INFO request for unsupported MSD / UE indicates unsuccessful in SIP INFO / 5GS | 24.229, 5.1.6.11.3 |  | RAN5#94 (Feb-22) |  | LTE test case 21.6 | 1 | 0% | 0% |  | 0% | 0%
20 | Y | 34.229-5 | 11.7 | eCall only mode / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 486 (Busy Here) / UE performs eCall in CS domain / UTRAN or GERAN / 5GS | 24.229, cl. 5.1.6.11.1, 5.1.6.11.2 |  | RAN5#93 (Nov-21) |  | LTE test case 21.13 | 1 | 0% | 0% |  | 0% | 0%
21 | Y | 34.229-5 | 11.8 | eCall only mode / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 600 (Busy Everywhere) / UE performs eCall in CS domain / UTRAN or GERAN / 5GS | 24.229, cl. 5.1.6.11.1, 5.1.6.11.2 |  | RAN5#94 (Feb-22) |  | LTE test case 21.16 | 1 | 0% | 0% |  | 0% | 0%
22 | Y | 34.229-5 | 11.9 | eCall only mode / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 603 (Decline) / UE performs eCall in CS domain / UTRAN or GERAN / 5GS | 24.229, cl. 5.1.6.11.1, 5.1.6.11.2 |  | RAN5#94 (Feb-22) |  | LTE test case 21.18 | 1 | 0% | 0% |  | 0% | 0%
TS 34.229-2: Applicability and ICS for IMS protocol test cases
23 |  | 34.229-2 | A.4 | Introduce PICS parameters for eCall over IMS for NR test cases | Add new ICS statements. |  | RAN5#93 (Nov-21) |  | To add PICS parmaters for support of NR eCall feature | 0.1 | 0% | 0% |  | 0% | 0%
24 |  | 34.229-2 | 4.2 | Add applicabilities of new test cases | Add test case applicability statements for the new test cases introduced in 34.229-1 and/or 34.229-5. |  | RAN5#94 (Feb-22) | R5-216330 | Addition of applicability conditions for 34.229-5 test cases | 0.1 | 10% (+10%) | 10% (+10%) |  | 10% | 10%
TS 34.229-3: IMS test suite (TTCN)
25 |  | 34.229-3 | TBD | Introduction of Signaling Test Environment for eCall over IMS for NR |  |  | RAN5#94 (Feb-22) |  | IMS Test model for NR EIEI | TBD | 0% | 0% |  | 0% | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.