3GPP TSG-RAN WG5 Meeting #107							        	       R5-252193

Malta, MT, 19th - 23rd May 2025

3GPP TSG RAN Meeting #108								                        RP-25xxxx

Prague , CZ, 9th - 13rd June 2025

Status Report to TSG

Agenda item:			7.5.2

| WI / SI Name | UE Conformance - Further NR coverage enhancements |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: No | Performance part: No |  | Testing part: Yes |
| Acronym | NR_cov_enh2-UEConTest |  |  |  |  |
| Unique ID | 1030069 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-240345 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: N/A | Core part: N/A | Performance part: N/A | Testing part: 12/2025 |  |
| Overall Completion level | Study Item: N/A | Core part: N/A | Performance Part: N/A | Testing part: 76% (+46%) |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | TSG RAN WG5 |
| --- | --- | --- |
| Rapporteur | Name | Weichen Ning |
|  | Company | China Telecom |
|  | Email | ningwc@chinatelecom.cn |
|  | Name | Xuesong Wang |
|  | Company | Huawei, Hisilicon |
|  | Email | wangxuesong743@huawei.com |
|  | Name | Mohan, Ashwin |
|  | Company | Apple |
|  | Email | ashwin mohan@apple.com |

1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table:

2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

2.1	RAN1

2.1.1	Agreements

2.1.2	Remaining Open issues

2.2	RAN2

2.2.1	Agreements

2.2.2	Remaining Open issues

2.3	RAN3

2.3.1	Agreements

2.3.2	Remaining Open issues

2.4	RAN4

2.4.1	Agreements

2.4.2	Remaining Open issues

2.5	RAN5

2.5.1	Agreements

Status after RAN5#107:

- The work plan has been agreed [1].

- 13 CRs were agreed.

- The overall progress is 76%.

2.5.2	Remaining Open issues

2.5.3	Remaining Open issues with cross-WG dependencies

2.6	RAN6

2.6.1	Agreements

2.6.2	Remaining Open issues

3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

3.1	SAx/CTs

3.1.1	Agreements with cross-TSG impacts

3.1.2	Remaining Open issues with cross-TSG impacts

4.	References

General Papers:

- R5-252192 WP for UE Conformance - Further NR coverage enhancements, China Telecom, Huawei, Hisilicon. RAN5#107

TS 38.508-1 CRs

- R5-252734 Addition of default configurations of DCI formats for dynamic waveform switching SIG test cases, Huawei, HiSilicon. RAN5#107

- R5-253436 Addition of RRC IE for R18 coverage enhancement, CMCC. RAN5#107

TS 38.508-2 CRs

- R5-252331 Addition of PICS for further NR coverage enhancement, Lenovo. RAN5#107

- R5-253152 Addition of PICS for dynamic waveform switching SIG test cases, Huawei, HiSilicon. RAN5#107

TS 38.521-1 Tx CRs

- R5-253435 Update to Tx TCs for R18 coverage enh, CMCC. RAN5#107

TS 38.521-3 Tx CRs

- R5-252430 Update to R18 Coverage enh higherpowerlimit TC of EN-DC, China Telecom. RAN5#107

TS 38.522 CRs

TS 38.523-1 CRs

- R5-253153 Correction to Cov_Enh2 SIG test case 7.1.1.1.21 - SI request, Huawei, HiSilicon. RAN5#107

- R5-253155 New test case for CFRA msg1 repetition, Lenovo. RAN5#107

- R5-253156 New test case for DPC PHR, Lenovo. RAN5#107

- R5-253157 New test case for assumed PUSCH PHR, Lenovo. RAN5#107

- R5-252736 Addition of Cov_Enh2 SIG test case 7.1.1.3.24 - DWS DCI 0_1, Lenovo. RAN5#107

TS 38.523-2 CRs

- R5-253154 Addition of applicability for Cov_Enh2 SIG test case 7.1.1.3.24, Huawei, HiSilicon. RAN5#107

- R5-253158 Applicability for new further NR coverage enhancement test cases, Lenovo. RAN5#107

TS 38.523-3 CRs

30.04.2024		minor adaptations for RAN #104

16.02.2024		minor adaptations for RAN #103

10.11.2023		minor adaptations for RAN #102

02.08.2023		minor adaptations for RAN #101

26.04.2023		minor adaptations for RAN #100

01.02.2023		minor adaptations for RAN #99

27.10.2022		minor adaptations for RAN #98e

01.08.2022		minor adaptations for RAN #97e

21.05.2022		minor adaptations for RAN #96

10.01.2022		minor adaptations for RAN #95e

04.10.2021		minor adaptations for RAN #94e

08.08.2021		minor adaptations for RAN #93e

17.05.2021		minor adaptations for RAN #92e

28.01.2021		minor adaptations for RAN #91e

09.11.2020		minor adaptations for RAN #90e

31.08.2020		minor adaptations for RAN #89e

20.04.2020		minor adaptations for RAN #88e

18.02.2020		minor adaptations for RAN #87e

14.11.2019		minor adaptations for RAN #86

18.08.2019		minor adaptations for RAN #85

12.05.2019		minor adaptations for RAN #84

27.02.2019		minor adaptations for RAN #83

21.11.2018		completion levels with colours added (for RAN #82)

v04.81	31.07.2018		simplification of template and addition of cross-TSG aspects (for RAN #81)

v04.80	21.05.2018		minor adaptations for RAN #80

v04.79	26.02.2018		minor adaptations for RAN #79

v04.78	18.11.2017		minor adaptations for RAN #78

v04.77	06.08.2017		minor adaptations for RAN #77

v04.76	15.05.2017		minor adaptations for RAN #76

v04.75	31.01.2017		minor adaptations for RAN #75

v04.74	28.10.2016		minor adaptations for RAN #74

v04.73	01.09.2016		adaptations for RAN #73 (time units in extra Excel table, RAN6 reporting included)

v04.72	26.05.2016		adaptations for RAN #72 (introduction of NR & GERAN TUs)

v04.71	10.02.2016		minor adaptations for RAN #71

v04.70	30.10.2015		minor adaptations for RAN #70

v04.69	12.08.2015		minor adaptations for RAN #69

v04.68	21.05.2015		minor adaptations for RAN #68

v04.67	01.02.2015		minor adaptations for RAN #67

v04.66	16.11.2014		minor adaptations for RAN #66

v04.65	16.08.2014		minor adaptations for RAN #65

v04.64	22.05.2014		minor adaptations for RAN #64

v04.63	24.01.2014		restructuring for RAN #63 to cover Core & Perf. in one doc file

v03.62	11.11.2013		section 1.2.3 adapted for RAN #62

v03	11.08.2013		section 1.2.3 added on time budget

v02	07.05.2010		history added, some spelling corrections

v01	13.11.2009		First version of the template