## Cover sheet
3GPP TSG-RAN WG5 Meeting #107 | [7 empty] | R5-253582
St. Julian's, Malta, May 19th - May 23rd, 2025
Agenda Item: | 5.5.1.13
Source: | EchoStar
Title: | WP for support of NB-IoT in-band operation in NR NTN bands
Work item code: | TEI18_Test
Release: | Rel-18
Document for: | Endorsement
RAN5 WP template v3.0.0
1. Introduction
Recently, support for NB-IoT in-band operation in NR NTN bands as TEI18 in RAN4. The support for inband operation is optional for Rel-18 and mandatory from Rel-19 onwards for NB-IoT NTN UEs. This WP assesses the impact to various conformance speciification test clauses and tenative schedule for updating the affected clauses.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 29% (+29%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (FDD) |  | 28.7% (+28.7%)
FDD |  | 28.7% (+28.7%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 0% |  |  | 0%
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-4 | 100% (+100%) |  |  | 100% (+100%)
RF Rx test cases | 36.521-4 Rx
RF Tx test cases | 36.521-4 Tx
RF Demod test cases | 36.521-4 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2 | 0% |  |  | 0%
Test suites (TTCN) | 36.523-3 | 0% |  |  | 0%
5 References
[1] RP-250611 | RAN4 CRs to Maintenance for Closed WIs/SIs for REL-18 and earlier – Batch 23
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for support of NB-IoT in-band operation in NR NTN bands | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | TEI18_Test
WP Scope: |  | Make necessary updates to RF and Signalling Conformance Specs related to in-band/guard-band operations in NTN NR specified in the core specifications of IoT NTN (36.102)
WP Resp: |  | Ojas Choksi |  |  | ojas.choksi@echostar.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD
28.7% (+28.7%)
11 (+11)
4 (+4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 8.1.3.1.1.254 | FDD reference test frequencies for operating band 254 | Addition of RF test frequencies for in-band/guard-band operation in band 254 |  | RAN5#108 (Aug-25) |  |  | 0.1 | 0% | 0% |  | 0%
2 |  | 36.508 | 8.1.3.1.1.255 | FDD reference test frequencies for operating band 255 | Addition of RF test frequencies for in-band/guard-band operation in band 255 |  | RAN5#108 (Aug-25) |  |  | 0.1 |  |  |  | 0%
3 |  | 36.508 | 8.1.3.1.1.256 | FDD reference test frequencies for operating band 256 | Addition of RF test frequencies for in-band/guard-band operation in band 256 |  | RAN5#108 (Aug-25) |  |  | 0.1 |  |  |  | 0%
4 |  | 36.508 | 8.1.3.3.3 | NB-IoT Mapping of downlink physical channels and signals to physical resources | Update mapping table to indicate there Res are not reserved for PDCCH |  | RAN5#108 (Aug-25) |  |  | 0.2 |  |  |  | 0%
5 |  | 36.508 | 8.1.4.3.2 | NB-IoT Common contents of system information messages | Update MIB-NB, SIB1-NB, SIB2-NB |  | RAN5#108 (Aug-25) |  |  | 0.3 |  |  |  | 0%
6 |  | 36.508 | 8.3.1 | NB-IoT Requirements of test equipment | Need to add scenario of In-band operation with NR and guard-band operation with NR |  | RAN5#108 (Aug-25) |  |  | 0.1 |  |  |  | 0%
7 |  | 36.508 | 8.3.2.3.1 | Test frequencies for signalling test | Addition of new set of test freq for in-band/guard-band |  | RAN5#108 (Aug-25) |  |  | 0.1 |  |  |  | 0%
LTE RAN and CN protocols
TS 36.521-4: RF NTN test cases - Common parts (general clauses, Annexes)
1 |  | 36.521-4 | 5.4B | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | Update clause with addition of new subclause related to in-band operation and updates the Tx-Rx separation sub-clause |  | RAN5#107 (May-25) | R5-252601 |  | 1 |  |  |  | 100%
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
Idle Mode
Layer 2
RRC
NAS
TS 36.523-2: Applicability for Protocol test cases
1 |  | 36.523-2 | 4 | Recommended Test Case Applicability | Incorporates in-band NR PICS and PIXITs to relevant NTN test cases and a new note to test for stand-alone, in-band, guard-band |  | RAN5#108 (Aug-25) |  |  | 0.5 |  |  |  | 0%
2 |  | 36.523-2 | A.4.4 | Additional information | New PICS to be added for in-band operation in NR |  | RAN5#108 (Aug-25) |  |  | 0.5 |  |  |  | 0%
TS 36.523-3: Protocol test suites (TTCN)
1 |  | 36.523-3 | 9.3 | NB-IoT PIXIT | New PIXIT to be added if necessary |  | RAN5#108 (Aug-25) |  |  | 1 |  |  |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.