## Slide 1: SA WG6 status report to TSG SA#110
Atle Monrad
SA6 Chair (InterDigital Communications)

## Slide 2: SA6 Leadership
Chair:
  Mr. Atle Monrad 1 InterDigital Corporation / ATIS
Vice-chairs:
  Mr. Jukka Vialen 2 Airbus DS SLC / ETSI
  Mr. Basavaraj (Basu) Pattan 3 Samsung Electronics Ind. Co., Ltd. / TTA
Secretary:
  Bernt Mattsson (MCC)
1 Elected in February 2024 – Election of SA6 chair at SA6#71 in February 2026
2 Re-elected for fourth term in April 2025
3 Re-elected for second term in August 2024

## Slide 3: Executive Summary 1/2
Two meetings held in Q4 2025
  SA6#69, 13 – 17 October 2025
  SA6#70, 17 – 21 November 2025
Older releases (upto Rel-18)
  14 CRs Agreed
Rel-19 activities
  40 CRs Agreed
Rel-20 5GA activities
  Work on Approved SIDs & WIDs in progress
  45 CRs Agreed
  280 pCRs Approved
  1 revised SID Agreed
  3 new WIDs Agreed
Rel-20 6G-study activities
  New 6G-SID on Application Enablement Agreed

## Slide 4: Executive Summary 2/2
Release 19
  Further alignments and clarifications performed.
Release 20
  5GA: The first SIDs move towards completion and corresponding WIDs have started.
  6G-study: After two NWMs and discussions at SA6#69 and SA#70, the 6G-SID on Application Enablement is Agreed Discussions on timeline / plan for a 6G SID on Mission Critical features has not been formally initiated.
Other topics
  Removal of all Editor’s Notes in the Rel-18 and Rel-19 specifications are progressing well
Meeting Schedule for next quarter
  One meeting will be held:
    February – SA6#71

## Slide 5: SA6#69 Statistics
Meeting dates: 13 – 17 October 2025
  5 quarters on Monday – Thursday, 4 quarters on Friday
Statistics
  365 Tdoc numbers initially reserved, 685 Tdoc numbers used by end-of-meeting
  48 Agreed CRs – 8 for Rel-18, 23 for Rel-19, 17 for Rel-20
  144 Approved pCRs for Rel-20 – 5GA
  10 incoming LSs discussed, 4 outgoing LSs Approved
  Time allocation: Pre-Rel-19: 5%; Rel-19: 10%; Rel-20 5GA: 65%; Rel-20 6G-study: 20%
Conference calls (pre-SA6#69)
  2 informal conference calls

## Slide 6: SA6#70 Statistics
Meeting dates: 17 – 21 November 2025
  5 quarters on Monday – Thursday, 4 quarters on Friday
Statistics
  321 Tdoc numbers initially reserved, 594 Tdoc numbers used by end-of-meeting
  51 Agreed CRs – 6 for Rel-18, 17 for Rel-19, 28 for Rel-20
  136 Approved pCRs for Rel-20 – 5GA
  7 incoming LSs discussed, 4 outgoing LSs Approved
  1 revised SID Agreed (revised due to downscoping)
  3 new WIDs Agreed (follow-up WIDs after completed SIDs)
  1 new 6G-SID on Application Enablement discussed and Agreed
  Time allocation: Pre-Rel-19: Rel-19: 10%; Rel-20 5GA: 70%; Rel-20 6G-study: 20%
Conference calls (pre-SA6#70)
  1 informal conference call

## Slide 7: Number of Tdocs in SA6

## Slide 8
Number of approved pCRs & agreed CRs per SA6-meeting

## Slide 9: Progress of approved Release 20 5GA Study Items
UID | Name | Acronym | Target Month/year | Old % | WID | New %
1070024 | Study on Discreet listening and monitoring of mission critical services, Phase 2 | FS_MCDISC_Ph2 | SA#111 (03/2026) | 20% | SP-250580 | 40%
1070025 | Study on Logging and recording of mission critical services, Phase 2 | FS_MCLOG_Ph2 | SA#111 (03/2026) | 20% | SP-250581 | 40%
1050034 | Study on Service Enabler Architecture Layer (SEAL) Phase 4 | FS_SEAL_Ph4 | SA#110 (12/2025) | 95% | SP-250374 | 100%
1070029 | Study on Stage 2 for AI/ML service Phase 2 | FS_AIML_App_Ph2 | SA#110 (12/2025) | 60% | SP-250384 | 85%
1070026 | Study on Application enabler for XR Services Phase 3 | FS_XRM_Ph3_APP | SA#110 (12/2025) | 70% | S6-250381 | 100%
1070028 | Study on Stage 2 for MMTel Phase 2 | FS_MMTel_Ph2_APP | SA#111 (03/2026) | 40% | SP-250383 | 75%
1070027 | Study on SEAL data delivery Phase 3 | FS_SEALDD_Ph3 | SA#110 (12/2025) | 40% | SP-250382 | 95%
Legend: grey – on track, green – completed, yellow – behind

## Slide 10: Progress of approved Release 20 5GA Study Items
UID | Name | Acronym | Target Month/year | Old % | WID | New %
1080027 | Study on application enablement for satellite access enabled 5G services Phase 4 | FS_5GSAT_Ph4_APP | SA#111 (03/2026) | 10% | SP-250874 | 50%
1080023 | Study on application enablement for Ambient IoT services Phase 2 | FS_AmbientIoT_Ph2_APP | SA#111 (03/2026) | 10% | SP-250870 | 60%
1080025 | Study on Application user consent | FS_APCOT | SA#111 (03/2026) | 5% | SP-250872 | 60%
1080023 | Study of CAPIF Phase 4 | FS_CAPIF_Ph4 | SA#111 (03/2026) | 20% | SP-250873 | 70%
1080024 | Study on Application Enablement to support Energy Saving Phase 2 | FS_EnergySys_Ph2_APP | SA#111 (03/2026) | 15% | S6-250871 | 60%
1080028 | Study on use of Sensing results for Vertical Applications | FS_Sensing_APP | SA#111 (03/2026) | 15% | SP-250875 | 60%
Legend: grey – on track, green – completed, yellow – behind

## Slide 11: Progress of approved Release 20 5GA Work Items
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070032 | Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 | enhMC_Ph2-MC | SA#112 (06/2026) | 30% | SP-250391 | 45%
1070031 | Stage 2 for FRMCS Phase 6 | FRMCS_Ph6 | SA#112 (06/2026) | 45% | SP-250390 | 65%
1070030 | Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay | MultiHop-MC | SA#111 (03/2026) | 75& | SP-250389 | 100%
1070033 | Stage 2 for mobile metaverse services Phase 2 | Metaverse_Ph2-APP | SA#110 (12/2025) | 65% | SP-250392 | 100%
1080029 | Guidelines for 3GPP Application Enablement usage | AppEnable_EXT | SA#111 (03/2026) | 5% | SP-250883 | 60%
1090038 | Service Enabler Architecture Layer (SEAL) Phase 4 | SEAL_Ph4-APP | SA#112 (06/2026) | - | SP-251215 | 45%
Legend: grey – on track, green – completed, yellow – behind

## Slide 12
FS_MCLOG_Ph2
Progress since SA#109:
  10 new Key Issues
  2 new solutions
  1 major solution update
RAN and other impacts and dependencies:
  No RAN dependencies
  At a moment 4 of the KIs potentially requiring co-operation with SA3 during the solution phase
Contentious Issues:
  None
Next steps:
  Create solutions
  Solution evaluations
  The 03/2026 target will not be met, more realistic target is 60% ready by 03/2026 and WI may start, but even this (60%) is a challenge
  New target (for 100%) will be estimated after SA6#71
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070025 | Study on logging and recording of mission critical services, Phase 2 | FS_MCLOG_Ph2 | March-2026 | 20% | SP-250581 | 40%

## Slide 13: FS_MCDISC_Ph2
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070024 | Study on discreet listening and monitoring of mission critical services, Phase 2 | FS_MCDISC_Ph2 | March-2026 | 20% | SP-250580 | 40%
Progress since SA#109:
  3 scenarios added, 7 key issues added
RAN and other impacts and dependencies:
  No RAN dependencies
  For solutions FS_MCDISC_Ph2 relies on reuse of solutions developed for FS_MCLOG_Ph2
Contentious Issues:
  None
Next steps:
  Evaluate solutions developed for FS_MCLOG_Ph2 for reuse for discreet monitoring
  The completion is dependent on progress of FS_MCLOG_Ph2 and new target (for 100%) will be estimated after SA6#71.

## Slide 14: FS_SEAL_Ph4
UID | Name | Acronym | Target month/year | Old % | WID | New %
1050034 | Study on Service Enabler Architecture Layer (SEAL) Phase 4 | FS_SEAL_Ph4 | 12-2025 | 95% | SP-250374 | 100%
Progress since SA#109:
  Technical solution#6 is modified due to the conclusions of technical gap#1.
  Conclusions of technical gap#1,gap#4,gap8 are completed as part of TR conclusion.
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Study is completed.

## Slide 15: SEAL_Ph4-APP
UID | Name | Acronym | Target month/year | Old % | WID | New %
1090038 | Service Enabler Architecture Layer (SEAL) Phase 4 | SEAL_Ph4-APP | June-2026 | - | SP-251215 | 45%
Progress since SA#109:
  3GPP TR 23.949 is created and approved with skeleton.
  11 PCRs to 3GPP TR 23.949 approved by SA6#69 and SA6#70.
  3 CRs to 23.434 approved by SA6#69 and SA6#70.
RAN and other impacts and dependencies:
  None
Contentious Issues:
  How to capture the relationship between different components with 3GPP exposure overall architecture to improve the Comprehensibility of SA6 defining CAPIF and SEAL services.
Next steps:
  Completing the remaining objectives of the WID.

## Slide 16: FS_AIML_App_Ph2
Progress since SA#109:
  Finalized architecture enhancements, deployment and business models
  Finalized all key Issues and most solutions
  Progress on overall evaluation and conclusions
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Finalization of evaluations of 4 remaining solutions, finalization of overall evaluation and conclusions, resolution of remaining ENs.
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070029 | Study on Stage 2 for AI/ML service Phase 2 | FS_AIML_App_Ph2 | Dec-2025 | 60% | SP-250384 | 85%

## Slide 17: FS_XRM_Ph3_APP
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070026 | Study on Application enabler for XR Services Phase 3 | FS_XRM_Ph3_APP | Dec-2025 | 70% | SP-250381 | 100%
Progress since SA#109:
  SA6#69: 11 pCRs agreed, SA6#70: 8 pCRs agreed
  Progress made for:
    2 new Solution for Key Issue#1
    1 new Solution for Key Issue#4
    1 new Solution for Key Issue#5
    Solution update for Solution #1, #3, #5 and #6
    Solution evaluations for solution #1, #6, #7 and #8
    Overall evaluation and conclusion for Key Issue #1, #3, #4 and #5
    23.700-51 TR clean up
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Study is completed

## Slide 18: FS_MMTel_Ph2_APP
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070028 | Study on Stage 2 for MMTel Phase 2 | FS_MMTel_Ph2_APP | March-2026 | 40% | SP-250383 | 75%
Progress since SA#109:
  SA6#69: 8 pCRs agreed
  SA6#70: 7 pCRs agreed
  Progress made for:
    5 new solution: Alignment 8.4.2 and 8.4.3 service flows with SA2, Alignment 8.4.4 and 8.4.5, enable the A2P avatar communication, enablement of standalone DC, enablement of standalone DC
    2 updated solutions: solution #1, solution #2
    evolutions and conclusion: KI# 1, KI#2, KI#3, KI#4, KI#6
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Update solutions which have SA2 dependency
  Update other agreed solutions
  architecture enhancements
  finalized evolutions and conclusions

## Slide 19: FS_SEALDD_Ph3
Progress since SA#109:
  SA6#69 and SA6#70: 15 submitted, 12 agreed.
  Down scope the SID objective, i.e., the last objective is removed.
  Progress made for:
    Solution #1 is further updated
    4 new solution to key issue#1 were agreed
    Evaluation of each solution is added.
    Overall evaluation and overall conclusion
RAN and other impacts and dependencies:
  None
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070027 | Study on SEAL data delivery Phase 3 | FS_SEALDD_Ph3 | Dec-2025 | 40% | SP-250382 | 95%
Contentious Issues:
  N/A
Next steps:
  Start the WI phase work

## Slide 20: FS_5GSAT_Ph4_APP
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070027 | Study on application enablement for satellite access enabled 5G services Phase 4 | FS_5GSAT_Ph4_APP | March-2026 | 10% | SP-250382 | 50%
Progress since SA#109:
  Solution evaluation for Sol#1 & Sol#2
  KI3 & K4 solution updated
  New Solution on support of satellite related information utilizing AI analysis
  New Solution for support of QoS analysis for services over satellite access
  Solution for location service via satellite access
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Finalized the remaining KI
  Consolidate solutions

## Slide 21: FS_AmbientIoT_Ph2_APP
UID | Name | Acronym | Target month/year | Old % | WID | New %
1080023 | Study on application enablement for Ambient IoT services Phase 2 | FS_AmbientIoT_Ph2_APP | March-2026 | 10% | SP-250870 | 60%
Progress since SA#109:
  TR 23.700-26 v.0.3.0 was created based on approved contributions.
  33 pCRs agreed mainly including 14 new solutions and solution updates addressing the KI#1, KI#2, KI#3 and KI#4.
  Overall evaluation for KI#1 were agreed.
  Architectural assumptions and requirements were agreed.
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Update solutions to resolve the remaining ENs.
  Propose the overall evaluation for KI#2, KI#3 and KI#4.
  Propose the general conclusion and split conclusion for KI#1, KI#2, KI#3 and KI#4.
  Finalize the TR 23.700-26.
  Prepare TR for approval to SA plenary.

## Slide 22: FS_APCOT
UID | Name | Acronym | Target month/year | Old % | WID | New %
1080025 | Study on Application user consent | FS_APCOT | March-2026 | 5% | SP-250872 | 60%
Progress since SA#109:
  Addition of KIs and solutions for the Application user consent architecture and for the E2E application user consent
  Addition of 4 recommended requirements
  Sent an LS to SA3 (cc SA2) to inform of the FS_APCOT progress and inform SA3 they can use current TR draft to determine the security, regulatory analysis work for SA3
RAN and other impacts and dependencies:
  None for RAN
  During SI phase 2:
    Coordination with SA3 for security & regulatory aspects
    Coordination with SA2 for architecture aspects
Contentious Issues:
  None
Next steps:
  Solution evaluations, conclusions, recommendations, finalize recommended requirements
  Coordinate with SA3 and SA2

## Slide 23: FS_CAPIF_Ph4
UID | Name | Acronym | Target month/year | Old % | WID | New %
1080023 | Study of CAPIF Phase 4 | FS_CAPIF_Ph4 | March-2026 | 20% | SP-250873 | 70%
Progress since SA#108:
  Total 7 Key issues agreed
  Total 14 solutions agreed
  Total 24 pCRs agreed
    In SA6#69: 10 pCRs
    In SA6#70: 14 pCRs
  TR 23.700-43 is sent for information to plenary
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Update solutions
  Solution Evaluation, and Key issue evaluation and conclusion

## Slide 24: FS_EnergySys_Ph2_APP
UID | Name | Acronym | Target month/year | Old % | WID | New %
1080024 | Study on Application Enablement to support Energy Saving Phase 2 | FS_EnergySys_Ph2_APP | March-2026 | 15% | SP-250871 | 60%
Progress since SA#109:
  Added definitions of terms, architectural requirements and assumptions
  21 solutions for the 6 key issues were added to TR 23.700-44
  Solution updates for KI#1, KI#3, KI#4, and KI#6
  Started solution evaluations
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Update solutions to resolve the remaining ENs
  Finalize evaluations and conclusions

## Slide 25: FS_Sensing_APP
UID | Name | Acronym | Target month/year | Old % | WID | New %
1080028 | Study on use of Sensing results for Vertical Applications | FS_Sensing_APP | March-2026 | 15% | SP-250875 | 60%
Progress since SA#109:
  SA6#69: 13 pCRs agreed
  SA6#70: 13 pCRs agreed
  Progress made for:
    5 new solutions and 3 updated solutions for KI#1 general aspect
    7 new solution and 1 updated solution for KI#2 UAV use case
    4 new solution and 1 updated solution for KI#3 Spatial map use case
    1 new solutionn for KI#4 V2X use case
    evolutions for solution #9 and #10 (KI#3)
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Update agreed solutions
  Finailize architecture ,requirements and potential architecture enhancement
  Finalized evolutions and conclusions

## Slide 26: enhMC_Ph2-MC
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070032 | Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 | enhMC_Ph2-MC | June-2026 | 30% | SP-250391 | 45%
Progress since SA#109:
  SA#70: 6 CR’s Agreed
  Progress made for:
    Editor notes resolution in Rel-19 Specifications (90% complete)
    CRs discussed related to Remote UE enable/disable.
  Discussion Topics:
    Location Management Stage2 and Stage3 alignment.
    Hidden user support.
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Complete remaining normative work identified in WID:
    Ambient listening pause and resume
    Support for remote UE enable/disable.
  Resolving remaining editor notes (9 out of 48) in Rel-19 specification (TS 23.282)

## Slide 27: FRMCS_Ph6
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070031 | Stage 2 for FRMCS Phase 6 | FRMCS_Ph6 | June-2026 | 45% | SP-250390 | 65%
Progress since SA#109:
  Combining of adhoc group calls and adhoc emergency alerts (3 CRs)
  Call forwarding of adhoc group calls (3 CRs)
  Resolving EN on MC gateway UE (1 CR)
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  MC gateway UE (migration, interconnection, multiple UEs per service)
  Resolving open issues (ENs)

## Slide 28: MultiHop-MC
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070030 | Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay | MultiHop-MC | March-2026 | 75% | SP-250389 | 100%
Progress since SA#109:
  Final open issue was resolved
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  None, work item is completed

## Slide 29
Metaverse_ph2-APP
UID | Name | Acronym | Target month/year | Old % | WID | New %
1070033 | Stage 2 for mobile metaverse services Phase 2 | Metaverse_Ph2-APP | Dec-2025 | 65% | SP-250392 | 100%
Progress since SA#109:
  Completion of Spatial Anchor Group Mgmt procedures
  Updates to the SM data source subscription procedures
  Addition of APIs for the completed procedures
  SM data source triggering procedure
  Resolution of Editor’s Notes
  Correction CRs in the area of digital assets information flows
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Resolution of pending Editor’s Notes
  Cleanup CRs.

## Slide 30: AppEnable_EXT
UID | Name | Acronym | Target month/year | Old % | WID | New %
1080029 | Guidelines for 3GPP Application Enablement usage | AppEnable_EXT | March-2026 | 5% | SP-250883 | 60%
Progress since SA#109:
  TR 23.947 achieved 60% completion
    To be presented for information (V0.3.0)
  Text agreed on:
    1 Scope, 2 References & 3 Definitions
    4 Overview of Frameworks (CAPIF; EDGEAPP; & SEAL)
    5 Use Cases (1 use case approved to date)
    6 Developer Guidelines: Cross-Framework Integration & Example Application Flows
    Annex A: CAPIF plus EDGEAPP Topology & CAPIF+SEAL Topology
RAN and other impacts and dependencies:
  None
Contentious Issues:
  None
Next steps:
  Consider restructuring to avoid potential overlap between clauses and address ENs
  Focus on completion of the agreed clauses:
    5 Use Cases
    6 Developer Guidelines
    7 Security Considerations
    Annex A: Infrastructure Topology Diagrams Examples

## Slide 31
Future SA6 meetings
Meeting | Date | Location
2026 |  | 
SA6#71 | 9 – 13 Feb 2026 | Goa India
SA6#72 | 13 – 17 April 2026 | St. Paul’s Bay, Malta
SA6#73 | 18 – 22 May 2026 | TBC, P. R. China
SA6#74 | 24 – 28 August 2026 | Prague, Czech Republic
SA6#75 | 12 – 16 October 2026 | Prague, Czech Republic
SA6#76 | 16 – 20 November 2026 | Calgary, Canada
2027 |  | 
SA6#77 | 22 – 26 Feb 2027 | South Korea, Location TBC
SA6#78 | 19 – 23 April 2027 | Location TBD
SA6#79 | 24 – 28 May 2027 | China, Location TBC
SA6#80 | 30 Aug. – 3 Sept. 2027 | Location TBD
SA6#81 | 11 – 15 October 2027 | Location TBD
SA6#82 | 15 – 19 November 2027 | Location TBD

## Slide 32: For TSG SA information and approval

## Slide 33: Rel-20 6G-study planning for information
The following timeline / plan for agreement of the 6G SID on application enablement has been executed
 | SA6#68 (Aug 25 - 29) | Moderated Discussion #1 (Sep 1 - 14) | SA6#69 (Oct 13 - 17) | Moderated Discussion #2 (Oct 20 - 26) | SA6#70 (Nov 17 - 21)
Input | 1. Company proposed work tasks and initial analysis SA1 TR 22.870. 2. Discussion on Working methods (NWM, email, conf calls) for Moderated discussions. 3. Discuss the questions for Moderated Discussions | Candidate Work Tasks from SA6#68 Dates: Sep 1 to 14 (2 weeks) See S6-253382 https://nwm-trial.etsi.org/#/documents/9246 | 1. Moderator collated Work Tasks 2. Company proposed Work Tasks to SA6#69 | Candidate Work Tasks from SA6#69 Dates: Oct 20 to 26 (1 week) See S6-254714 https://nwm-trial.etsi.org/#/documents/9278 | 1. Moderator collates Work Tasks 2. Company proposed Work Tasks to SA6#70
Output | 1. Populate candidate Work Tasks 2. Finalize tool and plan for Moderated Discussions. 3. Agree to questions for Moderated Discussions | Moderator collates Work Tasks and prepares discussion summary | Intermediate SID based on the agreed Work Tasks (Round 1) | Moderator collates Work Tasks and prepares discussion summary | Finalize Work Tasks (Round 2). Complete the SID, Agree in SA6 and submit to SA plenary for Approval.

## Slide 34: Further work on IOPS for information and guidance
SA1 initially provided TS 22.346 “Isolated Evolved Universal Terrestrial Radio Access Network (E-UTRAN) operation for public safety” (Rel-13). 5G support was introduced in TS 22.261 (Rel-15).
The corresponding stage 2 were provided in:
  TS 23.401 “General Packet Radio Service (GPRS) enhancements for Evolved Universal Terrestrial Radio Access Network (E-UTRAN) access” (Rel-13) by SA2
  TS 33.401 “3GPP System Architecture Evolution (SAE); Security architecture” (Rel-13) by SA3
  TS 33.180 “Security of the Mission Critical (MC) service” (Rel-14) by SA3
  TS 23.180 “Mission critical services support in the Isolated Operation for Public Safety (IOPS) mode of operation” (Rel-17) by SA6
At SA#104, SA6 provided a SID on “MC services support on IOPS mode of operation for 5G” for Rel-19. SA decided to modify this study to “MC services support on generic IOPS mode of operation” (SP-241017). Based on this study, a corresponding WID was approved in (SP-241382) and implemented in TS 23.180.
SA6 has debated if our generic solution on IOPS, as requested by SA and implemented in TS 23.180, is sufficiently reflected across other specifications in SA.
SA6 has asked SA1 (SP-251300) if the service requirements from Rel-13 should be reconsidered and possibly adjusted.

## Slide 35: CR packs for approval (1/3)
For Approval: CR packs
  SP-251469 Rel-19 CRs to TS 23.554 for 5GMARCH_Ph3
  SP-251470 Rel-19 CRs to TS 23.482 for AIML_App
  SP-251471 Rel-19 CRs to TS 23.222 for CAPIF, TEI19
  SP-251472 Rel-18 CRs to TS 23.222 for eCAPIF
  SP-251473 Rel-19 CRs to TS 23.222 for CAPIF_Ph3
  SP-251474 Rel-19 CRs to TS 23.558 for EDGEAPP_Ph3
  SP-251475 Rel-19 CRs to TS 23.434 for eLSAPP
  SP-251476 Rel-18 CRs to 23.282 and 23.379 for enh4MCPTT
  SP-251477 Rel-19 CRs to 23.280, 23.281, 23.282 and 23.379 for enhMC
  SP-251478 Rel-20 CRs to TS 23.280, TS 23.282 and TS 23.379 for enhMC_Ph2-MC

## Slide 36: CR packs for approval (2/3)
For Approval: CR packs
  SP-251479 Rel-19 CRs to TS 23.280, TS 23.282 and TS 23.379 for FRMCS_Ph5
  SP-251480 Rel-20 CRs to TS 23.280 and TS 23.379 for FRMCS_Ph6-MC
  SP-251481 Rel-20 CRs to TR 23.700-35 for FS_SEAL_Ph4
  SP-251482 Rel-19 CRs to TS 23.180 for Generic_IOPS
  SP-251483 Rel-18 CRs to TS 23.379 for MC_AHGC
  SP-251484 Rel-18 CRs to TS 23.180 for MCIOPS, TEI18
  SP-251485 Rel-19 CRs to TS 23.437 and TS 23.438 for Metaverse_App
  SP-251486 Rel-20 CRs to TS 23.437 and TS 23.438 for Metaverse_Ph2-APP
  SP-251487 Rel-19 CRs to TS 23.392 for MMTel_App
  SP-251488 Rel-20 CRs to TS 23.280 and TS 23.289 for MultiHop-MC

## Slide 37: CR packs for approval (3/3)
For Approval: CR packs
  SP-251489 Rel-18 CRs to TS 23.434 for SEAL_Ph3
  SP-251490 Rel-20 CRs to TS 23.434 for SEAL_Ph4-APP
  SP-251491 Rel-19 CRs to TS 23.433 for SEALDD_Ph2
  SP-251492 Rel-20 CRs to TS 23.433 for TEI20, SEALDD_Ph2
  SP-251493 Rel-19 CRs to TS 23.283 for TEI19
  SP-251494 Rel-20 CRs to TS 23.434 for TEI20
  SP-251495 Rel-20 CRs to TS 23.482 for TEI20
  SP-251496 Rel-18 CRs to TS 23.286 for V2XAPP_Ph3
  SP-251497 Rel-19 CRs to TS 23.433 for XRM_Ph2_App

## Slide 38: Specifications for information and approval
For Information: Technical Reports/Specifications
  SP-251459 Presentation of TR 23.700-15 v1.0.0 “Study on Use of sensing results for Vertical Applications” for Information
  SP-251460 Presentation of TR23.700-26 V1.0.0 “Study on application enablement for Ambient IoT services” for information
  SP-251461 Presentation of TR 23.700-42 V1.0.0 “Study on application user consent” for Information
  SP-251462 Presentation of TR23.700-43 V1.0.0 “Study on CAPIF Phase 4” for Information
  SP-251463 Presentation of TR23.700-44 V1.0.0 “Study on application enablement to support energy saving” for Information
  SP-251464 Presentation of TR 23.700-57 V1.0.0 “Study on Stage 2 for MMTel Phase 2” for Information
  SP-251465 Presentation of TR 23.947 for V1.0.0 “Guidelines for 3GPP Application Enablement usage” for Information
For Information and Approval: Technical Reports/Specifications
  SP-251467 Presentation of TR 23.700-52 v1.0.0 “Study on Service Enabler Architecture Layer (SEAL) Phase 4” for Information and Approval
For Approval: Technical Reports/Specifications
  SP-251466 Presentation of TR 23.700-51 v1.0.0 “Study on Application enabler for XR Services Phase 3” for Approval
  SP-251468 Presentation of TR 23.700-83 v1.0.0 “Study on application layer support for AI/ML services Phase 2” for Approval

## Slide 39: New and revised work & study items
For Approval: New SIDs/WIDs for Approval
  SP-251455 New SID study on 6G Application Enablement
  SP-251456 New WID Application enabler for XR Services Phase 3
  SP-251457 New WID SEAL data delivery Phase 3
  SP-251458 New WID on application enablement for AI/ML service Phase 2
For Approval: Revised SIDs/WIDs for Approval
  SP-251454 Revised SID on SEAL data delivery phase 3
For Potential Approval: Endorsed SIDs/WIDs
  None

## Slide 40: Acknowledgements
The Chair would like to thank:
  The hosts, CCSA / CF3 and ATIS, for well organized meetings with all needed facilities.
  The MCC, Bernt Mattsson, for all necessary help, prior to, during and after the meetings.
  The Vice Chairs, Jukka Vialen and Basu Pattan for constructive input on meeting planning and good help with off-line coordination and chairing of sessions during the meetings.
  Most of all, each and every delegate in SA6, which with a positive attitude, a cooperative spirit and an open mind always show willingness to compromise to progress our work, both for regular contributions as well as for the 6G-SID on Application Enablement !!!

## Slide 42: Thank You