## Slide 1
SP-200800
On Release 17 Schedule
Source: Qualcomm Incorporated, Samsung, Nokia, Nokia Shanghai Bell
3GPP SA #89e
September 15-21, 2020

## Slide 2: General context
The current pandemic presents some unique challenges to 3GPP
3GPP Release 17 schedule planning was agreed in December 2019, obviously with the assumption of conducting working group meetings face-to-face
3GPP has adapted extremely well to the new circumstances with all working group meetings operating electronically and managing to make progress
It is however an objective fact that the overall “throughput” of electronic working groups is lower than physical meetings
We are not in a position to predict for how long the current situation will persist
The SA2 and SA6 Chairman reports indicate that Dec 2020 stage 2 freeze is not feasible
It is reasonable to assume that meetings will continue electronically for at least H1 of 2021 and re-plan 3GPP schedule accordingly
Available time in Q1 general is compressed due to major holidays in all regions and time for official meeting and/or offline collaboration will be limited (ref. Christmas/New Year, lunar new year)

## Slide 3: SA2 specific context
The majority of conclusions that have been agreed so far as interim conclusions were a set of principles. We expect that this approach will continue for “final” conclusions for most key issues and as such it is expected that normative work will take more time than previously
Quite a few study items have dependencies to RAN and SA3 and it is expected that will continue well into Q1-Q2 2021 taking into account their respective schedules

## Slide 4: Proposal - principles
We believe it is beneficial to agree to a revised Rel-17 schedule now, as opposed to waiting until future Plenaries, to provide more stability to the organization and to the industry in general
We propose to add 6 more months to the completion of the Release
We also propose that we consider the resulting deadline a “firm” deadline. Thus, in case not enough progress is achieved on some projects, we will have to accept some downscoping
More details in the next slide

## Slide 5
Sep 2020 (TSG#89e)
Dec 2020 (TSG#90): SA2 study items completion
Dec 2020 (TSG#90): SA2 work items completion
Sept 2021 (TSG#93): Freeze of Stage 3
Dec 2021 (TSG#94): ASN-1 Freeze
TODAY
Current Release 17 (as in SP-20606)

## Slide 6: Proposed Release 17 Freezes
Sep 2020 (TSG#89e)
Dec 2020 (TSG#90): SA2 study items completion
Dec 2020 (TSG#90): SA2 work items completion
Sept 2021 (TSG#93): Freeze of Stage 3
Dec 2021 (TSG#94): ASN-1 Freeze
TODAY
KEEP SAME
Current Release 17
Sep 2020 (TSG#89e)
Dec 2020 (TSG#90): SA2 study items completion
June 2021 (TSG#92): SA2 work items completion
March 2022 (TSG#95): Freeze of Stage 3
June 2022 (TSG#96): ASN-1 Freeze

## Slide 7: Conclusion
We propose to
  Agree to a revised Release 17 schedule during this round of 3GPP TSG meetings to ensure industry stability
  Extend Rel-17 of 6 months (Stage-2 freeze: June 2021, Stage-3 freeze: March 2022)
  Consider the new schedule firm. If absolutely necessary, in future SA Plenary, adjust the content of the Release to fit the new schedule