## Slide 1: FS_MASSS Status Report
Krisztian Kiss (Primary Rapporteur)
Apple
Zhuoyi Chen (Secondary Rapporteur)
China Telecom

## Slide 2: FS_MASSS Status after SA2#161
  Progress since SA2#160AH-e
  TR 23.700-54 v0.2.0 is available.
  72 TDocs were submitted and 25 tdocs could not be handled. The handled documents included:
    Terms and Architectural Assumptions/Requirements (12 tdocs)
    Key Issue for WT#1.3 (13 tdocs), updates to KIs (2 tdocs)
    ATSSS_Ph4 solutions: KI#2.1 (7 tdocs) & KI#2.2 (13 tdocs), DualSteer solution to KI#1.1 (1 tdoc)
  Updated Architectural Assumptions/Requirements for ATSSS_Ph4, 2 key issues for WT1.3, Updated KI#2.2, 4 new solutions to KI#2.1 and 4 new solutions to KI#2.2 were approved
  Terms and Architectural Assumptions and Requirements for DualSteer were noted
  RAN impacts and dependencies
  Key Issue #1.x and #2.2 have SA3 dependencies to handle security aspects
  No RAN dependency
Contentious issues – issues identified during SA2#160AH-e remain unresolved:
  DualSteer Device definition by SA1 has been challenged by some companies. Disagreement whether it requires any Stage-2 alignments
  Whether both traffic steering and switching requires anchoring in 5GC or only traffic switching
  Whether two registered accesses are required to initiate traffic steering or switching in DualSteer, or whether traffic steering or switching could trigger second RAT/PLMN registration
Next steps
  In the next meeting: Agree new solutions for DualSteer Key Issues, Architectural assumptions/requirements and terms and definitions for DualSteer, Evaluation and conclusion of ATSSS_Ph4, Solution updates & new solutions for ATSSS_Ph4 Key Issues.
WI Code | Work Item Title | WP | Target Date | WID#
FS_MASSS | Study on Multi-Access (DualSteer and ATSSS_Ph4) | 9% -> 30% | June 2024 | 1020070

## Slide 3: FS_MASSS status at SA#103
Progress since SA#102:
  TR 23.700-54 v.0.2.0 was created based on approved contributions.
  20 contributions agreed including TR skeleton, Scope, Architectural Assumptions and Requirements for ATSSS_Ph4, 6 key issues and 8 solutions addressing KI#2.1 & KI#2.2 (ATSSS_Ph4).
  Terms and Architectural Assumptions and Requirements for DualSteer were not approved after 2 meetings due to disagreement whether SA1 definitions require any Stage-2 alignments or not.
  3.5 TUs are used and 4 TUs are left for the Study Phase.
Impacts and dependencies on other WGs:
  Key Issue #1.x and #2.2 have SA3 dependencies to handle security aspects.
Contentious issues:
  DualSteer KIs may be at risk not to be completed by May 2024 if common understanding on DualSteer Device definition cannot be reached.
Next steps:
  New solutions for DualSteer Key Issues.
  Agree Architectural assumptions/requirements and terms and definitions for DualSteer.
  Solution evaluation and conclusions, prepare sending TR for approval. Plan LS to SA3 based on agreed solutions.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 06/03/2024 | 0% | SP-231802 | 30% | SID to be updated by S2-2401315

## Slide 4
Total 13.5 TUs
  7.5 TUs for Study Phase and 6 TUs for Normative Work
FS_MASSS Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan. 2024 | 1.5 | 1.5 | TR skeleton, TR scope, Terms, Architectural assumptions Key Issues for all WTs.
SA2#161 | Feb 2024 | 2 | 2 | Terms, Architectural assumptions/requirements for DualSteer, Postponed Key Issues for WT#1.3, Key Issue updates (if necessary), New solutions for approved Key Issues.
SA2#162 | Apr 2024 | 2 |  | In priority order: New solutions for DualSteer, Architectural assumptions/requirements & Terms and definitions for DualSteer, Evaluation and conclusion for ATSSS_Ph4 (conclusion on SA3 dependencies need to wait for SA3 feedback), Solution updates for ATSSS_Ph4, New solutions for ATSSS_Ph4. No new KI is allowed.
SA2#163 | May 2024 | 2 |  | In priority order: New and updated solutions for DualSteer, Evaluation and conclusion for DualSteer, Evaluation and conclusion for ATSSS_Ph4 (if needed), Solution updates for ATSSS_Ph4 (if needed). No new solution is allowed for ATSSS_Ph4. Send TR for Information & Approval. WID approval.
 | Total | 7.5 |  | 

## Slide 5: FS_MASSS Status after SA2#160AH-e
  Progress since SA#102
  Study started in SA2#160AH-e, TR 23.700-54 v0.1.0 is available.
  71 TDocs were submitted and 24 tdocs could not be handled due to TU budget. The handled documents included:
    TR skeleton, Scope (2 tdocs)
    Terms, and Architectural Assumptions/Requirements (5 tdocs)
    40 Key Issue Proposals
  TR skeleton, Scope, Architectural Assumptions/Requirements for ATSSS_Ph4, and 4 key issues were approved (1 KI for WT#1.1, 1 KI for WT#1.2, 1 KI for WT#2 and 1 KI for WT#3)
  Terms, Architectural Assumptions and Requirements for DualSteer and 2 key issues were postponed (2 KIs for WT#1.3)
  RAN impacts and dependencies
  Key Issue #1.x and #2.2 have SA3 dependencies to handle security aspects
  No RAN dependency
Contentious issues
  DualSteer Device definition by SA1 has been challenged by some companies. Disagreement whether it requires any Stage-2 alignments
  Whether both traffic steering and switching requires anchoring in 5GC or only traffic switching
  Whether two registered accesses are required to initiate traffic steering or switching in DualSteer, or whether traffic steering or switching could trigger second RAT/PLMN registration
Next steps
  In the next meeting: Agree terms, Architectural assumptions/requirements for DualSteer, Postponed Key Issues for WT#1.3, New solutions for approved Key Issues.
WI Code | Work Item Title | WP | Target Date | WID#
FS_MASSS | Study on Multi-Access (DualSteer and ATSSS_Ph4) | 0% -> 9% | June 2024 | 1020070