## Slide 1: Rel-19 AmbientIoT-ARC Status Report
Runze Zhou (Huawei), Fei Lu (OPPO)
(Rapporteurs)

## Slide 2: AmbientIoT-ARC Status at SA#110
  Progress since SA2#171
  15 CR were approved, including:
    Alignment work with SA3 and RAN progress (all remaining editor’s notes are resolved), clarification on AIoT Device context for AIOTF, Clarification on Ambient IoT Device
    Handling of unsupported command in the network, extension of identification information length, clarification on AIoT Device profile data and AIoT security data, further update of security related descriptions.
  4 LS out were approved.
  TS 23.369 is 100% complete.
  Impacts and dependencies on other WGs
  None
Outstanding issues
  None
Next steps
  Maintenance work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070010 | Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-ARC | Jun, 2025 | 95% | SP-250377 | 100% | 
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 100% | SP-240969 | 100% | 

## Slide 3: AmbientIoT-ARC Status after SA2#172
  Progress since SA2#171
  4 new CR and 3 CR update from SA2#171 were approved, including:
    Handling of unsupported command in the network, extension of identification information length, clarification on AIoT Device profile data and AIoT security data, etc,.
  3 LS out were approved, to CT1, CT3, CT4 and SA3
  TS 23.369 is 100% complete.
  Impacts and dependencies on other WGs
  None
Outstanding issues
  None
Next steps
  Maintenance work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070010 | Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-ARC | Jun, 2025 | 98% | SP-250377 | 100% | 
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 100% | SP-240969 | 100% | 

## Slide 4: AmbientIoT-ARC Status after SA2#171
  Progress since SA#109
  11 CR were approved, including:
    Alignment work with SA3 and RAN progress (all remaining editor’s notes are resolved), clarification on AIoT Device context for AIOTF, Clarification on Ambient IoT Device
  1 LS out were approved: Reply LS on Structure updates of AIoT Identifiers
  TS 23.369 is 98% complete.
  Impacts and dependencies on other WGs
  None
Outstanding issues
  None
Next steps
  Maintenance work, including incoming LS related issues
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070010 | Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-ARC | Jun, 2025 | 95% | SP-250377 | 98% | 
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 100% | SP-240969 | 100% | 

## Slide 5
AmbientIoT-ARC work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#166-Ad Hoc-e | Jan 2025 | 1 | 1 | Start the normative work. Meeting agreed TS skeleton, Scope, Definition, Architecture model and concepts, and Functional description.
SA2#167 | Feb 2025 | 1.5 | 1.5 | Continue with the normative work. Meeting agreed additional Functional description, inventory and command procedures, and NF services.
SA2#168 | Apr 2025 | 2 | 2 | Continue with the normative work, addressing several FFS for AIoT features, AIoT procedures and NF descriptions.
SA2#169 | May 2025 | 2 | 2 | Continue and finalize the normative work.
SA2#170 | Aug 2025 | 1 | 1 | Resolve outstanding issues based on SA3 and RAN WGs progress
SA2#171 | Oct 2025 | 1 | 1 | Resolve outstanding issues based on SA3 and RAN progress
SA2#172 | Nov 2025 | 1 |  | Maintenance work
Total TU | Total | 8.5+ future meeting planned TU | 8.5 | 

## Slide 6: BACKUP

## Slide 7: FS_AmbientIoT Status after SA2#160AH-e
  Progress since SA2#160AH-e
  Study started with SA2#160AH-e.
  TR 23.700-13 v0.1.0 is available.
  40 TDocs were submitted and 22 Tdocs could not be handled due to TU budget/quota.
    The contents of the not handled Tdocs for new key issues were also considered in the discussion of the e-meeting.
  8 pCRs for TR skeleton, Scope, Terms, Architecture Assumptions/Requirements, 3 Key Issues to cover the WTs in the SID have been agreed.
  Key issue discussion has been finalized with two ENs(reference of the RAN TR to be updated, term name of “inventory” and “command” to be given). For future meetings, key issue update to address the ENs can be considered, but no new key issue proposal will be considered.
  RAN impacts and dependencies
  3 key issues have RAN dependency
  Whether traffic type “DO-A” will be in the R19 scope needs RAN decision
Contentious issues
  None
Next steps
  Start solution discussions for agreed Key Issues in next meeting
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 0% -> 13% | Dec 2024 | 1020071

## Slide 8: FS_AmbientIoT Status after SA2#161
  Progress since SA#102
  TR skeleton, Scope, Terms, Architecture Assumptions and Requirements are agreed
  3 key issues are agreed and no new key issue will be considered
  12 solutions are agreed and documented in the TR
  TR 23.700-13 v0.2.0 is available
  RAN impacts and dependencies
  3 key issues have RAN dependency
  Whether traffic type “DO-A” will be in the R19 scope needs RAN decision
Contentious issues
  None
Next steps
  Continue solution discussions in SA2#162 meeting
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 13% -> 25% | Dec 2024 | SP-231803 1020071

## Slide 9: FS_AmbientIoT Status at SA#103
  Progress since SA#102
  TR skeleton, Scope, Terms, Architecture Assumptions and Requirements are agreed
  3 key issues are agreed and no new key issue will be considered
  12 solutions are agreed and documented in the TR
  TR 23.700-13 v0.2.0 is available
  RAN impacts and dependencies
  3 key issues have RAN dependency
  Whether traffic type “DO-A” will be in the R19 scope needs RAN decision
Contentious issues
  None
Next steps
  Continue solution discussions
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 13% -> 25% | Dec 2024 | SP-231803 1020071

## Slide 10: FS_AmbientIoT Status after SA2#162
  Overall progress in SA2#162
  In total 16 papers are agreed, including:
    12 new solutions
    3 solution update
    1 new abbreviation “RFID”
  TR 23.700-13 v0.3.0 is available, including 24 solutions
  Impacts and dependencies on other WGs
  Several solutions have EN/note, need coordination with RAN, SA3 and SA5
Next steps
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 25% -> 45% | Dec 2024 | SP-231803 1020071

## Slide 11: FS_AmbientIoT Status at SA#104
  Progress since SA#102
  TR 23.700-13 v0.4.0 is available.
  22 new solutions agreed, for 3 key issues
  1 LS (S2-2407231) to SA1, SA3 and RAN1 (CC RAN2, RAN3)
  RAN impacts and dependencies
  1 LS (S2-2407231) to SA1, SA3 and RAN1 (CC RAN2, RAN3)
  Several solutions have EN/note, need coordination with RAN, SA3 and SA5
Contentious issues
  None
Next steps
  Continue and complete solution discussions (multi-sourced papers will be handled with priority, any new solution should be in principle different from the existing solutions in the TR and ready for evaluation).
  Start evaluation/conclusion: group/categorize the solutions, identify the non-controversial aspects and key controversial aspects, identify the dependency with other WHs and have earlier coordination.
  AIoT conference call and NWM discussion will be arranged between SA2#163 and SA2#164 for e.g. deployment scenarios including roaming, etc.
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 25% -> 65% | Dec 2024 | SP-231803 1020071

## Slide 12: FS_AmbientIoT Status after SA2#163
  Overall progress in SA2#163
  TR 23.700-13 v0.4.0 is available, including 34 solutions
  15 papers has been agreed (62 submitted), including:
    1 LS out to SA1, SA3 and RAN1 (CC RAN2, RAN3)
    4 solution updates
    10 new solutions
  Impacts and dependencies on other WGs
  1 LS (S2-2407231) to SA1, SA3 and RAN1 (CC RAN2, RAN3)
  Several solutions have EN/note, need coordination with RAN, SA3 and SA5
Next steps
  Continue and complete solution discussions (multi-sourced papers will be handled with priority, any new solution should be in principle different from the existing solutions in the TR and ready for evaluation).
  Start evaluation/conclusion: group/categorize the solutions, identify the non-controversial aspects and key controversial aspects, identify the dependency with other WHs and have earlier coordination.
  AIoT conference call and NWM discussion will be arranged between SA2#163 and SA2#164 for e.g. deployment scenarios including roaming, etc.
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 45% -> 65% | Dec 2024 | SP-231803 1020071

## Slide 13: FS_ AmbientIoT Status at SA#105
Progress since SA#104
  TR 23.700-13 v0.5.0 sent to TSG SA for information
  Revised SID was agreed in SA#104 (SP-240696)
  19 pCRs are approved in SA2#164, including: 8 new solutions, 8 solution updates, 1 new architecture assumption, and 2 interim conclusion.
  Other WG impacts and dependencies
  Incomplete feedback from SA1 due to lack of consensus in SA1 (no feedback on need for an unalterable/permanent equipment identification and related usage, no feedback on business model and need for subscription).
  Several editor’s notes in the TR solution, need coordination with RAN, SA3 and SA5
Outstanding issues
  Diverging views on the need for subscription, network layer security, temporary CN ID, roaming support and related to that, the implications for the overall architecture. Lack of clear SA1 feedback/requirements on these aspects poses a potential risk for SA2 conclusion.
Next steps
  Discuss way forward on open issues, taking into account LS reply from RAN1 and SA1, and 11 postponed papers from SA2#164 meeting.
  Continue with evaluation and conclusion
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 65% -> 80% | December 2024 | SP-240969

## Slide 14: FS_ AmbientIoT Status after SA2#164
  Progress in SA2#164
  19 pCRs are approved in the meeting, including: 8 new solutions, 8 solution updates, 1 new architecture assumption, and 2 interim conclusions
  TR 23.700-13 v0.5.0 is available
  LS in from RAN2 (S2-2407447) was discussed but the reply LS was postponed, due to no consensus
  Other WG dependencies
  Incomplete feedback from SA1 due to lack of consensus in SA1 (no feedback on need for an unalterable/permanent equipment identification and related usage, no feedback on business model and need for subscription).
  Several editor’s notes in the TR solution, need coordination with RAN, SA3 and SA5
Outstanding issues
  Diverging views on the need for subscription, network layer security, temporary CN ID, roaming support and related to that, the implications for the overall architecture. Lack of clear SA1 feedback/requirements on these aspects poses a potential risk for SA2 conclusion.
Next steps
  Discuss way forward on open issues, taking into account LS reply from RAN1 and SA1, and 11 postponed papers from SA2#164 meeting
  Continue with evaluation and conclusion
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 65% -> 80% | December 2024 | SP-240969

## Slide 15: FS_AmbientIoT Status after SA2#165
  Progress since SA2#165
  7 pCR and 1 LS out were agreed.
  Interim conclusions are captured in TR 23.700-13 v1.1.0, including:
    Key issue 1:
      Architecture options of topology 1
      Architecture options of topology 2
      Common aspects for both topologies
    Key issue 2: Permanent AIoT Device ID component
    Key issue 3: AIoT services supported by the 5GC
  RAN impacts and dependencies
  Several editor’s notes in the TR interim conclusions need coordination with RAN and SA3
Outstanding issues
  Architecture options for T1 and T2 needs further discussion in next meeting.
  Whether and how temporary ID is supported for privacy protection, pending SA3 study and feedback on LSout S2-2411049
  Various open issues, e.g., reader selection, reader area identification, for topology 2 whether NAS option can be supported, et al
Next steps
  Finalize the TR conclusion in next SA2 meeting
  Discuss and try to approve the work item in next SA2 meeting
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 80% | SP-240969 | 85% | 

## Slide 16: FS_ AmbientIoT Status at SA#106
Progress since SA#105
  TR cover sheet (including TR 23.700-13 1.2.0) sent to TSG SA for information
  19 pCRs are approved and documented in TR conclusions
  Rel-19 Ambient IoT architecture are concluded that 2 options for Topology 1 (i.e. Direct interface option and Indirect interface option) and 2 options for Topology 2 (i.e. UP option and RRC indirect option)
  Other WG impacts and dependencies
  RAN and SA3 dependencies are listed in the TR cover sheet.
Outstanding issues
  Editor’s notes are captured in TR conclusion, which need further work by SA2 or coordination with other WG, details see TR cover sheet
Next steps
  Decide the R19 next phase work together with RAN, in SA#106
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 80% | SP-240969 | 90% | 

## Slide 17: FS_AmbientIoT Status after SA2#166
  Progress since SA2#166
  12 pCRs, further completing the TR conclusions, are agreed in SA2#166 meeting. 1 LS out to RAN, SA3, SA5 is under email approval.
  Rel-19 Ambient IoT architecture are concluded that 2 options for Topology 1 (i.e. Direct interface option and Indirect interface option) and 2 options for Topology 2 (i.e. UP option and RRC indirect option).
  Highlights of other conclusions:
    AIoT NAS protocol is supported between AIoT Device and AIOTF
    Assistance information provided from AIOTF to RAN/UE Reader
    Reader selection by AIOTF
    Network management of AIoT Device related information
    Permanent AIoT Device identifier, e.g. information of the Device ID, allocation options, locating subscription information
    Network management of subscription-like information management of Ambient IoT Device and AF
    Procedure principles of Ambient IoT Services
    New NEF service exposure for Ambient IoT
    Information provided by AF to request Ambient IoT services
  TR 23.700-13 v1.2.0, is available
  (other aspects see next slide)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 85% | SP-240969 | 90% | 

## Slide 18: FS_AmbientIoT Status after SA2#166
  RAN impacts and dependencies
  Issues e.g. (1) radio resources allocation (what information and how to provide it) to Readers for topology 2. (2) For RRC based option of topology2, whether the gNB performs the down selection of UE readers provided by AIOTF need coordination with RAN WG. Detailed issue list is captured in TR cover sheet
SA3 impacts and dependencies
  Issues e.g. (1) Architecture aspects to support security e.g. Authentication, ID Validation. (2) Whether the temporary ID in the AIoT NAS layer is required for the privacy protection is FFS and is pending SA WG3 decision. Detailed issue list is captured in TR cover sheet
Outstanding issues
  Issues e.g (1) Information that can be stored in the AIoT Device subscription-like data (static information) and that can be stored in AIoT device context data (dynamic information) (2) The entity to store the static and dynamic information, need further work by SA2. Detailed issue list is captured in TR cover sheet.
Next steps
  Decide the R19 next phase work together with RAN, in SA#106
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 85% | SP-240969 | 90% | 

## Slide 19: FS_ AmbientIoT and AmbientIoT Status at SA#107
Progress since SA#106
  TR is 100% complete, and will be sent to SA for approval.
  Started normative work in the new TS 23.xyz. Several pCR are agreed and incorporated in the new TS.
  SA2 approved Rel-19 AmbientIoT WID.
  Other WG impacts and dependencies
  Several issues need coordination with RAN & SA WG3 in the normative phase.
Outstanding issues
  How the AIoT Device ID privacy protection and including ID authentication is done will be concluded by SA WG3. SA2 alignment with SA3 TR conclusions for AIoT Device security including AIoT Device ID privacy protection is FFS.
Next steps
  Address the outstanding issue (as mentioned in the TR cover sheet)
  Continue the normative work, and target for TS completion by SA#108 meeting
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 90% | SP-240969 | 100% | 
N/A | Architecture support of Ambient power-enabled Internet of Things | N/A | June, 2025 | / | SP-241979 | 30% | 
Rel-19 AmbientIoT WID was endorsed in SA#106

## Slide 20: FS_AmbientIoT Status after SA2#167
  Progress since SA2#166
  SA#106 endorsed “Way forward proposal on Architecture support of Ambient IoT” (SP-241980), in which asked SA2 to finalize in Q1 2025, the conclusions for the Ambient IoT work with the focus on device 1 and D1T1.
  Based on the above guidance from SA, SA2 discussed all the editor’s notes in TR 23.700-13, and reached consensus as follows:
    Several editor’s notes are addressed by documenting new conclusion agreements, converting to NOTE or simply removing (as it was determined no work was needed);
    Topology 2 related editor’s notes are left in the TR unhandled due to the scope of Rel-19 update;
    One editor’s note is left in the TR related to AIoT Device security. SA2 will align with SA3 conclusions.
  TR is 100% complete (according to TR cover sheet approved by SA2)
  TR 23.700-13 v1.4.0, is available
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 90% | SP-240969 | 100% | 

## Slide 21: FS_AmbientIoT Status after SA2#167
  RAN impacts and dependencies
  Several issues need coordination with RAN, in the normative phase.
SA3 impacts and dependencies
  SA3 concludes to protect AIoT device ID based on the use of temporary ID.
Outstanding issues
  How the AIoT Device ID privacy protection and including ID authentication is done will be concluded by SA WG3. SA2 alignment with SA3 TR conclusions for AIoT Device security including AIoT Device ID privacy protection is FFS
Next steps
  None. (SA2 to address the outstanding issue, in the normative phase)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 90% | SP-240969 | 100% | 

## Slide 22: AmbientIoT normative work Status after SA2#167
  Progress since SA2#166
  SA#106 endorsed WID “Architecture support of Ambient power-enabled Internet of Things” (SP-241979), which asked SA2, if TUs allow, to proceed in 2025 Q1 with pCRs for a new TS and draft CRs on the already concluded aspects.
  SA2 started the normative work in the new TS 23.xyz, and the progress includes:
    Skeleton of the new TS agreed
    pCRs agreed for TS Scope, references, definitions, Architecture model and concepts, High level functionality and features, AIoT Procedures, Network Functions Services.
  SA2 approved WID (S2-2502772) in SA2#167 meeting
  TS 23.xyz, v0.2.0, is available
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
N/A | Architecture support of Ambient power-enabled Internet of Things | N/A | June, 2025 | / | SP-241979 | 30% | 
Rel-19 AmbientIoT WID was endorsed in SA#106

## Slide 23: AmbientIoT normative work Status after SA2#167
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
N/A | Architecture support of Ambient power-enabled Internet of Things | N/A | June, 2025 | / | SP-241979 | 30% | 
  RAN impacts and dependencies
  Several issues need coordination with RAN, e.g. terminology alignment on AIoT RAN
SA3 impacts and dependencies
  AIoT Device security, including AIoT Device ID privacy protection.
Outstanding issues
  None
Next steps
  Address the outstanding issue (as mentioned in TR cover sheet): “How the AIoT Device ID privacy protection and including ID authentication is done will be concluded by SA WG3. SA2 alignment with SA3 TR conclusions for AIoT Device security including AIoT Device ID privacy protection is FFS.”
  Continue the normative work, and target for completion in SA2#169 meeting
Rel-19 AmbientIoT WID was endorsed in SA#106

## Slide 24: AmbientIoT-ARC Status after SA2#168
  Progress since SA2#167
  17 p-CR were approved in the meeting:
    NG-RAN terminology alignment with RAN, and AIOT reference point naming using “AIOTx”
    Feature update for “reader selection”, “assistance information”, “NF selection for AIOTF, AMF and ADM”, “AIoT Device Profile Management” and “AF authorization”
    Procedure update for inventory and command, including documentation style
    NF description update for AIOTF and NRF
  3 LS out were approved:
    Follow- up questions on Reader selection (to RAN3)
    Check RAN view on removal of service type information (to RAN2 and RAN3)
    Guidance on AIoT Device ID length (to CT4)
  1 CR was agreed in TS 23.501: add AIoT reference point names, by referring to TS 23.369
  TS 23.369 v0.3.0, is available
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070010 | Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-ARC | Jun, 2025 | 30% | SP-250377 | 60% | 
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 100% | SP-240969 | 100% | 

## Slide 25: AmbientIoT-ARC Status after SA2#168
  Impacts and dependencies on other WGs
  RAN3: SA2 need definition of “RAN supported area” from RAN3, to resolve the remaining issue in the feature of “NG-RAN Node and RAN Reader Selection”
  SA3: AIoT Device security, including AIoT Device ID privacy protection
Outstanding issues
  AIoT data structure for AIoT command operations (i.e. read, write, disable): there is no common understanding whether SA2 needs to define AIoT data structure.
  Temporary ID: SA2 may not start work on temporary ID until SA3 concludes the issue.
Next steps
  Continue and complete the normative work in SA2#169.

## Slide 26: AmbientIoT-ARC Status at SA#108
  Progress since SA#107
  36 p-CR were approved, including:
    Feature update for “NF and reader discover and selection”, “assistance information”, “AIoT data structure for command service”, “AIoT permanent identifier”, “AIoT Device Profile Management” and “AF authorization”
    Procedure update for inventory and command
    NF functionality update for NG-RAN, AIOTF, AMF, ADM, NEF and NRF
    NF service update for AIOTF services, AMF services, NEF services and ADM services
    Architecture figure and Protocol update
  5 LS out were approved, including:
    D2R message size(RAN2 and RAN3), paging ID length(RAN2, CT4 and SA3), Follow- up questions on Reader selection (RAN3), Check RAN view on removal of service type information (RAN2 and RAN3), AIoT Device ID length (CT4)
  TS 23.369 is 90% complete, and will be sent to SA plenary for approval
  Impacts and dependencies on other WGs
  SA3: AIoT Device security, including AIoT Device ID privacy protection
Outstanding issues
  Alignment and dependency to SA3 on security aspects and RAN2/RAN3 on RAN aspects are required to be addressed.
  Once SA3 has concluded on security aspects, SA2 needs to determine which procedures are mandatory or optional for the Ambient IoT device
Next steps
  Resolve outstanding issues based on SA3 and RAN WGs progress
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070010 | Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-ARC | Jun, 2025 | 30% | SP-250377 | 90% | 
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 100% | SP-240969 | 100% | 

## Slide 27: AmbientIoT-ARC Status after SA2#170
  Progress since SA#108
  11 CR were approved, including:
    Update UDR service and functionality for AIoT data, update on filtering information update, Support of AIoT session release, Support of AIoT device location exposure, Update of Procedures between AIOTF and NG-RAN for Indirect Connectivity, Removal of AIoT service type provided to NG-RAN, Update on AIoTF selection and NG RAN selection.
  3 LS out were approved, including:
    LS reply to CT4 on UDR service and functionality update for AIoT data
    LS reply to RAN2 and RAN3 on Removal of AIoT service type provided to NG-RAN
    LS to RAN2 on AIoT Device Permanent ID length
  TS 23.369 is 95% complete.
  Impacts and dependencies on other WGs
  SA3: AIoT Device security, including AIoT Device ID privacy protection
Outstanding issues
  Alignment and dependency to SA3 on security aspects.
  Based on SA3 agreements on security aspects, SA2 needs to determine which procedures are mandatory or optional for the Ambient IoT device.
Next steps
  Resolve outstanding issues based on SA3 progress.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070010 | Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-ARC | Jun, 2025 | 90% | SP-250377 | 95% | 
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 100% | SP-240969 | 100% | 

## Slide 28: AmbientIoT-ARC Status at SA#109
  Progress since SA#108
  11 CR were approved, including:
    Update UDR service and functionality for AIoT data, update on filtering information update, Support of AIoT session release, Support of AIoT device location exposure, Update of Procedures between AIOTF and NG-RAN for Indirect Connectivity, Removal of AIoT service type provided to NG-RAN, Update on AIoTF selection and NG RAN selection.
  3 LS out were approved, including:
    LS reply to CT4 on UDR service and functionality update for AIoT data
    LS reply to RAN2 and RAN3 on Removal of AIoT service type provided to NG-RAN
    LS to RAN2 on AIoT Device Permanent ID length
  TS 23.369 is 95% complete.
  Impacts and dependencies on other WGs
  SA3: AIoT Device security, including AIoT Device ID privacy protection
Outstanding issues
  Alignment and dependency to SA3 on security aspects.
  Based on SA3 agreements on security aspects, SA2 needs to determine which procedures are mandatory or optional for the Ambient IoT device.
Next steps
  Resolve outstanding issues based on SA3 progress.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070010 | Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-ARC | Jun, 2025 | 90% | SP-250377 | 95% | 
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 100% | SP-240969 | 100% | 

## Slide 29
In total 11.5 TUs for Study Phase
Check in TSG#106 (Dec’24) for further Ambient IoT work taking into account RAN Ambient IoT progress
FS_AmbientIoT Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 E-AH | Jan 2024 | 0.5 | 0.5 | TR skeleton, scope, architectural assumptions/requirements Start and complete key issue (only for information)Solutions
SA2#161 | Feb 2024 | 2 | 2 | Start solutions discussions key issue update to address the ENs can be considered NOTE: no new key issue proposal will be considered
SA2#162 | Apr 2024 | 2 | 2 | Continue solutions discussions
SA2#163 | May 2024 | 2 | 2 | Continue solutions discussions
SA2#164 | Aug 2024 | 2 | 2 | Continue and complete solution discussions (multi-sourced papers will be handled with priority, any new solution should be in principle different from the existing solutions in the TR and ready for evaluation). Start evaluation/conclusion: group/categorize the solutions, identify the non-controversial aspects and key controversial aspects, identify the dependency with other WHs and have earlier coordination. AIoT conference call and NWM discussion will be arranged between SA2#163 and SA2#164 for e.g. deployment scenarios including roaming, etc.
SA2#165 | Oct 2024 | 1.5 | 2 | Decide way forward for open issues Continue TR conclusion and evaluation, focus on conclusions (and where needed supporting evaluations). Priority will be for contributions that help us all work towards finalizing the conclusion.
SA2#166 | Nov 2024 | 1.5 | 2 | Finalize all key issue conclusions i.e. to address FFS in TR conclusion clause, and new conclusion proposal essential for the study
 | Total | 11.5 | 12.5 |