## 3GPP SA4 Rel-19 and 20 Planning
Date of SA4 meeting | 2025-02-01 | 2025-04-01 | 2025-05-01 | 2025-07-01 | 2025-11-01 | 2026-02-01 | 2026-04-01 | 2026-05-05 | 2026-08-08 | 2026-10-10 | 2026-11-11 | 2026-01-01
SA meeting -> | SA#107 |  | SA#108 | SA#109 Rel-19 Stage 3 | SA#110 Rel-19 OpenAPI/Code | SA#111 |  | SA#112 | SA#113 |  | SA#114 | SA#115 Rel-20 Stage 3
SA4 Meeting-> | SA4#131 | SA4#131bis-e | SA4#132 | SA4#133 | SA4#134 | SA4#135 | SA4#135e-bis | SA4#136 | SA4#137e | SA4#137e-bis | SA4#138 | SA4#139 (TBD)
Audio SWG | IVAS_Codec_Ph2 | IVAS_Codec_Ph2 | IVAS_Codec_Ph2 | IVAS_Codec_Ph2 | IVAS_Codec_Ph2 (Conform.)
Audio SWG |  | FS_ULBC (Rel-20) | FS_ULBC (Rel-20) | FS_ULBC (Rel-20) | FS_ULBC (Rel-20) | FS_ULBC (Rel-20) | FS_ULBC (Rel-20) | FS_ULBC (Rel-20) | ULBC-MED (Rel-20) | ULBC-MED (Rel-20) | ULBC-MED (Rel-20) | ULBC-MED (Rel-20)
Audio SWG | ATIAS_Ph2 | ATIAS_Ph2 | ATIAS_Ph2 | ATIAS_Ph2
Audio SWG | FS_ACAPI | FS_ACAPI | FS_ACAPI
Audio SWG | DaCAS | DaCAS | DaCAS | DaCAS
MBS SWG | FS_MeMe | FS_MeMe | FS_MeMe | MeMe_Stage 3
MBS SWG | FS_AMD | AMD_PRO-MED (MBS) | AMD_PRO-MED (MBS) | AMD_PRO-MED (MBS) | FS_AMD Phase 2 | FS_AMD Phase 2 | FS_AMD Phase 2
MBS SWG | AMD-ARCH-MED | AMD_PRO-MED (5GMS) | AMD_PRO-MED (5GMS) | AMD_PRO-MED (5GMS) | AMD_PRO-MED (OpenAPI)
MBS SWG | FS_MediaEnergyGREEN |  |  | FS_MediaEnergy_ph2-MED | FS_MediaEnergy_ph2-MED | FS_MediaEnergy_ph2-MED | FS_MediaEnergy_ph2-MED | FS_MediaEnergy_ph2-MED
Video SWG | FS_AI4Media | FS_AI4Media | FS_AI4Media
Video SWG | VOPS | VOPS | VOPS | VOPS (Conformance) | VOPS (Conformance)
Video SWG | FS_AVATAR
Video SWG | FS_Beyond2D | FS_Beyond2D | FS_Beyond2D | FS_Beyond2D
Video SWG | FS_ARSpatial | FS_ARSpatial | FS_ARSpatial
RTC SWG | FS_HapticsMedia | AvCall-MED | AvCall-MED | AvCall-MED | FS_AVATAR_Ph2 | FS_AVATAR_Ph3 | FS_AVATAR_Ph4
RTC SWG | FS_iRTCW_Ph2 | FS_iRTCW_Ph2 | FS_iRTCW_Ph2
RTC SWG | 5G_RTP_Ph2 | 5G_RTP_Ph2 | 5G_RTP_Ph2 | 5G_RTP_Ph2
RTC SWG | SR_IMS | SR_IMS | SR_IMS
Total # SID/WID | 17 | 16 | 16 | 12 | 7 | 4 | 4 | 2 | 1 | 1 | 1 | 1
Agreed
Exception request
TBD
Completed