3GPP TSG-SA WG4 Meeting#134						      S4-251782

Dallas, US 17th – 21st Nov 2025	                                                              revision of S4-251344

Agenda item: 	17.1

Source: 	Apple Inc.

Title: 	[FS_AIF-Med] Draft Work Plan

Version:	0.2

Document for	Discussion and agreement

# 1 Introduction

The following document provides a work plan for the Feasibility Study on advanced image formats.

# 2 Objective

The objectives of work on Feasibility Study on advanced image formats are reproduced here as reference.

The objectives of this study are to:

- Identify currently widely employed use cases of still images on mobile devices:

  - Sharing of images using messaging services including 3GPP and 3rd party services.

  - Traditional photo taking for uploading to and sharing via cloud, social networking, as well as device-to-device sharing.

  - Taking, processing, and sharing of screen captures.

  - HDR processing, visualization, and rendering aspects.

- Identify already widely employed and 3GPP relevant imaging formats in the market for each of these use cases. When video coding tools are used for images, the study would focus on existing 3GPP codecs, i.e. AVC and HEVC video coding standards.

- Document image capturing formats for traditional photography.

- Based on the identified image formats, identify key operating points suitable for interoperability for these image formats.

- In the cases where interoperability is not the primary focus, a list of guidelines may be provided for mobile devices, based on other criteria such as screen capabilities and computational resource consumption. These use cases are:

  - use of tiling for edits and random access of large images.

  - HDR gain map metadata processing capabilities in relation to device support of SDR only/HLG/PQ.

- Provide recommendations for potential subsequent normative work.

- Liaise with MPEG, TC 42, and GSMA RCSG on this topic as needed.

# 4 Proposed Time and Work Plan

Legend: Black items like this: upcoming work. Grey items like this: past work. Lighter grey items like this: (also crossed out) not done, pushed forward/postpend:

| Meeting | Work on “Feasibility Study on advanced image formats” |
| --- | --- |
| 3GPP SA4#134 (17th – 21st November, 2025, Dallas, US) | - Agree study item |
| SA#110 (9th – 12th Dec 2025, Baltimore, US) | - Approve study item in SP-240XYZ. |
| SA4#135 (9th-13th Feb 2026, India, IN) | - Gather currently deployed use cases for images. - Gather deployed imaging formats for each use case. - Identify key interoperability points for the image formats. - Provide guidelines where interoperability is not a focus. - Start identifying guidance for normative work. |
| SA#111 (10th - 13th March, 2026, Japan, JP) | - Send TR to SA plenary for information. |
| SA4#135-bis-e (13th – 17th April 2026) | - Complete gathering deployed imaging formats for each use case. - Complete identifying interoperability points for the image formats. - Complete guidelines where interoperability is not a focus. - Complete guidance for normative work. |
| SA#112 (9th - 12th June, 2026, Singapore, SG) | - Send TR to SA plenary for approval. |