3GPP TSG-SA WG4 Meeting #134	S4-251862

# 17 – 21 November 2025, Dallas, Texas, USA

# Source:	Pengcheng Laboratory, Huawei, OPPO, vivo, ZTE, China Telecom, Hisilicon

# Title:	[FS_ULLV] Work Plan v0.1

# Document for:	Agreement

# Agenda Item:	17.2

- Introduction

The study item has the following objectives:

- Refine SA1-defined use cases and specific requirements for the Ultra-Low Latency (ULL) video applications, e.g. cloud gaming, autonomous driving, and remote mining.

- Investigate and identify test conditions, evaluation criteria, and evaluation methodology for ultra-low latency video applications, taking 3GPP TR 26.926 as a reference model where applicable.

- Investigate and document processing strategies and technologies for ultra-low latency video applications under network fluctuation, e.g., packet-loss resilience, jitter and congestion control, and optimized configurations.

- Develop comprehensive end-to-end characterization of video quality and latency performance for 3GPP network, based on identified test conditions and evaluation methodologies (Objective 2), and leveraging packet loss resilient configurations for ultra-low latency scenarios (Objective 3).

- Evaluate end-to-end video quality and latency performance for ultra-low-latency applications, building on the test conditions, methodologies, and characterization developed in Objectives 2–4, and referencing the codec configurations specified in 3GPP.

- Time Plan

| Meeting | Study on Ultra-Low Latency Video Communication Characterization and Evaluation | Completion Status |
| --- | --- | --- |
| SA4#134 - Nov. 2025, Dallas) | - Agree New Study Item on “Study on Ultra-Low Latency Video Communication Characterization and Evaluation” |  |
| SA#110 (09-12 Dec. 2025, Baltimore, US) | - Approve New Study Item on “Study on Ultra-Low Latency Video Communication Characterization and Evaluation” |  |
| SA4#135 (2-13 Feb. 2026, India) | - Initiate work on: - Refine SA1-defined ULL use cases(e.g. cloud gaming, autonomous driving, and remote mining). - Define an initial set of KPIs and service requirements per use case (e.g. E2E latency ranges, frame rate, reliability). - Draft TR 26.xxx skeleton and agree on main clause structure (e.g., Scope, Use cases, Test conditions, Evaluation Criteria, Evaluation Methodology, etc.). - High-level investigate and identify of relevant test conditions, evaluation criteria and evaluation methodology, taking TR 26.926 as reference where applicable. | Target 10% Real % |
| SA4#135e (13-17 Apr. 2026 e-meeting) | - Complete work on: - Consolidating and documenting refined ULL use cases, requirements and KPIs per scenario - Progress work on: - Define detailed test conditions and evaluation framework per ULL use case: - Identify representative test channel, content and traffic models per prioritized use case. - Identify the configurations of video format, transport and processing for ultra-low latency operation. - Define evaluation metrics and computation methods for end-to-end latency, video quality, and QoE. - Define an end-to-end evaluation framework specifying experiment matrices, simulation procedures, and result reporting for each ULL use case. - Initial list of test content and corresponding usage scenarios. - Initiate work on: - Investigating processing strategies and technologies for ULL under network fluctuation: - Packet-loss resilience methods, - Jitter and congestion control strategies, - Joint encoder/decoder/transport configuration scheme for low latency. | Target 30% Real % |
| SA4#136 (11-15 May 2026, Montreal) | - Complete work on: - Define detailed test conditions and evaluation framework per ULL use case: - Identify representative test channel, content and traffic models per prioritized use case. - Identify the configurations of video format, transport and processing for ultra-low latency operation. - Define evaluation metrics and computation methods for end-to-end latency, video quality, and QoE. - Define an end-to-end evaluation framework specifying experiment matrices, simulation procedures, and result reporting for each ULL use case. - Initial list of test content and corresponding usage scenarios. - Progress work on: - Investigating processing strategies and technologies for ULL under network fluctuation: - Packet-loss resilience methods, - Jitter and congestion control strategies, - Joint encoder/decoder/transport configuration scheme for low latency. - Initiate work on: - End-to-end characterization of video quality and latency performance for selected ULL scenarios: - Define reference sequences, anchors and reference tools for ULL scenarios. - Specify objective quality metrics, bitrate points and reference computation methods. - Apply encoding constraints and design test matrices against anchor configurations. - Execute characterization and verification, generating anchor results and documentation for the TR. - Evaluate End-to-End Video Quality and Latency Performance for ULL Applications - Integrate inputs from Objectives 1–4 to define final ULL scenarios, codec/transport settings, and measurement parameters. - Set up end-to-end test environment (encoder → transport → decoder → rendering) using the inputs from Objectives 1-4. - Execute experiments under representative 3GPP network conditions and collect full trace data for quality and latency evaluation. - Compute and analyze objective metrics and latency statistics. | Target 50% Real % |
| SA4#137e (24-28 Aug. 2026, e-meeting) | - Complete work on: - Investigating processing strategies and technologies for ULL under network fluctuation: - Packet-loss resilience methods, - Jitter and congestion control strategies, - Joint encoder/decoder/transport configuration scheme for low latency. - Progress work on: - End-to-end characterization of video quality and latency performance for selected ULL scenarios: - Define reference sequences, anchors and reference tools for ULL scenarios. - Specify objective quality metrics, bitrate points and reference computation methods. - Apply encoding constraints and design test matrices against anchor configurations. - Execute characterization and verification, generating anchor results and documentation for the TR. - Evaluate End-to-End Video Quality and Latency Performance for ULL Applications - Integrate inputs from Objectives 1–4 to define final ULL scenarios, codec/transport settings, and measurement parameters. - Set up end-to-end test environment (encoder → transport → decoder → rendering) using the inputs from Objectives 1-4. - Execute experiments under representative 3GPP network conditions and collect full trace data for quality and latency evaluation. - Compute and analyze objective metrics and latency statistics. - Verify and document results for the Technical Report. - Identify gaps and deficiencies of existing 3GPP configurations/mechanisms, offering recommendations to enhance specification and capabilities for ULL scenarios. - Initiate work on potential related normative work and conclusions. - Communicate with other 3GPP working groups and external organizations, if necessary. - Agree on TR 26.xxx to be sent to SA plenary for information | Target 80% Real % |
| SA#113 (15-18 Sep. 2026, EU) | - Present TR 26.xxx to SA for information |  |
| SA4#137e-bis (12-16 Oct. 2026, e-meeting) | - Complete work on: - End-to-end characterization of video quality and latency performance for selected ULL scenarios: - Define reference sequences, anchors and reference tools for ULL scenarios. - Specify objective quality metrics, bitrate points and reference computation methods. - Apply encoding constraints and design test matrices against anchor configurations. - Execute characterization and verification, generating anchor results and documentation for the TR. - Evaluate End-to-End Video Quality and Latency Performance for ULL Applications - Integrate inputs from Objectives 1–4 to define final ULL scenarios, codec/transport settings, and measurement parameters. - Set up end-to-end test environment (encoder → transport → decoder → rendering) using the inputs from Objectives 1-4. - Execute experiments under representative 3GPP network conditions and collect full trace data for quality and latency evaluation. - Compute and analyze objective metrics and latency statistics. - Identify gaps and deficiencies of existing 3GPP configurations/mechanisms, offering recommendations to enhance specification and capabilities for ULL scenarios. - Identify potential related normative work and conclusions. - Communicate with other 3GPP working groups and external organizations, if necessary. | Target 90% Real % |
| SA4#138 (16-20 Nov. 2026, North America) | - Complete work on identify potential related normative work and conclusions. - Complete all remaining open issues. - Agree on TR 26.xxx to be sent to SA plenary for approval | Target 100% Real % |
| SA#114 (08-11 Dec. 2026, US) | - Send TR 26.xxx to SA for Approval |  |