## Slide 1: 3GPP IT Task Force Group Report and Recommendations
Erik Guttman
3GPP IT Task Force Convenor

## Slide 2: Status
Feasibility Study on Virtual Presence in Physical Meetings [Completed]
  We began study 2 year ago.
    A-PCG41/01 Ongoing - To study the conditions under which virtual presence in physical meetings/virtual meetings would be practicable and the types of tools that would be required to support them [3GPP/PCG#41(18)05].
    We followed the WP Group decisions upon elections and other matters.
    The study takes into account 2020 experience with e-meetings.
    The findings may be important when we begin to meet again face to face.
  Recommendation for action – endorse the recommendations on slides 4, 5 and 6 which have been derived from section 10 of the study.
Trials for Hybrid meetings [Completed]
  A-PCG42/05 Ongoing - To consider the possibility to introduce remote monitoring trials within some of the smaller working groups and to report the experience gained to PCG [3GPP/PCG#42(19)17&18].
    Report at PCG 44 already [PCG(20)44-31]. Further trials will have to wait until this is possible.
    In some sense, this action item has been overtaken by events – remote monitoring is now ‘normal.’

## Slide 3: Status, continued
Improved exposure to information about the work of 3GPP [Ongoing]
  There is an outstanding action for the 3GPP IT Task Force: Action PCG43/03 Ongoing - IT Improvements Ad Hoc Group, in conjunction with the TSG Chairmen, to review the responses that MCC had provided to their recommendations on the accessibility of 3GPP’s work [3GPP/PCG#43(19)10].
  This relates to the work reported to PCG #41
    3GPP/PCG#41(18)21, IT Improvements Report, IT Improvements Convenor
    A number of potential improvements to expose the work of 3GPP were identified.
  For the next PCG meeting, the 3GPP IT Task Force will review the response and work with MCC IT leadership. The 3GPP IT Task Force will provide a final report.

## Slide 4: Recommendation 1 (endorse proposals)
Feasibility Study on Virtual Presence in Physical Meetings
  The capabilities listed below are considered ‘new’ (not yet supported by existing facilities available to 3GPP delegates and MCC.)
  The study found that the below are Required Functionality.
  Recommendations:
    A tool enabling anyone (those present in the physical meeting and those who are remote) to see the live tdoc status, agenda
    Additional consideration of internet accessible files from the physical meeting is needed, so that DRAFTS and INBOX files are synchronized between the internet and local file servers.
    A tool enabling message (text) based chat would facilitate off-line communication between delegates physically present in the meeting and those remotely participating. This facility should have an archive so that the text messages exchanged can be accessed at any time during and subsequent to the meeting.

## Slide 5: Recommendation 2 (endorse proposals)
Feasibility Study on Virtual Presence in Physical Meetings [Complete]
  The following recommendations use existing IT technology to support Hybrid meetings, but with specific considerations.
  The study indicates that these are Essential In-meeting support.
  Recommendations:
    Patching the audio of the physical meeting into the GTM.
    Patching the video output of the screen at the meeting into the GTM
    Ensuring the sound quality for the remote participants is adequate. This can be accomplished by running a ‘sound check’ during the minutes before session start, where participants speak one by one, and receive confirmation of their sound quality and level by an audio technician (or volunteer) present at the meeting.
    In general, good quality audio is essential for remote participation roles in a hybrid meeting to succeed – so it is recommended that sessions have an audio technician (at least early in the meeting week.)
    It is recommended that use of GTM and TOHRU by participants at the face to face meeting be possible, so that parallel sessions and informal drafting sessions can be enabled for hybrid meeting participants.

## Slide 6: Recommendation 3 (for endorsement)
Recommendations for IT Infrastructure and Service Support
  Qualification:
    An overall recommendation is to set expectations for Hybrid Meetings realistically. Hybrid Meeting IT support should proceed for the remote participants on a ‘best effort basis.’ The physical meeting should proceed even if there is an issue with IT support (e.g. due to problems with internet connectivity) to one, some or all remote participants.

## Slide 7: Recommendation conclusion
The 3GPP IT Task Force requests that PCG endorse these recommendations and give MCC and hosts the task to provide the required functionality (Recommendation 1) and in-meeting support (Recommendation 2).
  It would be advantageous to complete development of this IT support in time for Hybrid meetings, when physical meetings are again possible (e.g. 2022).

## Slide 8: Please see the attached
The informal “TR” developed by the 3GPP IT Task Force is attached.

## Slide 9: Acknowledgements
Thanks for the discussion and support on the 3GPP IT Task Force discussion list, especially from John Meredith.