## RIL list for R18 SONMDT
ID | Delegate | Work Item | Class | TDoc | Status | Processed | Proposed Conclusion | Description | Proposed Change | Comments | Section
C300 | CATT (Haocheng) | SONMDT | 1 | None | Agreed |  |  | Should clarify which (LTE or NR) VarRLF-Report is checked here. | 3> if reconnectCellId in VarRLF-Report of TS 38.331 [82] is not set, and if the UE selected the current PCell immediately after failure in performing MobilityFromNRCommand: | [Huawei - Chen Jun] PropAgree The condition of the corresponding text states that the RLF report variable is about NR RLF report, so the change is ok. Will be corrected in the correction CR | 5.3.3.4
N003 | Jarkko T. Koskela (Nokia) | NR_ENDC_SON_MDT_enh2-Core | 0 | None | Agreed |  |  | what is SHR? | add abbreviation or spell out? This does not seem to be used in many occasions so just writing this out might be simplest. | [Huawei - Chen Jun] PropAgree Ok to add SHR into the abbreviation section. Will be corrected in the correction CR | 5.3.11.3
C301 | CATT (Haocheng) | SONMDT | 1 | None | Agreed |  |  | Add the description of UE capability. | 5> if the UE supports LTE RLF report for voice fallback in LTE and if voiceFallbackIndication is included in the MobilityFromNRCommand: | [Huawei - Chen Jun] PropAgree No strong opinion. On one hand, the previous text works and the UE should anyway check the corresponding capability. This UE capability checking seems obvious (and lots of changes do not capture UE capability checking inside). On the other hand, the change is technically correct. Will be corrected in the correction CR | 5.3.11.3
C302 | CATT (Haocheng) | SONMDT | 1 | None | Agreed |  |  | The new introduced NR RACH report information should also “except for NB-IoT”. | 1> except for NB-IoT, if rach-ReportReqNR is set to true, and if the UE has NR RACH report information available in VarRA-Report of TS 38.331 [82] that is stored and the RPLMN is included in plmn-IdentityList stored in VarRA-Report of TS 38.331 [82], set the content of rach-ReportNR in the UEInformationResponse message as below: | [Huawei - Chen Jun] PropAgree The change is ok as NB-IoT case was not discussed for this RA report functionality. Will be corrected in the correction CR | 5.6.5.3
C303 | CATT (Haocheng) | SONMDT | 1 | None | ToDo |  |  | The NR RACH report information should be included into the UEInformationResponse message before submitting the message. All the content of “1>” should be moved before “1> if the logMeasReport is included in the UEInformationResponse”. | … 1> except for NB-IoT, if the coarseLocationReq is set to true: 2> if available, include the coarseLocationInfo; 1> if rach-ReportReqNR is set to true, and if the UE has NR RACH report information available in VarRA-Report of TS 38.331 [82] that is stored and the RPLMN is included in plmn-IdentityList stored in VarRA-Report of TS 38.331 [82], set the content of rach-ReportNR in the UEInformationResponse message as below: 2> for each RA-Report of ra-ReportList in VarRA-Report of TS 38.331 [82]: 3> include it as part of rach-ReportListNR; 3> if the cellIdListNR is not set or the cellId of RA-Report has not been included in cellIdListNR: 4> add a new entry in cellIdListNR and set the cellIdNR to the global cell identity including the tracking area code, if available, otherwise to the physical cell identity and carrier frequency, as indicated in the cellId of RA-Report; 2> discard the RA-Report that was included in rach-ReportListNR from ra-ReportList in VarRA-Report of TS 38.331[82] upon successful delivery of the UEInformationResponse message as confirmed by lower layers. 1> if the logMeasReport is included in the UEInformationResponse: 2> submit the UEInformationResponse message to lower layers for transmission via SRB2; 2> discard the logged measurement entries included in the logMeasInfoList from VarLogMeasReport upon successful delivery of the UEInformationResponse message confirmed by lower layers; 1> else: 2> submit the UEInformationResponse message to lower layers for transmission via SRB1; 1> if rach-ReportReqNR is set to true, and if the UE has NR RACH report information available in VarRA-Report of TS 38.331 [82] that is stored and the RPLMN is included in plmn-IdentityList stored in VarRA-Report of TS 38.331 [82], set the content of rach-ReportNR in the UEInformationResponse message as below: 2> for each RA-Report of ra-ReportList in VarRA-Report of TS 38.331 [82]: 3> include it as part of rach-ReportListNR; 3> if the cellIdListNR is not set or the cellId of RA-Report has not been included in cellIdListNR: 4> add a new entry in cellIdListNR and set the cellIdNR to the global cell identity including the tracking area code, if available, otherwise to the physical cell identity and carrier frequency, as indicated in the cellId of RA-Report; 2> discard the RA-Report that was included in rach-ReportListNR from ra-ReportList in VarRA-Report of TS 38.331[82] upon successful delivery of the UEInformationResponse message as confirmed by lower layers. | Huawei - Chen Jun] Can be discussed. The rapporteur thinks that one alternative change is to move the following text to the end of this section. It is proposed RAN2 to discuss this RIL. 1> if the logMeasReport is included in the UEInformationResponse: 2> submit the UEInformationResponse message to lower layers for transmission via SRB2; 2> discard the logged measurement entries included in the logMeasInfoList from VarLogMeasReport upon successful delivery of the UEInformationResponse message confirmed by lower layers; 1> else: 2> submit the UEInformationResponse message to lower layers for transmission via SRB1; [Huawei - Chen Jun @20240304] C303 was postponed based on RAN2#125 progress. | 5.6.5.3
C304 | CATT (Haocheng) | SONMDT | 1 | None | Rejected |  |  | NR RACH information can only be reported together with the LTE RA report based on the RAN3 agreed 37.340 BLCR: “When a E-UTRAN node retrieves the E-UTRA RA Report, it can also request UE to include the NR RA Report”. So to capture this point, the “-- Need ON” can be change to a “Cond”. | rach-ReportReqNR-r18 ENUMERATED {true} OPTIONAL, -- Cond RA-ReportLTENeed ON Conditional presence Explanation  RA-ReportLTE The field is optional present, Need ON, if rach-ReportReq is present. Otherwise the field is not present.   | [Huawei - Chen Jun] Can be discussed. At RAN2#124 meeting, the following agreement was made. In our understanding, it means LTE side can request NR RACH report via the flag (separate from the flag for LTE RA report). Agreements UE report all available NR RACH report based on request from LTE BS [Huawei - Chen Jun @20240304] It was rejected based on RAN2#125 discussion. | 6.2.2
C305 | CATT (Haocheng) | SONMDT | 2 | None | Agreed |  |  | Since the new added IE is changed to “RACH-Report-v1800” which is an NCE, the R16 fields should not be duplicated listed in this IE. | numberOfPreamblesSent-r18 NumberOfPreamblesSent-r11 OPTIONAL, contentionDetected-r18 BOOLEAN OPTIONAL, | [Huawei - Chen Jun] Can be discussed. Since it is class 2, it is suggested companies to double check it (issue and proposed changes). [Huawei - Chen Jun @20240304] RAN2#125 agreed that:  Introduce a new IE, not a critical extension In addition, during CB session, RAN2 made the following agreement:  [AT125][654][SONMDT] TS 36.331 (Huawei) Scope: Develop TPs for agreements during the meeting; no need to discuss the actual CR, which will be approved by a post meeting email discussion Intended outcome: Report in R2-2401672 Deadline: Friday CB session  The change to UEInformationResponse-v1800-IEs as in R2-2401672 is agreeable | 6.2.2
C306 | CATT (Haocheng) | SONMDT | 1 | None | Agreed |  |  | IE is a parameter structure of the field, so a field can not be used to indicate an IE. Here the wording can be change to “Include the XXX IE”. | rach-ReportListNR This field is used to indicate the list of NR RACH report information, including the NR RA-ReportList IE, which is specified in TS 38.331 [82]. | [Huawei - Chen Jun] PropAgree The change is ok. Will be corrected in the correction CR This RIL is agreeable from CR rapporteur's point of view, however, the status is ToDo. It can be further updated (if needed) during the meeting. [Huawei - Chen Jun @20240304] C306 was agreed based on RAN2#125 progress. | 6.2.2
E033 | Ericsson (Ali) | NR_ENDC_SON_MDT_enh2-Core | 1 | None | Agreed |  | v003 | This field description is not needed here. It should be instead added to the NR spec. | This field is used to indicate the cell in which the UE comes back to connected after connection failure and after failing to perform reestablishment or to indicate the cell in which the UE comes back to connected as part of cell selection after MobilityFromNRCommand execution failure. | [Huawei - Chen Jun] PropAgree The change is ok. Will be corrected in the correction CR In TS 38.331 v18.0.0, the following field description is defined, and then the referring text here is not needed. reconnectCellId This field is used to indicate the cell in which the UE comes back to connected after connection failure and after failing to perform reestablishment. | 6.2.2
C307 | CATT (Haocheng) | SONMDT | 1 | None | Agreed |  |  | This time can be set without re-connected cell ID only when UE fallback to an acceptable cell with ongoing emergency call. | timeUntilReconnection This field is used to indicate the time that elapsed between the connection (radio link or handover) failure and the next time the UE comes to RRC CONNECTED in an NR or EUTRA cell, after failing to perform reestablishment or after cell selection to an acceptable cell after MobilityFromNRCommand execution failure including fallback indication. Value in seconds. The maximum value 172800 means 172800s or longer. | [Huawei - Chen Jun] PropAgree This change is ok. Will be corrected in the correction CR At RAN2#122 meeting, it was agreed. So the change is aligned with this agreement. 2 UE to log the time until reconnection during RRC connection establishment to the acceptable cell and reconnection cell ID in is absent, which will reuse the legacy field. | 6.2.2