## Slide 1: SA WG3 Status report for FS_ZTS
Sheeba Backia Mary B.
Lenovo

## Slide 2
August meeting (SA3#108-e):
  Agree on the main key issue(s) for the SID (KIs were not agreed. But agreed a tenet evaluation template).
  Main Key Issue includes: ‘Need for continuous trust evaluation’ and ‘Scenarios which can benefit from trust evaluation outcome’.
October Meeting (SA3#108Adhoc-e):
  Agree on the key issue(s) for the SID. (Agreed partial KI details. KIs threat and security requirement was not agreed. But agreed some tenet evaluation information (e.g., T1, T2, T3, T5, T6, T7)
  Discuss and agree on evaluation information for the Tenets.
November Meeting (SA3#109):
  A Key Issue was agreed. (Agreed partial KI threat and security requirement was agreed. T7 evaluation was done).
  A tenet evaluation was refined (e.g., T7).
January Meeting (SA3#109-bis):
  Discuss and agree on solutions for KI#1.
  Discuss and agree on additional KIs (if any).
  Resolve EN in Key Issue#1.
February Meeting (SA3#110):
  The ENs in KI#1 Security Requirement was cleaned up.
  Discussed solutions to KI#1, but there was no approval/consensus reached on the solutions.
April Meeting (SA3#110-bis-e):
  Discuss and agree on solutions for KI#1. (Couldn’t make it - sustained objection from 2 companies, with no revision proposal received).
  Discuss and agree on additional KIs (if any). (No agreement - sustained objection from 2 companies).
  Completion of Tenet 5 and 6 evaluations. (Completed Tenet 5 evaluation but not Tenet 6)
  Draw initial conclusions for the Key Issue #1. (Couldn’t make it - sustained objection from 2 companies).
May Meeting (SA3#111):
  Complete the evaluations (if any left out) and complete the conclusions.). (No agreement on Solution and conclusion, but some suggestions received from the objected company for the possible convergence in the next meeting (ref. SA3 thread). Apart from this, T6 evaluation tdocs were opened and agreed. Rest all tdocs (i.e., 7) couldn’t be treated due to time constraints)
  WID proposal is planned to be submitted for discussion and approval. (Not applicable – TR do not have any form of agreed solution)
    Send the TR 33.894 for approval
    Initiate the Normative work.
Aug Meeting (SA3#112):
  All pending tenet evaluation was completed (especially tenets 4, 6,7).
  KI#1 Solution was discussed and agreed.
  KI#1 was concluded
    Agreed Conclusion: Solution#1 illustrates how existing services can be used to collect the necessary data listed in the solution for security monitoring purposes in line with the principles of zero trust (Tenet 5). However, no consensus could be reached on the normative work.
  WID proposal and CR was discussed for the normative work but no consensus reached.
    Due to 1 / 2 companies objection.
Over-all plan
FS_ZTS Status
The SID AI was not on agenda

## Slide 3
Key Issues | Solutions | Solution status
KI#1 Agreed (Key Issue #1: Need for continuous security monitoring) | Solution #1 Agreed for KI#1 (Data Collection to enable security monitoring for the Core Network) | Solution was discussed and agreed.
TR 33.894 Summary
FS_ZTS Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Agreed Skeleton and Scope.
KI not agreed.
SA3#108
Aug 22-26, 2022
Agreed Tenet evaluation template.
KI not agreed.
SA3#108 Adhoc-e Oct 10-14, 2022
Partial Key Issue Agreed.
Tenet evaluations initiated.
SA3#109
Nov 14-18, 2022
Key Issue Security requirement agreed.
Tenet evaluations Continued.
SA3#110-e
April 17-21, 2023
Solution to KI#1 not agreed.
Tenet evaluations Continued.
SA also 3#110
Feb 20-22, 2023
Key Issue Sec. req. section cleaned-up
Tenet evaluations Continued.
1
2
3
4
5
SA3#111
May 22-26, 2023
Solution and Conclusion to KI#1 not agreed.
Tenet evaluations Continued. Status: T1, T2, T3, T5 completed. T6, T7 have ENs and T4 not done).
SA3#112
Aug 14-18, 2023
Formulated agreeable solution text and concluded KI#1.  Done
Completed and cleaned-up the Release18 ZTS SID.  Done
Completed all Tenet evaluations  Done
5
6
7

## Slide 4
General
  TR 33.894 v0.7.0 contains scope, tenet evlauation details (completed for Tenet 1,2,3,4,5,6, and 7), 1 main key issue, solution to KI#1 and conclusion.
    Main Key Issue#1 includes: ‘Need for continuous security monitoring’.
    Solution to KI#1: Data Collection to enable security monitoring for the Core Network
Dependencies:
  None (this SID has no RAN impacts)
  If any other work group impact identified, it was planned to be recorded in the conclusion. So far none captured in conclusion.
FS_ZTS status after SA3#112
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960038 | Study on Zero Trust Security principles in mobile networks | FS_ZTS | Rel-18 | S3 | Sept-2023 | 30% | 100% | TR 33.894

## Slide 5: FS_ZTS status after SA3#112
  SA2/RAN impacts and dependencies:
  None for RAN and SA2 or other SA groups as per the conclusion.
Contentious Issue:
  Consensus could not be reached on the normative work for KI#1 and so the progress of the WID/CR related to KI#1 conclusion was impacted.
Focus for the Next Meeting :
  Reach Consensus on open aspects of the agreed KI#1 conclusion.
Overall Plan:
  See dedicated slide (No. 2).
Risks:
  Already solution discussion phase got delayed due to late alignment on KI#1. Similar traces were observed in the solution and KI#1 conclusion discussions and agreement. Agreed KI#1 conclusion copied below - Lack of consensus over normative work impacts the Rel.18 normative progress and completion.
    Solution#1 illustrates how existing services can be used to collect the necessary data listed in the solution for security monitoring purposes in line with the principles of zero trust (Tenet 5). However, no consensus could be reached on the normative work.