## Slide 1: SA WG3 Status report for AKMA_GBA_OSCORE
Vlasios Tsiatsis
Ericsson

## Slide 2
February meeting
  GBA OSCORE living document of TS 33.220
  AKMA OSCORE living document of TS 33.535
April meeting
  The topic is NOT in scope
May meeting
  Finalize the draft CR/Living document to 33.220 for GBA OSCORE and add Ua/Ua* protocol identifiers in 33.220 for both GBA OSCORE and AKMA OSCORE
  Draft CR/Living document for 33.535 for AKMA OSCORE
  Potential conversion of draft CR/Living documents of 33.220 and 33.535 to CRs.
August meeting
  Add Ua* protocol identifier in the living document of 33.220 for AKMA OSCORE
  Conversion of the living document to 33.220 for GBA OSCORE to CR
  CR for TS 33.535 for AKMA OSCORE, conversion of draft CR to CR
November meeting
  No plan, the work was completed in SA3#112, August 14-18, 2023.
Overall plan
AKMA_GBA_OSCORE Status

## Slide 3
Living document | Description | Status
Living document to 33.220: GBA OSCORE | GBA OSCORE specification | 100% done
Living document to 33.220: GBA OSCORE | Ua, Ua* protocol identifiers | 100% done
Living document to 33.535: AKMA OSCORE | AKMA OSCORE specification | 100% done
Living document
AKMA_GBA_OSCORE Status
SA3#110 Feb 24-28, 2023
GBA OSCORE living document of TS 33.220
AKMA OSCORE living document of TS 33.535
SA3#110-bis-e Apr 17-21, 2023
Topic not in scope
SA3#111 May 22-26, 2023
Finalization of draft CRs and conversion to CRs to the extend possible
SA3#112 Aug 14-20, 2023
Final touches to open Living documents and conversion of living documents to CRs.

## Slide 4
General
  The living document to the TS 33.220 (GBA), covering the GBA OSCORE specification, was converted to a CR and agreed in SA3#112
  A CR to TS 33.535 (AKMA), covering the AKMA OSCORE specification, was submitted to the SA3#112 and was agreed
Dependencies:
  The WI does not depend on any other item, it is also expected to produce minimal stage 3 specification.
  The WI may have impact on CT1 for the GBA/AKMA.
  Just in case an exception sheet was submitted in SA3#111 and was agreed.
AKMA_GBA_OSCORE status after SA3#112
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
980023 | WID on IETF OSCORE protocol profiles for GBA and AKMA | AKMA_GBA_OSCORE | Rel-18 | S3 | June September 2023 | 80% | 100% | CR TS 33.220 CR TS 33.535

## Slide 5: AKMA_GBA_OSCORE status after SA3#112
  SA2/RAN impacts and dependencies:
  None. This is an exclusive SA3 topic.
Contentious Issue(s):
  None for the moment.
Focus for the Next (applicable) Meeting (November SA3#113 meeting):
  None, the work item was completed in SA3#112.
Overall Plan:
  See dedicated slide
Risks:
  None