## Slide 1: SA WG3 Status report for AKMA_GBA_OSCORE
Vlasios Tsiatsis
Ericsson

## Slide 2
February meeting
  GBA OSCORE living document of TS 33.220
  AKMA OSCORE living document of TS 33.535
April meeting
  The topic is NOT in scope
May meeting
  Finalize the draft CR/Living document to 33.220 for GBA OSCORE and add Ua/Ua* protocol identifiers in 33.220 for both GBA OSCORE and AKMA OSCORE
  Draft CR/Living document for 33.535 for AKMA OSCORE
  Potential conversion of draft CR/Living documents of 33.220 and 33.535 to CRs.
August meeting
  Draft CR for TS 33.535 for AKMA OSCORE, conversion of draft CR to CR
  Add Ua* protocol identifier in the living document of 33.220 for AKMA OSCORE
  Conversion of the living document to 33.220 for GBA OSCORE to CR
Overall plan
AKMA_GBA_OSCORE Status

## Slide 3
Living document | Description | Status
Living document to 33.220: GBA OSCORE | GBA OSCORE specification | 100% done
Living document to 33.220: GBA OSCORE | Ua, Ua* protocol identifiers | 50% done
Living document to 33.535: AKMA OSCORE | AKMA OSCORE specification | 0% done
Living document
AKMA_GBA_OSCORE Status
SA3#110 Feb 24-28, 2023
GBA OSCORE living document of TS 33.220
AKMA OSCORE living document of TS 33.535
SA3#110-bis-e Apr 17-21, 2023
Topic not in scope
SA3#111 May 22-26, 2023
Finalization of draft CRs and conversion to CRs to the extend possible
SA3#112 Aug 14-20, 2023
Final touches to open Living documents and conversion of living documents to CRs.

## Slide 4
General
  It is expected that two living documents will be developed and converted to CRs
    Living document to TS 33.220 for the GBA OSCORE and the Ua/ua* protocol identifiers
    Living document to TS 33.535 for the AKMA OSCORE
Dependencies:
  The WI does not depend on any other item, it is also expected to produce minimal stage 3 specification.
  The WI may have impact on CT1 for the GBA/AKMA
AKMA_GBA_OSCORE status after SA3#111
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
980023 | WID on IETF OSCORE protocol profiles for GBA and AKMA | AKMA_GBA_OSCORE | Rel-18 | S3 | June September 2023 | 40% | 80% | Living doc TS 33.220

## Slide 5: AKMA_GBA_OSCORE status after SA3#111
  SA2/RAN impacts and dependencies:
  None. This is an exclusive SA3 topic.
Contentious Issue(s):
  None for the moment.
Focus for the Next (applicable) Meeting (May SA3#111 meeting):
  Draft CR for TS 33.535 for AKMA OSCORE, conversion of draft CR to CR
  Add Ua* protocol identifier in the living document of 33.220 for AKMA OSCORE
  Conversion of the living document to 33.220 for GBA OSCORE to CR
Overall Plan:
  See dedicated slide
Risks:
  None