## Slide 1: SA WG3 Status report for FS_5G_ProSe_Ph2
Wei Zhou
CATT

## Slide 2
August meeting (SA3#108-e, Aug 22-26 , 2022):
  New key issues, new solutions
October meeting (SA3#108-bis-e, Oct 10-14, 2022):
  New key issues, new solutions
November meeting (SA3#109, Nov 14-18 , 2022):
  New key issues, new solutions, solution evaluation, conclusion
January meeting (SA3#109Bis, Jan 16-20 , 2023):
  New solutions, solution evaluation, conclusion
February meeting (SA3#110, Feb20-24 , 2023):
  New solutions, solution evaluation, conclusion,
  WID proposal
April meeting (110Bis, Apr17-21 , 2023):
  New solutions, solution evaluation, conclusion
  Start normative work
May meeting (111, May22-26 , 2023):
  Solution evaluation, conclusion
  Normative work
August meeting (SA3#112, Aug14-18 , 2023):
  Finalize study work (only TR cleanup)
  Finalize normative work
Overall plan (new)
FS_5G_ProSe_Ph2 Status

## Slide 3
TR 33.740 Summary
FS_5G_ProSe_Ph2 Status
 | Key Issues |  |  |  |  |  |  | 
Solutions | 1 | 2 | 3 | 4 | 5 | 6 |  | 
1 | X |  | X | X |  |  |  | 
2 |  |  |  | X |  |  |  | 
3 |  | X | X |  |  |  |  | 
4 |  | X | X |  |  |  |  | 
5 |  | X | X |  |  |  |  | 
6 |  | X |  |  |  |  |  | 
7 |  | X |  |  |  |  |  | 
8 | X |  |  |  |  |  |  | 
9 | X |  |  |  |  |  |  | 
10 |  | X | X |  |  |  |  | 
11 | X |  |  |  |  |  |  | 
12 |  | X |  | X |  |  |  | 
13 | X |  | X | X |  |  |  | 
14 |  | X |  | X |  |  |  | 
15 |  | X | X |  |  |  |  | 
16 | X |  | X |  |  |  |  | 
17 | X |  | X |  |  |  |  | 
18 |  | X |  |  |  |  |  | 
19 |  | X | X |  | X |  |  | 
20 |  | X |  |  |  |  |  | 
21 |  | X |  |  |  |  |  | 
22 |  |  |  |  | X |  |  | 
23 | X |  |  |  |  |  |  | 
24 | X |  |  |  |  |  |  | 
25 |  | X |  |  |  |  |  | 
26 |  | X | X |  |  |  |  | 
27 |  |  |  |  |  | X |  | 
28 | X |  |  |  |  |  |  | 
29 |  | X | X |  | X |  |  | 
30 | X | X |  |  |  |  |  | 
31 | X | X |  |  |  |  |  | 
32 |  | X |  |  |  |  |  | 
33 |  |  |  |  | X |  |  | 
34 |  | X |  |  |  |  |  | 
35 |  |  |  | X |  |  |  | 
36 | X |  |  |  |  |  |  | 
37 | X | X |  |  |  |  |  | 

## Slide 4
General
  TR 33.740 v0.7.0 contains: 6 key issues , 37 solutions
  There are conclusions for KI#1, KI#2, KI#3, KI#4, KI#6
  There are no conclusions for KI#5
Dependencies:
  SA2’s sturdy work on FS_5G_ProSe_Ph2 (TR 23.700-33)
  SA2’s normative work on FS_5G_ProSe_Ph2(TS 23.304)
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
950024 | Study on Security Aspects of Proximity Based Services in 5GS Phase 2 | FS_5G_ProSe_Ph2 | Rel-18 | S3 | May-2023 | 90% | 90% | TR 33.740
FS_5G_ProSe_Ph2 status after SA3#110

## Slide 5
  SA2/RAN impacts and dependencies:
  None for RAN and none determined yet for SA2
Focus of the Next Meeting :
  TR cleanup
Contentious Issues:
  Key issue #1: In Model A, how to ensure validity of protected discovery sets in relay announcements messages is to be addressed during the normative work.
  Key issue #2: L2 U2U E2E security with relay reselection using pre-established communication security keys.
  Key issue #2: DCR message protection in U2U relay communication with integrated discovery.
  Key issue #4: Privacy of End UE (KNRP ID) in L2 U2U during relay reselection.
  Key issue #5: It has not yet reached a conclusion.
Risks:
FS_5G_ProSe_Ph2 status after SA3#111