## Slide 1: Status report for FS_eNS_Ph3 after SA3 #111
Zander Lei
Huawei

## Slide 2
Overall Plan
May 2022 meeting (#107)
  SID approval
July 2022 meeting (#107ah)
  Approval of Skeleton and Scope of TR 33.886
  Proposals for new Key Issues
August 2022 meeting (#108)
  Concentrate on key issues (new and updated)
  New solutions are welcomed
October 2022 meeting (#108ah)
  Key issues and solutions
November 2022 meeting (#109)
  Key issues and solutions
January 2023 meeting (#109ah)
  Key issues and solutions
February 2023 meeting (#110)
  Key issues (no new key issues), solutions, and conclusions
April 2023 meeting (#110ah)
  Key issues (no new key issues), solutions, and conclusions
May 2023 meeting (#111)
  Solutions and conclusions
  WID proposal, if any

## Slide 3
General
  Two solutions were evaluated.
  KI#2 and KI#3 were concluded.
  TR sent to SA for approval
Dependencies:
  SA2’s Study and WID
  TR 23.700-041 concluded and 100% completed
  WID agreed and Normative works are completing
Contentious Issues:
  Nil
Focus for the Next Meeting :
  Wrap up TR
Risks:
  Not foreseen
FS_eNS_Ph3 status after SA3#111
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960029 | Study on enhanced security for network slicing Phase 3 | FS_eNS_Ph3 | Rel-18 | S3 | Mar-2023 | 50% | 90% | 
Key Issues | KI status | Solutions | Solution status
#1 : providing VPLMN slice information to roaming UE | Incomplete (missing threats and requirements) | NA | concluded
#2 : temporary slice authorization and slice service area authorization | complete | 0 | concluded
#3: network slice admission control (NSAC) | complete | 3 | concluded