## Slide 1
SA WG3 Status report for FS_EDGE_Ph2
Bo Zhang
Huawei

## Slide 2
General
  TR 33.739 v0.8.0 contains scope, 9 key issues, and 34 solutions.
Dependencies:
  SA2 SID (TR 23.700-48: "5G System Enhancements for Edge Computing; Phase 2")
    Also approved by SA plenary.
  SA6 SID (TR 23.700-98: "Study on Enhanced architecture for enabling Edge Applications ")
    Also approved by SA plenary.
FS_EDGE_Ph2 status after SA3#111
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
950023 | Study on Security Enhancement of support for Edge Computing — phase 2 | FS_EDGE_Ph2 | Rel-18 | S3 | Q3-2023 | 80% | 90% | TR 33.739

## Slide 3
Key Issues | Solution status (TR) | DraftCR preparation (TS)
Key issue #1.1: How to authorize PDU session to support local traffic routing to access an EHE in the VPLMN | concluded | No
Key issue #1.2: Security of EAS discovery procedure via V-EASDF in VPLMN | Mainly concluded with two common issues on non-roaming and communication between V-EASDF and H-EASDF/DNS | Yes on the security information distribution.
Key Issue #2.1: Authentication and authorization of the EEC/UE by the ECS/EES | concluded | Ongoing
Key issue #2.2: Authentication mechanism selection between EEC and ECS/EES | concluded | Ongoing
Key issue #2.3: Authentication and Authorization between V-ECS and H-ECS | Concluded. | Yes
Key issue #2.4: Transport security for the EDGE10 interface | concluded | Yes
Key issue #2.5: Authentication and Authorization between AC and EEC | concluded | Yes
Key issue #2.6: New KI on authorization between EESes | Mainly concluded with one issue on the necessity of token authorization. | Yes on the local policy at this stage.
Key issue #2.7: EEC provided information verification | New solutions were proposed. To be concluded in August. | To be concluded in August.
TR Summary and TS Plan
FS_EDGE_Ph2 / EDGE_Ph2 Status