## Slide 1: SA WG3 Status report for 5GMARCH_SEC_Ph3
Xiaoting Huang
China Mobile

## Slide 2
TUs planned
1.5 TU
In SA3#115 meeting:
  The main issue of bulk registration solved
In SA3#116 meeting:
  Correction of protocol description and terminology alignement
In SA3#117 meeting:
  Finalise the normative text
Overall plan
5GMARCH_SEC_Ph3 overall plan

## Slide 3
General
  Feature is progressing according to plan
Dependencies:
  SA6 5GMARCH_Ph3 potential update which has SA3 impact
Contentious Issue:
  None
Risks:
  None identified
5GMARCH_SEC_Ph3 status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030030 | Security aspects for MSGin5G Service Phase 3 | 5GMARCH_SEC_Ph3 | Rel-19 | S3 | Mar-2024 | 50% | 70% | Correction of protocol description and terminology alignement

## Slide 4
Pending issues
  None
Dependencies:
  SA6 5GMARCH_Ph3 potential update which has SA3 impact
TUs consumed
  SA3#115 - 0.5
  SA3#116 - 0.5
TUs remaining
  SA3#117 - 0.5
Plan for completion
  SA3#117
5GMARCH_SEC_Ph3 pending work and plan for completion