## Slide 1: SA WG3 Status report for ACME_SBA
Charles Eckel
Cisco Systems

## Slide 2
TUs planned: 3
In SA3#116 meeting:
  Agree/update solutions
In SA3#117 meeting:
  Update solutions and agree conclusions
Overall plan
ACME_SBA overall plan

## Slide 3
General
  TR 33.776 with solutions for most key issues and evaluations for a few key issues
Dependencies
  None
Contentious issues
  None
Focus for next meeting
  Complete solutions and agree remaining evaluations and conclusions
Risks
  None
‘Feature Acronym’ status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1020040 | Study of Automatic Certificate Management Environment (ACME) for the Service Based Architecture (SBA) | FS_ACME_SBA | Rel-19 | S3 | Mar 2025 | 15% | 45% | 

## Slide 4
Pending issues
  None
Dependencies:
  None
TUs consumed
  1.5
TUs remaining
  1.5
Plan for completion
  SA3#120
ACME_SBA pending work and plan for completion