## Slide 1: SA WG3 Status report for ‘FS_AIoT_Sec’
Marcus Wong – OPPO
Longhua Guo - Huawei

## Slide 2
TUs 6
In SA3#115-Adhoc meeting: -
  Get KIs agreed
In SA3#116 meeting -
  Get KIs agreed
  Get solutions agreed
In SA3#117 meeting -
  Get Kis, architecture and assumptions agreed
  Get additional solutions and evaluations agreed
  Get initial conclusion agreed
In SA3#118 meeting -
  Get final solutions agreed
  Get more conclusions agreed
In SA3#119 meeting -
  Finalize all conclusions
  Get TR ready for SA plenary approval
Overall plan
FS_AIoT_Sec overall plan

## Slide 3
General
  40+ contributions from SA3#115-AdHoc
  50 contributions from SA3#116 - 13 not treated (~ 1/4)
Dependencies:
  SA2 on stable architecture
  RAN on device capabilities and protocol stack
Contentious Issue:
  Authentication requirements cannot be agreed
  Communication security requirements cannot be agreed
Risks:
  If authentication and communication security requirements cannot be agreed, solutions to authentication and communication security cannot be proposed and agreed.
  If there is no clarity or stable architecture and end points, SA3 solutions cannot be finalized
‘FS_AIoT_Sec status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1030031 | Security of Ambient IoT services in 5G | FS_AIoT_Sec | Rel-19 | S3 | Nov-2024 | 15% | 30% | +15%

## Slide 4
Pending issues
  Issue#1: there is no agreement on authentication requirement (e.g., termination point of authentication, device authentication, mutual authentication)
  Issue#2: there is no agreement on communication security requirement (e.g., termination points of communication)
Dependencies:
  SA2 on stable architecture
  RAN on device capabilities and protocol stack
  SA1 on service model
TUs consumed
  SA3#115 AdHoc – 1 TU
  SA3#116 – 2 TU
TUs remaining
  SA3#117 – 1 TU
  SA3#118 - 1 TU
  SA3#119 - 1 TU
Plan for completion
  Pre-SA3#117: conference call(s) prior to the meeting #117 to progress untreated contributions, potential solutions
  SA3#117: Get Kis, architecture and assumptions, get additional solutions and evaluations agreed, get initial conclusion agreed
FS_AIoT_Sec pending work and plan for completion